## Form1
UID | ID | What is the Execution Date of the Contract Agreement? | What is the AIA Form of Contract Agreement? | What is the Contract Type for this Project? (Custom Text Answer) | Are there Consequential Damages on the Project? | What are the are the Consequential Damages Terms & Conditions? | Is there a mutual waiver of Consequential Damages in the Contract? | Are there Liquidated Damages on the Project? | What are the are the Liquidated Damages Terms & Conditions? | What is the Article # for Consequential & Liquidated Damages? | What is the CCIP Rate % for this Project? | Is IMC or the Owner carrying the Builder's Risk Policy for this project? | What is the Builders Risk %? | What is the Builders Risk Deductible? ($) | What is the Builders Risk Waiver of Subrogation Appendix / Exhibit (Letter or Number) if the Owner Carries the Policy | Is Professional Liability Insurance Required for this project? | Is Railroad Insurance Required for this project? | Is Pollution Liability Insurance Required for this project? | Is a Payment & Performance Bond Required for this project? | What is the Payment & Performance Bond Article #? | What are the Payment & Performance Bond Article Terms & Conditions? | What is the Contract Documents Definition & Incorporation Article #? | What are the Contract Documents Definition & Incorporation Definitions, Terms, & Conditions? | What is the IMC Design Document Review obligations Article #? | What are the Terms & Conditions / IMC's obligations for Design Document Review? | What is the Submittal Alternates, Substitutions, & Contract Document Deviations Article #? | What are the Submittal Alternates, Substitutions, & Contract Document Deviations Terms & Conditions? | Do we have a Precon Agreement? | Is Precon Reimbursable beyond the Agreement? | What is the Precon Reimbursable Contract Article #? | What are the Precon Reimbursable Terms & Conditions? | What is the Subcontractor Bid Requirements Article #? | Are the Subcontractor Bids / Bid Tabs Required to be Provided to Owner? | What is the Subcontractor Required Number of Bids per package? | What are the Subcontractor Bids / Bid Tabs Provided to Owner Terms & Conditions? | Does a Subcontractor Award have to be Approved by Owner? | Can Owner Mandate Specific Subcontractors be used? | Is IMC Entitled a PCCO for Owner Selected / Mandated Subcontractors? | What is the GMP Shared Savings Article #? | What are the GMP Shared Savings Terms & Conditions? | What is the GMP Buyout Savings Article #? | Do GMP Buyout Savings need to be Reported to Owner? | Must the GMP Buyout Savings be Shown on Monthly Schedule of Values? | What are the GMP Buyout Savings Definition & Terms & Conditions? | Must Use of Buyout Savings for Trade Costs be Approved by Owner? | What is the General Conditions Rate Sheet Appendix / Exhibit (A,B,C,D, Etc.)? | What is the General Conditions Rate Sheet Year? | What is the Cost of the Work Article #? | What is the definition for the Cost of the Work? | What is the Contingency Usage Article #? | What are the Contingency Usage Terms and Conditions? | What are the Contingency Usage Owner Notification Requirements? | What is the General Conditions Type? | What are the General Conditions Billing Backup Requirements? | Are there General Conditions / Requirements Owner Audit Provisions? | What is the definition of General Conditions for this project? (01 v 50 Code Split) | What is the Change Markup - Subcontractor %? | What is the Change Markup - Tiered Subcontractor %? | What is the Change Markup - IMC Fee %? | What is the Change Markup - CCIP %? | What is the Change Markup - Warranty %? | What is the Change Markup - General Conditions %? | What is the Change Markup - CM Insurance %? | What is the Change Markup - P & P Bond %? | What is the Adverse Weather Days Article #? | What are the Adverse Weather Days Terms & Conditions? | Within how many days must we notify the owner of adverse weather day impacts? | How many Adverse Weather Days Included in Contract Agreement? | What is the Schedule Requirements Article #? | What are the Schedule Requirements Terms & Conditions? | What is the Daily Log & Manpower Article #? | What are the Daily Log & Manpower Terms and Conditions? | What is the Schedule Delay / Time Issues Article #? | What are the Schedule Delay / Time Issues Terms & Conditions? | How much Schedule Delay / Time Issues Notice to Owner Requirements (Within What # of Days)? | What is the Schedule Acceleration Directed by Owner Article #? | What are the Schedule Acceleration Directed by Owner Terms & Conditions? | What are the Schedule Definitions of Days (Work / Calendar / Holidays / Etc.)? | What is the Substantial Completion Article #? | What are the Substantial Completion Terms & Conditions? | What is the Final Completion Definition Article #? | What is the Final Completion Definition? | Are there Project Interim Milestones? | Project Interim Milestones List | What is the Payment Terms (Progress & Final) Article #? | What are the Payment Terms Retainage %? | What is the Payment Terms for Retainage Reduction Article #? | What are the Payment Terms & Conditions for Retainage Reduction? | Are there Payment Terms for Retainage on General Conditions? | Are there Payment Terms for Retainage on Fee? | What is the Payment Terms for Offsite Stored Material Article #? | What are the Terms and Conditions for Payment of Offsite Stored Material? | How many days within Approved Application for Owner Payment? | What is the Article # for IMC's Stop Work Ability for late Owner payment? | What are the Terms & Conditions for IMC's Stop Work Ability for late Owner payment? | What is the Dispute Resolution Article #? | What is the CM Suspension / Termination Article #? | How many days notice must the Owner give IMC for CM Termination for Convenience? | How many days notice must the Owner give IMC for CM Termination for Cause? | What is the Direct Negotiation Duration (# of Days)? | What is the Mediation Duration (# of Days)? | What is the Mediator Selection Duration (# of Days)? | How many days after Mediator Selection is the Mediation Session? | What is the Warranty Terms & Conditions Article #? | What are the Warranty Terms & Conditions? | What is the As-Built / Record Documents Requirements Article #? | What are the As-Built / Record Documents Requirements? | What is the Final Payment Article #? | What are the Final Payment Terms & Conditions? | What is the Concealed / Unknown / Hazardous Conditions Article #? | What are the Concealed / Unknown / Hazardous Conditions Terms & Conditions? | How much Concealed / Unknown / Hazardous Conditions Notice to Owner Requirements (Within What # of Days)? | List the Owner / Project Required Reports | Is Owner Allowed to Occupy Building Prior to Substantial Completion Article? | If the Owner is Allowed to Occupy Building Prior to Substantial Completion, what is the Article #? | Hazardous Materials - IMC is Only Responsible Content Created by Us or our Subcontractors | Hazardous Materials - IMC is Entitled to Stop Work, and Recover Cost for Delay for Encountered Hazardous Material | What is the Labor? | Is IMC Responsible to Recover Delay (Cost & Schedule) for labor related work stoppage; strike etc.? | List all Contract Agreement Exhibit / Appendix (Letter / Number /Name) | Are there any Contract Agreement / Specifications Containing BIM Requirements? | What is the Cyber Indemnification / Hacking Article #? | What are the Cyber Indemnification / Hacking Article Terms & Conditions? | Who is Responsible to pay the Builders Risk Deductible? (May Vary Depending on Amount)
1 | 8 | 2023-06-16 | A102 - GMP Cost Plus Fee | GMP | No | N/A - no consequential damages | Yes | Yes | - Reference Exhibit I for LDs per calendar day for each building - Total amount of LDs paid for each calendar day of delay shall not exceed $7,000 - Owner may deduct LDs from any partial payments or final payments - Until LDs are paid to the owner, the owner is entitled to receive interest (6% per annum per A102 - 15.2) |  | 2.5% | Owner | IMC will request a copy of the Owner's policy for confirmation | 25000 | A201 - 11.3.7 | Yes | No | No | Maybe |  | - Owner has the right to require payment and performance bonds, and will most likely do so - Secure bond and finalize Exhibit P after NTP is received - Owner will compensate the contractor for the direct cost only of the Bonds |  | - Contract Documents Include: Contract Agreement, Conditions of the Contract, Drawings, Specifications, Addenda issued prior to contract execution, and modifications issued after execution of the contract - Modifications: Written amendment to the contract signed by both parties, a change order, a constriction change directive, or a written order for a minor change in the work issued by the architect - Intent of the Contract Documents is to include all items necessary for proper execution and completion of work by the contractor - Contract Documents are complimentary - if something is shown on one drawing set it applies to all sets - Contractor owns "reasonable inferences" from the Contract Documents in order to produce indicated - Reference A102 - 1.1.3 for priority hierarchy for interpretations of Contract Documents |  | - Before starting any work, contractor must study and compare the various Contract Documents relative to that portion of the work, as well as: - Take field measurements of any existing conditions related to that portion of the work - Observe any conditions at the site affecting that portion of the work - Promptly report any errors, inconsistencies or omissions found in the Contract Documents to the Architect and Owner as an RFI - Must promply notify with an RFI, or may be liable for costs associated with RFI response per A102 - 3.2.4 - Contractor not responsible for confirming that the Contract Documents are in accordance with applicable laws, codes, etc. - Contractor must promptly report any nonconformities discovered to the Architect and Owner as an RFI - Must promply notify with an RFI, or may be liable for costs associated with RFI response per A102 - 3.2.4 |  | - Prior to submitting an alternate product through the submittal process, the contractor must submit the approved Substitution Form to the Architect and Owner certifying the proposed substitution will: - Perform the function called for by the specified design adequately - Be similar and of equal substance to the specified product - Be suited to the same use and capable of performing the same function as the specified product - Substitution Form must also include: - How acceptance or non-acceptance of the substitute will require a change in the Contract Documents - Design change, schedule or added cost - Note any variations from specified product | No | No |  | N/A - IMC team will attempt to submit for reimbursement of Precon |  | Yes | 3 Typical - No requirement per contract |  | Yes | Yes | Yes |  | - Savings = GMP (including Contractor's fee) - Actual Cost of the Work (including Contractor's fee) - Contractor and Owner share savings 50/50 until the Contractor accrues total savings of $2,400,000 - All savings to the owner after accruing $2,400,000 total ($1,200,000 to Contractor and $1,200,00 to Owner) - Savings on allowances, deduct change orders and Owner approved substitutions/alternates are not included in project savings |  | Yes | Yes | No specific requirements - Buyout savings incorporated into the project contingency | No | Exhibit T | 2023 |  | Costs necessarily incurred by the Contractor in the proper performance of the work - Labor costs (A102 - 7.2) - Subcontract costs (A102 - 7.3) - Costs of materials and equipment incorporated in the completed construction (A102 - 7.4) - Costs of other materials, equipment, temporary facilities and related items (A102 - 7.5) - Misc. costs (A102 - 7.6) - Other costs and emergencies (A102 - 7.7) - Related party transactions (A102 - 7.8) |  | No specific requirements - For any NTE allowance that is overrun, the overrun must be charged against any available contingency | No notification required per stricken A102 - 12.1.5.3 | Reimbursable | Must submit the following (A102 - 12.1.4): - Payrolls consisting of time sheets multiplied to lump sum rates identified in Exhibit T - Petty cash accounts - Receipted invoices or invoices with check vouchers attached | Yes | - IMC staff salaries and expenses for those stationed at the project site - does not include staffing stationed at offices other than site office (A102 - 8.1.1) - Cost and rental charges for temporary facilities, machinery, equipment, temporary protection, temporary construction that are provided by the Contractor (A102 - 7.5.1&2) - Debris removal from site (A102 - 7.5.3) - Document reproduction, telephone and postal expenses (A102 - 7.5.4) - Off site storage facilities (A102 - 7.5.5) | 15% (A201 - 7.5.1.3) | Markup Subcontractors of all tiers collectively shall not exceed 15% of such cost (A201 - 7.5.1.3) | 5% (A201 - 7.5.1.2) | 2.5% (Exhibit T) | 0.1% (Exhibit T) | Based on actual cost (A201 - 7.5.2.1) | 1% (Exhibit T) | 1% (Exhibit T) |  | - Extension of time requests due to adverse weather or conditions not reasonable anticipated will be considered when the delay impacts the critical path - Extensions of time due to adverse weather shall not be considered once the project is "dried in", except as it relates to sitework and weather impacting delivery of material - Contractor not entitled to additional time due to adverse weather unless: - Requirements of A201 - 8.3 are met - There are more than the number of adverse weather days as indicated in the Schedule in the month for which additional time is claimed | 14 (A201 - 15.1.2) | Per NOAA standards for the Project Location |  | - Within 30 days of contract execution, Contractor must submit a construction non-cost loaded CPM schedule for the work reflecting milestone dates and the specific Substantial Completion dates for each phase of the project - CPM schedule shall show start and finish dates for all activities - Activities shall be broken down separately to show material deliveries and labor activities for each phase of the project - Contractor shall prepare and provide 2-week look back and 4-week look ahead schedules as well as monthly updates to the CPM schedule for the entire project |  | Daily Log shall contain details of the weather conditions, materials delivered, work performed, operating hours, and the number of persons working on the project for each subcontractor (A201 - 3.3.4) |  | - If the Contractor is delayed at any time for reasons listed under A201 - 8.3.1, the Contract Time shall be extended by a change order for such reasonable time as the Owner may determine - Schedule and Contract Time shall not be adjusted for any delay to the extent that such delay is caused by the Contractor, or has not impacted the critical path of the Schedule | 14 |  | - Any acceleration of the Work in part or in total for which the Contractor requires a change in any conditions of the Contract (schedule) requires Owner's prior specific approval in writing of such acceleration - Owner reserves the right to perform construction with the Owner's own forces and to award separate contracts (A201 - 6.1.1) - Contractor shall reimburse the Owner for costs the Owner incurs that are payable to a separate contractor because of the Contractor's delays | Calendar | 4 | - Need Certificate of Occupancy or TCO in order to be substantially complete (A201 - 9.8.1) - Contractor shall notify Architect and Owner upon substantial completion and punchlist will be completed - Contractor must include comprehensive list of items still to be complete with notification, along with schedule showing proposed timeline for completing said items - Certificate of Substantial Completion issued once Architect and Owner confirm all punchlist items complete - Certificate establishes date of Substantial Completion - Liquidated damages apply in the event the contractor does not meet the substantial completion date | A102 - 12.2.1 | Reference conditions precedents to Final Completion listed under A201 - 12.2.1 | Yes | - Phase 1 Substantial Completion - 12/16/24 - Phase 2 Substantial Completion - 4/14/25 - Phase 3 Substantial Completion - 8/15/25 - Phase 4 Substantial Completion - 10/17/25 | A102 - 12.1 (Progress) & A102 - 12.2 (Final) | 10% | A102 - 12.1.7.10 | Upon 50% completion of work: - Retainage on each progress payment for that respective portion of the work will be reduced to 5% - 50% of the retainage held on that respective portion of the work shall be released | No | No |  | Owner must approve payment for materials stored offsite in advance - Storage location must be agreed upon in writing - See stored materials invoicing requirements in 9.3.2 | 30 | A201 - 9.7.1 | If Architect does not issue a Certificate for Payment through no fault of the contractor, within 7 days after receipt of the Contractor's application, or the Owner does not pay the Contractor within (60) days after the date established in the Contract Documents the amount certified by the Architect, then the Contractor may, upon 30 additional days written notice to Owner and Architect, file a claim for non-payment and not proceed with work until resolved | 13 | 14 | 10 | 7 | [5 empty] | - Contractor warrants to Owner and Architect that materials and equipment furnished under the Contract will be of good quality and new unless the Contract Documents require otherwise - Contractor warrants that the work will conform with the Contract Documents and will be free from defects - Work, materials or equipment not conforming to these requirements may be considered defective - Contractor's warranty excludes remedy for damage or defect caused by abuse, improper or insufficient maintenance, improper operation, or normal wear and tear and normal usage - Reference Article 12 for warranty period |  | - All mechanical, electrical, underground and other concealed work whose locations vary from those shown on the Contract Documents must be shown on the As-Builts - Must submit the following upon Substantial Completion: - (1) hard copy set of as-builts - (1) electronic version of as-builts | 12.2 | Final payment shall be made to the contractor no later than (60) days following the later of: - The date of issuance of the Architect's final Certificate for Payment - Resolution of all issues relating to any audit the owner elects to perform - The date that all of the preconditions to Final Completion have been fully satisfied (See Final Completion requirements under A102 - 12.2.1) |  | If Contractor encounters site conditions as noted below, the Contractor shall promptly provide written notice to the Owner and Architect before conditions are disturbed and no later than 14 days after the first observance of said conditions. - Subsurface or otherwise concealed physical conditions that different materially from those indicated in the Contract Documents - Unknown physical conditions of an unusual nature, that differ materially from those ordinarily found to exist and generally recognized as inherent in construction activities - Architect and Owner will review, and if agreed that it will impact the Contractor's cost of, or time required to complete the work, the Contract Sum and/or Contract Time will be adjusted | 14 | Reference list under A201 - 3.21.1 | Yes |  | Yes | Yes | Project Labor Agreement | No | - Exhibit A - Project Specifications - Exhibit B - Construction Drawing List - Exhibit C - AIA A201-2017, as amended General Conditions for Construction - Exhibit D - Geotechnical Reports - Exhibit E - Environmental Reports - Exhibit F - Clarifications and Exclusions - Exhibit G - Schedule of Key Personnel - Exhibit H - Contractor's Preliminary Schedule - Exhibit I - Liquidated Damages Agreement - Exhibit J - Cost of Work (Construction Budget) - Exhibit K - Allowances - Exhibit L - Alternates - Exhibit M - Preliminary Schedule of Values - Exhibit N - Bond Agreements - Exhibit O - Lien and Claim Waiver Forms - Exhibit P - Insurance Coverage and Limits - Exhibit Q - Contractor's Safety, Loss Prevention and Security Plan - Exhibit T - Contractor's General Conditions Cost Breakdown and Unit Rates - Exhibit U - Traffic Control Plan - Exhibit X - Subcontract & Purchase Order - Exhibit X1 - Approved Subcontract - Exhibit X2 - Approved Purchase Order | No |  |  | Owner/IMC - $25,000 deductible included in the Cost of the Work per A201- 11.3.1.2
2 | 6 | 2023-03-03 | A102 - GMP Cost Plus Fee | GMP | No |  | No | Yes | Tier 1 = $7,500 per calendar day after Substantial Completion date. Tier 2 = $1,000 per calendar day if Final Completion is not achieved (30)days after Substantial Completion. Tier 3 = $500 per calendar day if model units are not completed within (120)days of Substantial Completion date. | 4.3.1 | 2.5% | IMC | 1.18% | 25000 |  | Yes | No | Yes | No | 15.6.5 | If requested by the Owner, the Contractor shall fumish 100% Performance and Payment Bonds covering the faithful performance of the Contract and the payment of all obligations arising thereunder as required in the Contract Documents, with an issuer or surety satisfactory to Owner and Lender. Such Bonds shall also cover a one-yearwarranty period from the actual date of Substantial Completion of all the Work or such longer warranty periods as required by the Contract Documents and shall be paid as a Change Order to the Contract. | Article 1 | The Contract Documents are enumerated in the Agreement between the Owner and Contractor (as hereinafter defined in Sec. 1.1.9) and consist of the Agreement, all Exhibits to the Agreement (and the documents referenced therein), Conditions of the Contract (General, Supplementary and other Conditions), Drawings, Specifications, Addenda issued prior to execution of the Contract, other documents listed in the Agreement and Modifications issued after execution of the Contract. A Modification is (1) a written amendment to the Contract signed by both parties, (2) a Change Order, (3) a Construction Change Directive or (4) a written order for a minor change in the Work issued by the Architect and approved by the Owner. Unless specifically enumerated in the Agreement, the Contract Documents do not include the advertisement or invitation to bid, Instructions to Bidders, sample forms, other information furnished by the Owner in anticipation of receiving bids or proposals, the Contractor's bid or proposal, or portions of Addenda relating to bidding requirements. | 3.2 | Contractor shall review carefully and verify all Contract Documents as required by Section 2.3 of the agreement and this Section 3.2 and report discrepancies, inconsistencies or errors discovered by Contractor to the Architect and owner, in writing, in ample time so that corrections, if any, may be made without delaying the work or involving additional expense. Figures on drawings take precedence over measurements by scale. Scaling is done at the Contractor's own risk. Figures and notations on large scale drawings shall take precedence over small scale drawings. Material, sizes, notations and descriptions in specifications take precedence over drawings. Should Contractor fail to notify Owner and Architect of any discrepancies, inconsistencies or errors that it is required to report to Owner and Architect under this Section 3 .2.3, Contractor is responsible, at its own expense, to make any corrections or perform any Work arising from such failures to notify Owner and Architect. GMP assumes that the Owner’s Design Team has coordinated the Design between different design disciplines. GMP assumes the Architect will be responsible to coordinate all the design disciplines to resolve design conflicts among the Contract Documents, except for any design conflicts pertaining to design that has been delegated IMC and/or its Subcontractors. | 3.12.8 | The Work shall be in accordance with approved submittals except that the Contractor shall not be relieved of responsibility for deviations from requirements of the Contract Documents by the Architect's approval of Shop Drawings, Product Data, Samples or similar submittals unless the Contractor has specifically informed the Architect and owner in writing of such deviation at the time of submittal and (l) the Architect and owner have given written approval to the specific deviation as a minor change in the Work, or (2) a Change Order or Construction Change Directive has been issued authorizing the deviation. The Contractor shall not be relieved of responsibility for errors or omissions in Shop Drawings, Product Data, Samples or similar submittals by the Architect' s approval thereof. | Yes | No |  | $100,000 was included in GMP for precon. | 10.2 | Yes | N/A | Those portions of the Work that the Contractor does not customarily perform with the Contractor's own personnel shall be performed under subcontracts or by other appropriate agreements with the Contractor. The Owner may designate specific persons from whom, or entities from which, the Contractor shall obtain bids. The Contractor shall obtain bids from Subcontractors and from suppliers of materials or equipment fabricated especially for the Work and review such bids with the Owner. The Contractor shall then determine, with the advice of the Owner, which bids will be accepted. The Contractor shall not be required to contract with anyone to whom the Contractor has reasonable objection' The Contractor shall not contract with anyone to whom the Owner has a reasonable objection as set forth in Section 5.2 of the AIA Document A2011017, as modified. | Yes | Yes | Yes | 5.2.7 | Any cost Savings shall be shared by the contractor and owner as follows: Fifty percent (50%) to the Owner and fifty percent (50%) to the Contractor. "Cost Savings" shall mean the difference between the (1) Cost of the Work plus the Contractor's Fee, and (2) the Guaranteed Maximum Price, as modified. | 5.2.6 | Yes | Yes | Thirty percent (30%) to the Owner and seventy percent (70%) to the Contractor for Cost Savings declared by Contractor in months one (l) through three (3) of the Agreement term. Forty percent (40%) to the Owner and sixty percent (600/o) to the Contractor for Cost Savings declared by Contractor in months four (4) through six (6) of the Agreement term. Fifty percent (50%) to the Owner and fifty percent (50%) to the Contractor for Cost Savings determined via final project cost audit or accounting. | No | Exhibit N | 2023 | 7.1 | The term Cost of the Work mean costs necessarily incurred by the Contractor in the proper performance of the Work. Such costs shall be at rates not higher than the standard paid ai the place of the Project except with prior written consent of the Owner' The Cost of the Work shall include only the items set forth in this Article 7 and shall not include any costs associated with home office personnel or any overhead costs because such items are included as part of the Contractor's Fee. | NA | NA | NA | Reimbursable | Provide backup of all costs | Yes | NA | NA | NA | 3 | 2.5 | 0 | 0 | 1 | 0 | 8.7.1.3 | Contractor shall be entitled to request change orders for equitable increases in the Contract Time for completion due to bad weather only if (a) the weather experienced at the Project site during the term of this Agreement is more severe than the adverse weather anticipated for the Project location during any given month, (b) the unusually severe weather must actually cause a delay to the critical path for the completion of the project, and -(c) the delay must be beyond the control and without the fault or negligence of the Contractor. If the conditions of this Section 8.1.7.3 are met, the delay(s) shall be referred to as a Weather Delay. | At Progress meetings | 48 | 3.10 | The Project Schedule and CPM Schedule (defined below) shall be updated monthly and included with the Contractor's Application for Payment for review and approval by the Owner. If the Project Schedule and CPM Schedule (defined below) are not updated monthly, the Owner, in its sole discretion, may delay payment of Contractor's Application for Payment in an amount equal to the greater of (a) $50,000 or (b) ten percent (10%) of the payment sought by Contractor in such Application for Payment until a revised Project Schedule and CPM Schedule (defined below) are provided. The Project Schedule shall contain the dates that are critical in ensuring the timely and orderly completion of the Work in accordance with the requirements of the Contract Documents. The date(s) of Substantial Completion of the Work (or portions thereof if the Agreement contemplates phases of Work) in each revision to the Project Schedule shall be consistent with the date(s) of Substantial Completion, or the total number of days from commencement until Substantial Completion, set forth in the body of the Agreement, as said date(s) may be extended pursuant to the provisions of the Contract Documents. In addition to the Project Schedule updates described herein, the Owner may also require the Contractor to provide throughout the course of the Project two-week "look ahead" schedules of such detail which is reasonably acceptable to the Owner. | NA | NA | 8.3 | The Contractor shall not be entitled to any such extension of time for Excusable Delays unless (a) the contractor notifies the Owner in writing within five (5) days after the Contractor knows of, or in the exercise of reasonable diligence should have known of, the occurrence of an event giving rise to an alleged Excusable Delay; and (b) within thirty (30) days after providing such written notice, the Contractor shall submit the following additional information to the owner and Architect: (i) a written statement of the nature and cause of the claim; (ii) a complete and detailed CPM Schedule (including fragnets) showing how the delay adversely impacts the critical path of the project and the date(s) of Substantial Completion of the Work; and (iii) an itemized and substantiated statement of the time extension or dollar amount requested (for Owner Delays only) or, if sufficient information to do so is unavailable, then a reasonable estimate of the time extension or dollar amount (for Owner Delays only) supported by such documentation as the Owner may request. If the Contractor submits said reasonable estimate, the Contractor shail submit the itemized and substantiated statement of the time extension or dollar amount requested within fifteen (15) days after the reasonable estimate is delivered to the Owner and Architect. To the extent the Contractor cannot demonstrate to the reasonable satisfaction of the Owner that the Excusable Delay adversely impacts the critical path thereby requiring an extension of one or more of the dates of Substantial Completion, no extension of time shall be granted. | 5 | NA | NA | Duration is 586 calendar days. all days in contract are Calendar days. | 9.8.1 | When the Work is determined by the Owner to be complete in accordance with the Contract Documents, such that all interior and exterior construction, including without limitation, all components, systems, facilities, amenities, common areas, and portions of the Work' have been completed and is habitable, operational, and useable for the Owner's intended purposes (such that the units are fully leasable or saleable and the occupants of the units will have full use and enjoyment of all aspects and amenities), except for incidental corrective work, cleaning beyond the cleaning needed for Owner's intended use (which may remain for Final Completion), and minor commissioning and balancing work which may take place in conjunction with the Owner's set-up for operations activities for the Project. The Contractor acknowledges that the issuance of Use and occupancy permits are a condition precedent to the Substantial Completion of the Work unless withheld by no fault of the Contractor | 9.10 | Upon receipt of the Contractor's written notice that the Work is ready for final inspection and acceptance and upon receipt of a final Application for Payment, the Architect will promptly make such inspection and, when the Architect finds the Work acceptable under the Contract Documents and that all of the obligations of the Contractor under the Contract have been fully performed, the Architect will promptly issue a final Certificate for payment stating that to the best of the Architect's knowledge, information and belief, and on the basis of the Architect's on-site visits and inspections, the Work has been completed in accordance with terms and conditions of the Contract Documents and that the entire balance found to be due the Contractor and noted in the final Certificate is due and payable. | Yes | Mock wall - 120days after commencement Model units - 120days prior to substantial completion | 12.1.4 | 10% | 12.1.8 | When the Work is (50%) complete. as certified by the Architect. Contractor may request that the Owner not retain any additional amounts from subsequent progress payments. The Contractor may also request. and the Owner will also reasonably consider. reducing retainage for subcontractors completing their work prior to that date on which (50%) of the Work has been completed by Contractor. The Contractor must provide consent of surety, if applicable. prior to the Owner's consideration of the Contractor's request. Any decision to not withhold further retainage or to reduce retainage shall be at the sole discretion of the Owner. Upon Substantial Completion. such retainage shall be reduced to amount equal to 150% of the cost to complete any punch list items and any incomplete Work, and such amount shall be withheld until Final Payment. | No | No | 9.3.2 | If approved in writing, payments for stored materials offsite may be made at the owner and lenders discretion. | 25 days | 9.7 | if the owner does not pay the Contractor within seven days after the date established in the Contract Documents the undisputed amounts due or awarded by binding dispute resolution, then the Contractor may, upon seven additional days, written notice to the owner and Architect, stop the Work until payment of the undisputed amount owing has been received. Such cessation of Work shall be deemed to be an Excusable Delay under the provisions of Section 8.3 and the Contract Time and/or Contract Sum shall be adjusted to the extent permitted by Section 8.3 Notwithstanding the foregoing, in the event the unpaid amount owing to Contractor is less than 5% of the total amount of the approved advance, then Contractor shall not have the right to stop the Work unless such unpaid amount remaining outstanding for forty-five (45) days after the date for payment established in the Contract Documents and then only upon seven additional days' written notice to the Owner and Architect. | 13 | 14 | 0 days | 7 days | 15 days | 15 days |  | 60 days | 3.5 | warranty for 1 yr period from date of substantial completion. See exhibit P for greater detail. | Noted in Qualifications, also article | Provided in electronic format only. | 9.10 | Upon final notification of completion to architect and final pay application submission the architect will make a final inspection. If complete, the architect will issue a certificate of final completion. Neither final payment nor any remaining retained percentage shall become due until the Contractor submits to the Architect (1) an affidavit that payrolls, bills for materials and equipment, and other indebtedness connected with the Work for which the Owner or the owner's property might be responsible or encumbered (less amounts withheld by Owner) have been paid or otherwise satisfied, (2) a certificate evidencing that insurance required by the Contract Documents to remain in force after final payment is currently in effect and will not be canceled or allowed to expire until at least 30 days' prior written notice has been given to the Owner, (3) a written statement that the Contactor knows of no substantiate reason that the insurance will not be renewable to cover the period required by the Contract Documents, (4) consent of surety, if any, to final payment (5) other data establishing payment or satisfaction of obligations, such as receipts, releases and waivers of liens, claims, security interests or encumbrances arising out of the Contract, to the extent and in such form as may be designated by the owner or Lender; (6) one (l) f;ll set of the Redline Record Drawings of the work; (7) conditional and unconditional final lien waivers for all Subcontractors in the forms of Exhibits G-2 and G-4 of the Agreement and a final payment lien waiver from Contractor conditioned only upon receipt of payment in the form of Exhibit G-2 of the Agreement; (8) all manufacturers' warranties to be transferred to Owner (with evidence of transfer); (9) all operating and maintenance manuals; (10) any other deliverables required by the Contract Documents, and (l l) if required by the Owner or Lender, a final certification by the Contractor that all Work has been completed in accordance with the Contract Documents. Subject to the written approval of the Owner and Lender, if a Subcontractor refuses to furnish a release or waiver required by the Owner or Lender, the Contractor may furnish a bond satisfactory to the owner and Lender to indemnify the owner and Lender against such lien. If such lien remains unsatisfied after payments are made, the Contractor shall refund to the Owner all money that the Owner may be compelled to pay in discharging such lien, including all costs and reasonable attorneys' fees' | In Qualifications as well as article 3.7.4 | GMP pricing is based on classified excavation and does not include costs and/or handling associated with poor soils, obstructions, sinkholes, or other unknown, concealed, or uncharted conditions IMC Shall notify owner and architect no later than 14 days. | 14 days. | Owner reports due with monthly draw Monthly photo report submittal and rfi log OAC Meeting minutes Schedule update | No |  | Yes | Yes | Non-Union | Yes | Schedule of Exhibits ExhibitA: Construction Schedule Exhibit B: Unit Prices, Altemates, Allowances and Assumptions Exhibit C: Schedule of Values Exhibit D: Specs Exhibit E: Drawings Exhibit F: N/A Exhibit G-l: conditional Lien waiver Form for Subcontractors and contractor (progress payments) Exhibit G-2: conditional Lien waiver Form for subcontractors and contractor (Final payment) Exhibit G-3: Unconditional Lien Waiver Form for Subcontractors (progress payments) Exhibit G-4: Unconditional Lien Waiver Form for Subcontractors (Final payment) Exhibit H: White Glove Standards Exhibit I: Environmental / Geotech Reports Exhibit J: List of Entities for Insurance Purposes Exhibit K: Bonding Plan Exhibit L: Responsibility Matrix Exhibit M: Form of Contractor Notice of Substantial Completion Date Exhibit N: Reimbursable General Conditions Expenses Exhibit O: Form of Construction Change Directive Exhibit P: Warranty Process Standard Exhibit Q: Builders' Risk Requirements | No | 3.18
3 | 3 | 2023-05-22 | Custom Contract | GMP: At Risk | No | N/A | Yes | Yes | $2,000/day beyond the Substantial Completion date | 3.3 Liquidated Damages in lieu of consequential damages; General Conditions 4.3.10 mutual waiver of consequential damages | 2.5 | IMC | CM 1% ; BR 0.35% | CM $5,000/claim; BR $10,000 for all losses except flood, earthquake, and windstorm to be $25,000 | N/A | Yes | No | Yes | Yes | Exhibit J - Section 6 (Page 13) | Performance and Labor and Materials Bond (AIA 312) equal to 100% of Contract Price and amended by change orders if approved by owner and at the time of Contract award remaining in full effect through warranty and extended warranty periods. Amount paid as cost of work is limited to premium evidenced on an invoice from surety. | General Conditions of GMP - 1.1.1 | Contract Documents: - Agreement - General Conditions of the Contract - Supplemental and other Conditions - Amendments - Drawings - Specifications - Addenda issued prior to execution of Agreement - other documents listed in Agreement - Modifications/Change Orders issued after execution of Agreement (written amendment signed by both parties, Change Order, Construction Change Directive, Written order for a minor change in teh Work issued by Owner, ASI signed by both Owner and Architect | Agreement 13.2 | Within 60 days of receipt of completed construction drawings and specs, Contractor perform review and notify in writing scope changes that could not have been reasonably discernable at time of Contract Sum/Time were agreed | 3.4.2, 3.5.5, 3.5.7 | 3.4.2- need express written consent by owner after evaluation by Architect 3.5.5- quality of result at least equal with supporting evidence, approved substitution that requires deviations to related work Contract is responsible to present detailing and costs associated with performing deviation work, approval of substitution does not relieve Contractor from liability for failure to comply with Contract Documents 3.5.7 - Costs as a result of unapproved substitutions are borne by Contractor | No | No | N/A | N/A | Agreement 8.1, 8.2; General Conditions 5.2 | Yes | N/A | Within 120 days after award of Contract provide entities proposed for each principal portion of the Work. Owner/Architect to reply promptly in writing any objections. Contractor may not contract with proposed entity that Owner/Architect have reasonable/timely objection | No | No | Yes | Agreement 4.3 | Sliding scale first $100,000 30% to Contractor reducing 5% each $100,000 thereafter up to $500,000 and Contractor's share capped at $100,000 | N/A | No | No | N/A | No | Exhibit E | 2023 | Agreement - Article 5 | - General Conditions - Labor Costs - Subcontract Costs - Materials and Equipment - Temp facilities - Rental Charges - removal of debris - document reproductions - expenses - offsite stored materials if approved in advance by owner in writing - insurance/bond premiums - sales/use tax - permit fees, licenses, inspections - testing - legal fees - other costs associated with performance of work and to the extent approved by owner in writing | Agreement 4.3.1 | - cover costs reimbursable as a cost of the work - not reasonably anticipated at time of Agreement - refinement of drawing details - corrective work not due to fault/negligence - nonperformance by sub - unanticipated costs - unintended gaps/omissions - cannot be used for items due to negligence, fee, cost of work recovered from subcontractor/bond/insurance, cost of work that could have been reasonably avoided, item that does not constitute cost of work | - Use authorization form required for proposed uses above $35,000 and any General Conditions costs - Monthly report of Contingency use required | Other | - payroll for the period covered by pay application - invoices to substantiate pay requests | Yes | Agreement - Article 5 | 15 | 15 | 2.75 | 2.5 | N/A | N/A | 1 | 1 | General Conditions 4.3.7.2 | Abnormal conditions as compared to NOAA 10-yr average affecting critical path work | 21 days |  | General Conditions 3.10 | - Update Contract Schedule with each pay application - Submittal schedule to be coordinated with Contract Schedule; if submittal schedule is not maintained Contractor may not claim delay due to submittal review - Changes in Contract Schedule are only accepted via Change Order - Contractor delays/recovery to schedule are reimbursable only within GMP - Owner may direct in writing acceleration of schedule and reimbursed unless attributable to Contractor's actions - Prior to commencement of work, Contractor shall submit milestone schedule to Owner for approval to ensure timely completion. Recovery plan due to Contractor negligence and costs associated are borne by Contractor | General Conditions 3.11.1.2 | Maintain record set of meeting minutes and daily log available to owner and submitted upon completion of work | General Conditions 4.3.7 | - requires written notice within 21 days - entitled to an extension of time for failure to act, direction, order, neglect, delay or default of owner, arch/engineer, or any other contractor employed under the Project; changes in the work; fire, lightning, earthquake, enemy action, act of God, epidemic or pandemic, or similar catastrophe; by government restrictions in respect to materials or labor; by labor disputes beyond Contractor's reasonable control - impact to critical path only - | 21 days | 3.10.7 | - Owner may direct in writing acceleration of schedule and reimbursed unless attributable to Contractor's actions | Calendar | Agreement 3.3; General Conditions 9.8 | - 462 days from Commencement Date - all work sufficiently complete in accordance with Contract Documents as required to allow for licensing inspection so Owner can occupy and utilize the work for its intended use - Certificate of Occupancy are issued - all finishes complete exclusive of punchlist - all closeouts are been provided to owner - Architect has issued Certificate of Substantial Completion | Agreement 3.3; General Conditions 9.10 | - Work is ready for final inspection and acceptance - Receipt of final pay app - Architect accepts and provides cert of final completion - Owner may issue 3-day notice to cure after 45 days from Substantial Completion if work is not complete and within additional 15-day period owner may supplement Contractor to complete all work | Yes | - Access for Sales trailer/marketing office 9 months prior to substantial completion - model units 3 months prior to substantial completion | Agreement Article 11 | 10 | 11.1.9 | 10% through 50% complete on a line item basis. Once line item reaches 50% no additional retainage is held | No | No | General Conditions 9.3.2 | If approved in advance by the Owner, payment may similarly be made for materials and equipment suitably stored off the site at a location agreed upon in writing. Payment for materials and equipment stored on or off the site shall be conditioned upon compliance by the Contractor with procedures satisfactory to the Owner to establish the Owner's title to such materials and equipment or otherwise protect the Owner's interest, and shall include the costs of applicable insurance, storage and transportation to the site for such materials and equipment stored off the site. The Contractor shall be responsible for any loss or damage to unincorporated materials or equipment stored offsite not covered by insurance. | 30 | General Conditions 9.7 | If the Architect does not issue a Certificate for Payment for which the Owner and Contractor agree that an undisputed amount is due, through no fault of the Contractor, within forty-five (45) days after receipt of the Contractor's Application for Payment, or if the Owner does not pay the Contractor within seven (7) days after the date established in the Contract Documents the amount certified by the Architect, then the Contractor may, upon seven (7) additional days' written notice to the Owner and Architect, stop the Work until payment of the amount owing has been received. The Owner shall compensate the Contractor for the reasonable costs of shutdown and start-up, but this provision and such compensation shall nonetheless not be deemed to conflict with the “No Damages for Delay” provision set forth in the Contract, but shall be read in conjunction therewith. Notwithstanding the foregoing, if the Owner and Contractor have a payment dispute, the Contractor shall proceed with the Work without delay, subject to Contractor’s right to assert a claim in accordance herein. | General Conditions 4.3 | General Conditions 14.1 | 0 | 7 | 30 | N/A | N/A | N/A | General Conditions 3.5 | Warranty period commences at substantial completion and conforming to contract documents | General Conditions 9.8 | If required by lender to be submitted as part of substantial completion | General Conditions 9.10 | § 9.10.2 Neither final payment nor any remaining retained percentage shall become due until the Contractor submits to the Architect (1) an affidavit that required payrolls, bills for materials and equipment, and other indebtedness connected with the Work for which the Owner or the Owner's property might be responsible or encumbered (less amounts withheld by Owner) have been paid or otherwise satisfied, (2) a certificate evidencing that insurance required by the Contract Documents to remain in force after final payment is currently in effect and will not be canceled or allowed to expire until at least thirty (30) days' prior written notice has been given to the Owner, (3) a written statement that the Contractor knows of no substantial reason that the insurance will not be renewable to cover the period required by the Contract Documents, (4) consent of surety, if any, to final payment, (5), the lien waiver and release forms required under the Contract Documents, executed by Contractor and any other necessary parties, and (6) a letter copied to the Owner, stating that all close out Operations and Maintenance manuals and warranties have been submitted per Contract Document requirements. This scope shall include all “Architectural” and “Mechanical, Plumbing and Electrical” operations and maintenance manuals and warranty information. If the Contractor fails to furnish such releases or waivers as noted in item (5) as the Owner reasonably requires to satisfy the Owner that there are no outstanding liens, including outstanding liens by Subcontractors at any tier level, the Owner may require the Contractor, as a condition of final payment, to furnish a bond satisfactory to the Owner and meeting the requirements set forth in § 9.3.5 above. If a Subcontractor refuses to furnish a release or waiver required by the Owner, the Contractor may furnish a bond satisfactory to the Owner to indemnify the Owner against such lien and such personal liability arising from such claim. If such lien remains unsatisfied after payments are made, the Contractor shall refund to the Owner all money that the Owner may be compelled to pay in discharging such lien, including all costs and reasonable attorneys' fees. Contractor agrees that it will obtain the agreement of each of its Subcontractors and Suppliers in its contracts with such parties that its Subcontractors and Suppliers will execute the lien waivers and releases. | General Conditions 4.3.4 | § 4.3.4 Concealed or Unknown Conditions. If the Contractor encounters conditions at the site that are (1) subsurface or otherwise concealed physical conditions that differ materially from those indicated in the Contract Documents or (2) unknown physical conditions of an unusual nature, that differ materially from those ordinarily found to exist and generally recognized as inherent in construction activities of the character provided for in the Contract Documents, the Contractor shall promptly provide notice to the Owner and the Architect before conditions are disturbed and in no event later than twenty-one (21) days after first observance of the conditions. The Architect will promptly investigate such conditions and, if the Architect determines that they differ materially and cause an increase or decrease in the Contractor’s cost of, or time required for, performance of any part of the Work, will recommend an equitable adjustment in the Contract Sum or Contract Time, or both. If the Architect determines that the conditions at the site are not materially different from those indicated in the Contract Documents and that no change in the terms of the Contract is justified, the Architect shall promptly notify the Owner and Contractor in writing, stating the reasons. If either party disputes the Architect’s determination or recommendation, that party may proceed as provided in the Disputes provisions. | 21 | Monthly Contingency Tracking Log | Yes | General Conditions 9.9 | Yes | Yes | Non-Union | No | EXHIBIT A: Documentation List EXHIBIT B: Qualifications EXHIBIT C: Contract Schedule _ EXHIBIT D: Waivers EXHIBIT E: Reimbursable Cost of Work EXHIBIT F (a): Allowances 4.20.23 EXHIBIT F (b): VM List EXHIBIT H: GC and GR Breakdowns 4.4.23 EXHIBIT I: Cost Breakdown rev 4.20.23 EXHIBIT J: Insurance Requirements EXHIBIT K: Consent to Assignment Forms EXHIBIT L: Use Authorization Forms | No | N/A | N/A §11.1.11 Contractor shall provide Owner, upon execution of this Agreement, written instructions and all necessary forms required by Owner to effectuate payment to Contractor by check or wire transfer. If Contractor sends to Owner a request to change such payment information, Owner agrees that it will not modify or make a change to this payment information until Contractor's President and CEO or Chief Financial Officer, provides oral confirmation and Contractor provides Owner with a notarized confirmation from Contractor's Chief Financial Officer. Owner shall make no changes to the payment information if it does not receive both oral and written confirmation as stated herein.
4 | 23 | 2025-02-10 | A102 - GMP Cost Plus Fee | GMP | Yes | A201 – Article 15.1.6 This mutual waiver is applicable. without limitation. to all consequential damages due to either part),'s termination in accordance with Article 14. Nothing contained in this Section 15.1.6 shall be deemed to preclude an award of liquidated damages" when applicable. in accordance with the requirements of the Contract Documents. | Yes | Yes | First-tier - Substantial Completion - the Owner may assess and the Contractor shall then be liable for payment of First-tier Liquidated Damages in the amount of $7,500 per calendar day for each day the actual date of Substantial Completion of the Work exceeds the scheduled date of Substantial Completion set forth in Section 4.3 Second-Tier - Final Completion - After the actual date of Substantial Completion of the Work, the Owner will continue to suffer financial loss if the Contractor fails to achieve Final Completion within thirty (30) days after the actual date of Substantial Completion. If the Contractor fails to achieve Final Completion within thirty (30) days after the actual date of Substantial Completion, the Owner may assess and the Contractor shall then be liable for payment of Second-tier Liquidated Damages in the amount of $1,000 per calendar day for each day the actual date of Final Completion exceeds thirty (30) days after the actual date of Substantial Completion. Third-tier - Model Units - These Model Units shall be completed, permitted for occupancy and usable for Owner's intended purpose at least one hundred twenty (120) days prior to the projected date of Substantial Completion of the Work (the "Model Unit Milestone"). If the Contractor fails to complete the Model Units by the Model Unit Milestone the Owner may assess and the Contractor shall then be liable for payment of Model Unit Milestone Liquidated Damages in the amount of $500 per calendar day for each day the actual completion of the Model Units exceeds the Model Unit Milestone. |  | 2.5% | IMC | 1.4% | 25000 |  | Yes | No | Yes | No |  |  |  | The Contract Documents consist of this Agreement, all Exhibits to the Agreement (and the documents referenced therein), Conditions of the Contract (General, Supplementary and other Conditions), Drawings, Specifications, Addenda issued prior to execution of this Agreement, other documents listed in this Agreement and Modifications issued after execution of this Agreement, all of which form the Contract, and are as fully a part of the Contract as if attached to this Agreement or repeated herein. The Contract represents the entire and integrated agreement between the parties hereto and supersedes prior negotiations, representations or agreements, either written or oral. If anything in the other Contract Documents, other than a Modification, is inconsistent with this Agreement, this Agreement shall govern. All capitalized terms used herein are either defined herein or in the AIA Document A2011017, as modified. |  | $ 2.3 Contractor Review. $ 2.3.1 The Owner and the Contractor agree that the Owner has selected the Contractor for this Project because of the Contractor's special expertise in constructing similar projects. Before executing this Agreement and before commencing construction for any phase of the Work, the Contractor carefully reviewed and shall carefully review all Contract Documents, all Legal Requirements, and the environmental and geotechnical reports, if any, included as exhibits to the Agreement (hereinafter, the "Environmental/Geotechnical Reports"). The Contactor shall construct the Project in strict accordance with the Contract Documents including the Environmental/Geotechnical Reports. $ 2.3.2 The Contractor understands that the Work requires all construction necessary to result in a complete and functioning Project, including fully functioning components in accordance with the Contract Documents, and the Contractor shall perform all construction necessary to result in a completed and functioning Project, including fully functioning components. in accordance with the Contract Documents, notwithstanding, among other things, any obviously missing (a) information, (b) errors, (c) omissions, (d) inconsistencies, or (e) lack of coordination in the Contract Documents that an experienced contractor that has constructed many similar projects and performed preconstruction services on the Project could reasonably have recognized during any preconstruction efforts or the bidding and negotiation of the Guaranteed Maximum Price to construct the Project (hereinafter, "Discoverable Errors"). Therefore, the Contractor represents that if there are any such Discoverable Errors in the Contract Documents, the Contractor shall promptly report them to the Owner; however, unless the Owner and Contractor mutually agree otherwise, the cost to perform any additional Work necessary to complete the Project and any alleged delays or time impacts resulting therefrom, shall not form a basis for an increase in the Guaranteed Maximum Price or the Contract Time if such cost and time impacts would have been avoided if the Contractor had properly performed its obligations under this Section 2.3. $ 2.3.2,1 If there are errors, omissions, inconsistencies or lack of coordination in the Contract Documents that an experienced contractor that has constructed many similar projects could not reasonably have recognized during any preconstruction efforts or the bidding and negotiation of the Guaranteed Maximum Price, then the Contractor shall promptly report them to the Owner. and the Contractor shall be entitled to a Change Order increasing the Guaranteed Maximum Price in an amount equal to the cost to perform additional Work necessary to complete the Project or the increase in the Contract Sum resulting from an impact on other Work or any additional Work necessary to complete the Project and, to the extent applicable, extending the Contract Time pursuant to Section 8.3 of the AIA Document A2011017, as modified, as may be reasonably agreed to by the parties. |  |  | Yes | No |  | $100,000 of precon is built into the GMP and is billable. |  | No |  |  | Yes | Yes | Yes |  | "Buy-Out Savings" shall mean the difference between (i) the sum of the subcontract amounts in the schedule of values attached as Exhibit C and (ii) the sum of the actual amounts of the subcontracts entered into by the Contractor for the performance of the Work. Any Buy-Out Savings shall be shared by the Contractor and Owner as follows: Thirty percent (30%) to the Owner and seventy percent (70%) to the Contractor for Cost Savings declared by Contractor in months one (l) through three (3) of the Agreement term. Forty percent (40%) to the Owner and sixty percent (60%) to the Contractor for Cost Savings declared by Contractor in months four (4) through six (6) of the Agreement term. Fifty percent (50%) to the Owner and fifty percent (50%) to the Contractor for Cost Savings determined via final project cost audit or accounting. Upon declaration of the Buy-Out Savings, the Contractor shall provide the Owner with documentation reasonably requested by Owner to substantiate the Buy-Out Savings. The percentage of the Buy-Out Savings allocated to the Owner according to the foregoing schedule shall be subtracted from the Guaranteed Maximum Price through a deductive Change Order to be executed by the parties promptly after the declaration of the Buy-Out Savings. The portion of the Buy-Out Savings allocated to the Contractor shall be added to the Contractor's Fee, and become eligible for billing in accordance with Article 12 hereof promptly after the execution of the aforementioned Change Order. Any Cost Savings shall be shared by the Contractor and Owner as follows: Fifty percent (50%) to the Owner and fifty percent (50%) to the Contractor "Cost Savings" shall mean the difference between the (l) Cost of the Work plus the Contractor's Fee, and (2) the Guaranteed Maximum Price, as modified. |  | Yes | Yes | The Contractor shall exercise reasonable good faith efforts to reduce the actual amounts ofthe subcontractor trade costs through bidding, rebidding, negotiation, or otherwise. "Buy-Out Savings" shall mean the difference between (i) the sum of the subcontract amounts in the schedule of values attached as Exhibit C and (ii) the sum of the actual amounts of the subcontracts entered into by the Contractor for the performance of the Work | Yes | Exhibit N | 2025 |  | 7.1.1 The term Cost of the Work mean costs necessarily incurred by the Contractor in the proper performance of the Work. Such costs shall be at rates not higher than the standard paid at the place of the Project except with prior written consent of the Owner. The Cost of the Work shall include only the items set forth in this Article 7 and shall not include any costs associated with home office personnel or any overhead costs because such items are included as part of the Contractor's Fee. |  | Not stated | Not stated | Reimbursable | Provide Backup of All Costs | Yes | 01 codes. only Labor | Not stated | Not stated | 3% | 2.5% | Not stated | 0 | 1 | 0 |  | Contractor shall be entitled to request change orders for equitable increases in the Contract Time for completion due to bad weather only if (a) the weather experienced at the Project site during the term of this Agreement is more severe than the adverse weather anticipated for the Project location during any given month, (b) the unusually severe weather must actually cause a delay to the critical path for the completion of the Project, and (c) the delay must be beyond the control and without the fault or negligence of the Contractor. If the conditions of this Section 8.1.7'3 are met, the delay(s) shall be referred to a "Weather Delay". | 5 days | 54 |  | The Contractor shall prepare a submittal schedule, promptly after being awarded the Contract and thereafter as necessary to maintain a current submittal schedule, and shall submit the schedule(s) for the Architect's approval' The Architect's approval shall not unreasonably be delayed or withheld. The submittal schedule shall (l) be coordinated with the Contractor's construction schedule, and (2) allow the Architect reasonable time to review submittals. If the Contractor fails to submit a submittal schedule, the Contractor shall not be entitled to any increase in Contract Sum or extension of Contract Time based on the time required for review of submittals. Failure of the Contractor to deliver a submittal schedule shall entitle the Owner to withhold progress payments for the Work in an amount equal to the greater of (a) $50,000 or (b) ten percent (10%) of the payment sought by Contractor in an Application for Payment until such time as the submittal schedule is delivered to the Owner. |  | Not stated |  | The Contractor shall not be entitled to any such extension of time for Excusable Delays unless (a) the Contractor notifies the Owner in writing within five (5) days after the Contractor knows of, or in the exercise of reasonable diligence should have known of, the occurrence of an event giving rise to an alleged Excusable Delay; and (b) within thirty (30) days after providing such written notice, the Contractor shall submit the following additional information to the Owner and Architect: (i) a written statement of the nature and cause of the claim; (ii) a complete and detailed CPM Schedule (including fragnets) showing how the delay adversity impacts the critical path of the Project and the date(s) of Substantial Completion of the Work; and (iii) an itemized and substantiated statement of the time extension or dollar amount requested (for Owner Delays only) or, if sufficient information to do so is unavailable, then a reasonable estimate of the time extension or dollar amount (for Owner Delays only) supported by such documentation as the Owner may request. If the Contractor submits said reasonable estimate, the Contractor shall submit the itemized and substantiated statement of the time extension or dollar amount requested within fifteen (15) days after the reasonable estimate is delivered to the Owner and Architect. To the extent the Contractor cannot demonstrate to the reasonable satisfaction of the Owner that the Excusable Delay adversely impacts the critical path thereby requiring an extension of one or more of the dates of Substantial Completion, no extension of time shall be granted. | 5 |  | Not stated | Calendar | 9.8 | The term "Substantial Completion" of the Work shall mean when the Work is determined by the Owner to be complete in accordance with the Contract Documents, such that all interior and exterior construction, including without limitation, all components, systems, facilities, amenities, common areas, and portions of the Work, have been completed and is habitable, operational, and useable for the Owner's intended purposes (such that the units are fully leasable or saleable and the occupants of the units will have full use and enjoyment of all aspects and amenities), except for incidental corrective work, cleaning beyond the cleaning needed for Owner's intended use (which may remain for Final Completion), and minor commissioning and balancing work which may take place in conjunction with the Owner's set-up for operations activities for the Project. The Contractor acknowledges that the issuance of Use and Occupancy permits are a condition precedent to the Substantial Completion of the Work unless withheld by no fault of the Contractor; provided, however, that, for the purposes of First-tier Liquidated Damages, if all conditions have been met and the local City, County or Township authority is ready to issue Use and Occupancy permits and the Owner has not issued written approval to Contractor to obtain said permits, then the Contractor shall not be assessed First-tier Liquidated Damages for failure to obtain Use and Occupancy permits. The Contractor further acknowledges that (i) Owner is relying on the date of Substantial Completion established by Contractor to coordinate Owner's turnover and operations activities for the Project, and (ii) Owner may suffer substantial loss if the Contractor is unable to achieve Substantial Completion on or prior to the date of Substantial Completion established by the Contractor. Accordingly, at least ninety (90) days prior to the date on which Contractor shall achieve Substantial Completion of an assisted living community, or at least one hundred twenty (120) days prior to the date on which Contractor shall achieve Substantial Completion of a continuum community, Contractor shall complete, execute and deliver to Owner the Substantial Completion Date Certificate in the form attached to the Agreement as Exhibit M. When the Contractor considers the Work or a designated portion of the Work to be sufficiently complete in accordance with the above, the Contractor shall comply with the following procedures for acceptance of the Work or designated portion of the Work by the Owner. | 9.10 | Upon receipt of the Contractor's written notice that the Work is ready for final inspection and acceptance and upon receipt of a final Application for Payment, the Architect will promptly make such inspection and, when the Architect finds the Work acceptable under the Contract Documents and that all of the obligations of the Contractor under the Contract have been fully performed, the Architect will promptly issue a final Certificate for Payment stating that to the best of the Architect's knowledge, information and belief, and on the basis of the Architect's on-site visits and inspections. the Work has been completed in accordance with terms and conditions of the Contract Documents and that the entire balance found to be due the Contractor and noted in the final Certificate is due and payable. The Architect's final Certificate for Payment will constitute a further representation that conditions listed in Section 9. 10.2 as precedent to the Contractor's being entitled to final payment have been fulfilled. | Yes | Model Units - Turned over within 120 days of project substantial completion | 12.1.4 | 10% | 12.1.8 | When the Work is fifty percent (50%) complete, as certified by the Architect, Contractor may request that the Owner not retain any additional amounts from subsequent progress payments. The Contractor may also request, and the Owner will also reasonably consider, reducing retainage for subcontractors completing their work prior to that date on which fifty percent (50%) of the Work has been completed by Contractor. The Contractor must provide consent of surety, if applicable, prior to the Owner's consideration of the Contractor's request. Any decision to not withhold further retainage or to reduce retainage shall be at the sole discretion ofthe Owner. Upon Substantial Completion. such retainage shall be reduced to amount equal to 150% of the cost to complete any punch list items and any incomplete Work, and such amount shall be withheld until Final Payment. | No | Yes |  | If approved in writing, payments for stored materials offsite may be made at the owner and lenders discretion. | 30 days | 9.7 | If the Owner does not pay the Contractor within seven days after the date established in the Contract Documents the undisputed amounts due or awarded by binding dispute resolution, then the Contractor may, upon seven additional days' written notice to the Owner and Architect, stop the Work until payment of the undisputed amount owing has been received. Such cessation of Work shall be deemed to be an Excusable Delay under the provisions of Section 8.3 and the Contract Time and/or Contract Sum shall be adjusted to the extent permitted by Section 8.3. Notwithstanding the foregoing, in the event the unpaid amount owing to Contractor is less than 5% of the total amount of the approved advance, then Contractor shall not have the right to stop the Work unless such unpaid amount remains outstanding for forty-five (45) days after the date for payment established in the Contract Documents and then only upon seven additional days' written notice to the Owner and Architect. | 13 | 14 | Not stated | 7 | [5 empty] | 3.5 |  | Provide in electronic format only. | 9.10 | Neither final payment nor any remaining retained percentage shall become due until the Contractor submits to the Architect (l) an affidavit that payrolls, bills for materials and equipment, and other indebtedness connected with the Work for which the Owner or the Owner's property might be responsible or encumbered (less amounts withheld by' Owner) have been paid or otherwise satisfied, (2) a certificate evidencing that insurance required by the Contract Documents to remain in force after final payment is currently in effect and will not be canceled or allowed to expire until at least 30 days' prior written notice has been given to the Owner, (3) a written statement that the Contractor knows ofno substantial reason that the insurance will not be renewable to cover the period required by the Contract Documents, (4) consent of surety, if any, to final payment (5) other data establishing payment or satisfaction of obligations. such as receipts, releases and waivers ofliens, claims, security interests or encumbrances arising out ofthe Contt'act. to the extent and in such form as may be designated by the Owner or Lender; (6) one (l) full set of the Redline Record Drawings of the Work; (7) conditional and unconditional final lien waivers forall Subcontractors in the fbrms of Exhibits G-2 and G-4 of the Agreement and a final payment lien waiver from Contractor conditioned only upon receipt of payment in the form of Exhibit G-2 of the Agreement; (8) all manufacturers' warranties to be transf-erred to Owner (with evidence of transfer); (9) all operating and maintenance manuals; (10) any other deliverables required by the Contract Documents, and ( I I ) if required by the Owner or Lender, a final cerlification by the Contractor that all Work has been completed in accordance with the Contract Documents. Subject to the written approval of the Owner and Lender, if a Subcontractor refuses to furnish a release or waiver required by the Owner or Lender. the Contractor may furnish a bond satisfactory to the Owner and Lender to indemnify the Owner and Lender against such lien. If such lien remains unsatisfied after payments are made, the Contractor shall refund to the Owner all money that the Owner may be compelled to pay in discharging such lien, including all costs and reasonable attorneys' fees. |  | Concealed or Unknown Conditions. If the Contractor encounters conditions at the site that are (1) subsurface or otherwise concealed physical conditions that differ materially from those indicated in the Contract Documents or (2) unknown physical conditions of an unusual nature, that differ materially from those ordinarily found to exist and generally recognized as inherent in construction activities of the character provided for in the Contract Documents, the Contractor shall promptly provide notice, in writing, to the Owner and the Architect as soon as practicable before conditions are disturbed and in no event later than fourteen (14) days after first observance ofthe conditions. The Architect will promptly investigate such conditions and, where appropriate, will recommend an equitable adjustment in the Contract Sum or Contract Time, or both. If the Architect determines that the conditions at the site are not materially different from those indicated in the Contract Documents and that no change in the terms of the Contract is justified, the Architect shall promptly notify the Owner and Contractor in writing, stating the reasons. If either party disputes the Architect's determination or recommendation, that party may proceed as provided in Article 15. No adjustment shall be made for any condition encountered if notice is not given within fourteen (14) days after the Contractor first observes or discovers the unknown or concealed conditions. | 14 | Owner Reports dur with monthly draw Monthly Photo Report Submittal and RFI Log OAC Meeting Minutes Schedule Update | No |  | Yes | Yes | Non-Union | Yes | Exhibit A: Construction Schedule Exhibit B: Qualifications and Clarifications Exhibit C: Schedule of Values Exhibit D: Intentionally Omitted Exhibit E: Drawings and Specifications Exhibit F: Developer Agreements Exhibit G-l: Conditional Lien Waiver Form for Subcontractors and Contractor (Progress Payments) Exhibit G-2: Conditional Lien Waiver Form for Subcontractors and Contractor (Final Payment) Exhibit G-3: Unconditional Lien Waiver Form for Subcontractors (Progress Payments) Exhibit G-4: Unconditional Lien Waiver Form for Subcontractors (Final Payment) Exhibit H: White Glove Standards Exhibit I: Environmental / Geotechnical Reports Exhibit J: List of Entities for Insurance Purposes Exhibit K: Subcontractor Default Insurance Plan Exhibit L: Responsibility Matrix Exhibit M: Form of Contractor Notice of Substantial Completion Date Exhibit N: Reimbursable General Conditions Expenses Exhibit O: Form of Construction Change Directive Exhibit P: Warranty Process Standard Exhibit Q: Builders' Risk Requirements Exhibit R: Delegated Design Items | No |  | Not stated | IMC
5 | 11 |  | Custom Contract | Princeton Design Build Contract |  | Entitled to collect damages after 60-days - does not specify - negotiated after 60-days. | No | Yes | Can be negotiated after 60-days - no amount specified. |  | NA | IMC | 0.35% | TBD | NA | Yes | No | Yes | No |  | NA |  | Article 1 - Page 4 (a) The “Contract Documents” consist of the documents listed below in this paragraph, including all Modifications thereto, all of which form the “Contract” and are as fully a part of the Contract as if attached to this Agreement or repeated herein. A “Modification” to the Contract is: (1) a written amendment to the Contract signed by both parties; (2) a Change Order (as defined in and pursuant and subject to Part V of the Contract, General Terms & Conditions, Section H and its subparts) signed by both parties; or (3) a Disputed Change Order (as defined in and pursuant and subject to Part V of the Contract, General Terms & Conditions, Clause H5) issued by Princeton University. The Contract Documents are: 1) This Agreement. (Part I) • Attachment 1 – Princeton University’s Request for Proposal titled “Facilities and Athletics Operations Design Build Services”, in its entirety, and if not attached hereto deemed incorporated herein by reference as Attachment 1 (the “RFP”). • Attachment 2 – Design Builder’s proposal dated June 29, 2021, or portions thereof, only to the extent as attached as Attachment 2 (the “Proposal”). (86 pages) (2) Project Description. (Part II) (3) Preconstruction Services and Obligations. (Part III) (4) Design Obligations and Design Services. (Part IV) (5) General Terms & Conditions for Construction Contracts (v9.0 06-2020), as amended by the Design Build Rider. (Part V) (All references in the Agreement to the “General Terms & Conditions” and/or “Terms & Conditions” shall be deemed to refer to this document as amended by its the Design Build Rider whether or not so stated.) |  | IMC is design builder |  | Clause B9 - Page 166 (a) The Contractor may propose alternate equipment, materials, articles, or processes (“Substitutions”). Princeton University, in consultation with the Architect/Engineer, shall be the judge of the quality and suitability of proposed Substitutions. Princeton University reserves the right to reject the request for any reason in its sole discretion, and Princeton University’s decision not to approve a proposed Substitution shall not give rise to a Claim by Contractor for additional compensation. Approval by Princeton University shall not relieve the Contractor of its duty to use only equipment, materials, articles, or processes that conform to the Contract Documents in the Work. | Yes | No |  | NA |  | Yes | 3 |  | Yes | Yes | No |  | GMP Part VI, Paragraph g Savings Upon completion of the Work, the Design Builder shall provide to Princeton University a detailed and complete accounting of the Cost of the Work for the Project. Should the actual final Cost of the Work plus the Design Builder’s Fee be less than the GMP amount as adjusted pursuant to this Contract (“Savings”), the Savings shall accrue one hundred percent (100%) to Princeton University and zero percent (0%) to the Design Builder. Should, however, the actual final Cost of the Work plus the Design Builder’s Fee applicable thereto exceed the GMP amount as adjusted pursuant to this Contract, then, the excess amount shall be borne solely by the Design Builder. |  | Yes | Yes | GMP Part VI, paragraph f - Section 2 - Page 8 Subcontractor Buyout: Upon completion of 80% by count of the Subcontractor buyouts, Design Builder shall prepare and submit a “Subcontractor Buyout Report” for Princeton University’s review and approval that lists and summarizes all Subcontractor buyouts to date. For each Subcontract awarded, the report shall include a list of all trade line items included in the award and compare the total GMP amount for those line items to the actual award value for the Subcontract to calculate the “buyout variance” for each Subcontract and then tally these to determine if there is an overall net buyout “savings” or “overrun” at that point. If there are net buyout “savings” then that net amount shall be transferred into and treated as a part of the Construction Contingency. Should there be a net buyout “overrun” a transfer out of Construction Contingency may be made after consideration of other mitigating actions that may be available within the GMP. It is expressly understood that unused Allowances shall not for any purpose be transferred into the Construction Contingency and shall remain as a credit to Princeton University one hundred percent (100%) of such. | Yes | 6.2.ii - Attached as a supplemental document | 2024 |  | clause L4 - page 216 (a) The term “Cost of the Work” shall be defined as costs necessarily, reasonably and actually incurred by Contractor in connection with the proper performance of all of the Work and other obligations of the Contract and as hereinafter enumerated. Such costs shall be at rates not higher than the standard paid in the locality of the Work, except with the prior written consent of Princeton University, and shall include and be limited to only the following items in this Clause L4(a): has context menu. |  | GMP Part VI, paragraph f - Page 7 Construction Contingency. A “Construction Contingency” shall be included within the Guaranteed Maximum Price in the amount of $283,002 (as also identified the GMP Breakdown and Basis Documents) which shall be reserved to cover increased or added costs that are Cost of the Work resulting from circumstances that may not be completely predictable or foreseeable at the time that the GMP is established but that can reasonably be assumed to be included within the scope of Work for the Project and presumed to have been included in but were omitted from the GMP. Examples of circumstances that may give rise to the use of Construction Contingency include but are not limited to: (i) utility coordination by the Design Builder or a Subcontractor at any tier; (ii) purchasing, estimating, and scheduling difficulties (e.g., changes in local material or labor market conditions at time of bidding; or, items that were missed in the GMP but that are required expressly or by necessary implication by the Contract Documents for a complete Project; or, net Subcontractor buyout overruns that exceed the GMP for the trade line(s) involved as provided in subpart (2) to this paragraph (f)) below); (iii) detail refinement (i.e., minor items or material selections required to complete a detail that may have not been fully developed in the Design Documents or that were familiar to the Design Builder from its work on previous Princeton University Projects); and (iv) the re-procurement of a Subcontractor at any tier due to termination for any reason, excluding any re-procurement costs that would be covered by Subcontractor Default Insurance (SDI) and any deductibles to be paid in connection with any applicable SDI insurance, if SDI is included in this Contract, and any legal costs which are unallowable. The above list is meant to be illustrative and Princeton University, in its discretion, may determine that there are other circumstances that meet the general definition for use of Construction Contingency; however, the Construction Contingency is not intended to fund additional scope or to fund additional cost of allowances beyond the dollar values included in the GMP. Additionally, notwithstanding anything to the contrary herein, Design Builder shall not be allowed to receive payment of sums from the Construction Contingency or otherwise for costs/charges/sums/etc. relating to: (i) sums that are successfully recovered from a Subcontractor or other responsible entity (with the express understanding that Design Builder shall be required to take reasonable action to recover such sums without resort to litigation); (ii) sums for which Design Builder would have been indemnified or compensated by insurance (including SDI), if not for the failure of Design Builder to procure and maintain such insurance in accordance with the requirements of this Contract, or if not for the failure of Design Builder to comply with the requirements of any insurance carriers providing coverage for the Project, or if not for the failure of Design Builder to pursue all available claims against such carriers for coverage or recovery; (iii) deductibles of any kind (insurance, SDI, etc.); and (iv) any sums, costs, charges, etc. that exceed the available Construction Contingency set forth in the Guaranteed Maximum Price (as such amount may be adjusted only by the terms of this Contract). Notwithstanding the establishment of the Construction Contingency or any of the listed examples for its potential usage above or any other circumstances, the Design Builder’s use of any Construction Contingency funds and each individual transfer into or out of Construction Contingency shall be subject to advance review and written approval by Princeton University, which shall not be unreasonably withheld. If the Construction Contingency is exhausted, all costs and expenses that would qualify for reimbursement from the Construction Contingency shall be borne by Design | GMP Part VI, paragraph f-1 - Page 7 Contingency Transfers The Design Builder is responsible for initiating requests for, obtaining prior written approvals, managing, and reporting on transfers into and out of Construction Contingency. Prior to initiating any Construction Contingency transfer, the Design Builder shall submit a written request for approval to Princeton University. The request shall describe the need for the transfer and identify how the transfer will be accounted for within the GMP. Princeton University will consider the request to determine if the transfer should be made from Construction Contingency or by another means and will not unreasonably withhold or delay its approval or determination. Design Builder shall maintain a log of all Construction Contingency transfer requests and shall summarize and include this log with its monthly status reports. Should Design Builder dispute Princeton University’s determination with respect to transfer of usage of the Construction Contingency | Lump Sum | Paragraph d - Item 2 - page 36 Additionally, for GMP Contracts and Cost Plus Fixed Fee Contracts only, Contractor shall submit payrolls (e.g., time sheets) for all labor and other data supporting the Contractor’s right to payment for Subcontracts or materials in accordance with Generally Accepted Accounting Procedures (GAAP), and any other reasonable evidence required by Princeton University to demonstrate that cash disbursements already made by the Contractor on account of the Cost of the Work equal or exceed progress payments already received by the Contractor, less that portion of those payments attributable to the Contractor’s Fee. The Application for Payment shall comprise both (1) the Cost of the Work incurred during the preceding month for which the has context menu. | Yes | Section 2 - Item i - page 134 Attached as part of the GMP Breakdown and Basis Documents is Design Builder’s General Conditions Cost Itemization, which identifies each category of the Design Builder’s “General Conditions Cost” component of the Cost of the Work as agreed upon between Princeton University and Design Builder. Design Builder shall not be entitled to reimbursement for any categories of costs that are generally considered in the construction industry to be “general conditions” costs unless they are identified on the General Conditions Cost Itemization included as part of the GMP Breakdown and Basis Documents notwithstanding any other provision of the Contract Documents to the contrary that may otherwise allow for reimbursement of such or identifies such costs as a Cost of the Work, including, without limitation, Clause L4(a). | 15% capped across all subcontract tiers | 15% capped across all subcontract tiers | 1.75% after $50,000 | 0 | 0 - included in fee | Not specified - add at cost to fist CO for negotiation | 1% for GL and 1.2% for SDI | 0 |  | Page 183 (x) by unusually severe weather conditions that could not have been anticipated for Work during the time frame shown on the original Project Schedule; then, Contractor shall be entitled to an extension of the affected Schedule Milestones or the Required Substantial Completion Date for the delay to the critical path of the Work directly resulting therefrom as determined by Princeton University in its discretion subject to the following provisions and limitations and all other relevant terms and conditions of the Contract. | 5 | Reasonably anticipated for that time of year (ie NOAA) |  | Clause E1 page 179 of 227 TLDW |  | Clause L3, number 7 - page 215 Monthly cash flow and manpower reports that compare an approved baseline to actual and projected cash flows and manpower forecasts. Also, include an explanation of the cause for any variance between the actual/current projections and the baseline. |  | Section 1 - page 183 Time is expressly of the essence with respect to Contractor’s giving of notice of any Claim or potential Claim to Princeton University for an extension of the Contract Time for any Schedule Milestones or the Required Substantial Completion Date, and the timely furnishing of such notice along with the subsequent timely furnishing of the detailed Change Order Request information identified herein are express conditions precedent to Contractor’s ability to pursue any Claim or potential Claim for adjustment to the Contract Time, the Project Schedule or the Contract Price arising from any claimed delay so as to provide Princeton University an opportunity to remedy any breach or to take action to avoid or mitigate any cause regarding any delay to the performance of the Work or the Project. Within five (5) business days after Contractor knew or, reasonably should have known of any such delay, Contractor shall provide Princeton University written notice thereof in accordance with this Clause E5 and all other relevant provisions of the Contract. The initial notice hereunder must state: (1) the nature of the claimed excusable delay; the date, circumstances, and source of the claimed excusable delay; and an order of magnitude of the impact to the critical path of any Schedule Milestones or the Required Substantial Completion Date; (2) that the Contractor regards the claimed delay as an excusable delay under this Clause E5 and describe, in reasonably preliminary detail, all changes in the Contract to which the Contractor believes it is entitled; and (3) and any other information required of such notice by Clause J3(c). Within ten (10) business days after giving the initial Contractor notice in compliance with the preceding sentence, the Contractor shall submit a written Change Order Request for extension of the Contract Time on account of such delay for Princeton University’s review and potential approval. Contractor’s Change Order Request for extension of Contract Time shall be supported by documentation and other demonstrable proof necessary for Princeton University to determine the extent of and the liability for the claimed delay, which documentation shall include, without limitation: (i) a time impact analysis (TIA) or other information in form and substance acceptable to Princeton University if reasonably ascertainable, and if not reasonably ascertainable stating the basis why it is not reasonably ascertainable, and thereafter providing such TIA or other information within an additional fifteen (15) days or some other time as agreed to by Princeton University in its discretion; (ii) suggestion of strategies to Princeton University to mitigate the effect of any such delay including without limitation overtime, re-sequencing and other remedial methods as indicated in subparagraph (5) herein below; and (iii) if reimbursement for costs in addition to additional time are requested, a written explanation of the reasons therefor, together with back-up sufficient for Princeton University to verify actual costs incurred and projected costs consistent with the information required by Clause H2(2). If Contractor fails to timely provide Princeton University with written initial notice of the delay and the subsequent Change Order Request, both with full information required herein, then the Contractor shall have waived any Claim or right to any adjustment to the Contract Time, the Project Schedule, or the Contract Price arising from the claimed delay or any ability to pursue any remedies for the subject matter of the claimed delay in the Work or events or circumstances regarding the same. In case of a continuing cause of delay of a particular nature, Contractor shall be required to file only one initial notice with respect thereto prior to the termination of the condition caused by the delay, but shall otherwise comply with all requirements herein and elsewhere in the Contract, incl | See above |  | Page 182 CLAUSE E4 ACCELERATION OF THE WORK (a) Recovery Plan, Acceleration at Contractor’s Expense. In addition to other rights granted to Princeton University in the Contract, if Contractor fails to achieve any Schedule Milestone dates, or if any (Updated) Project Schedule indicates that any Schedule Milestone date or the Required Substantial Completion Date will not be achieved, or Princeton University determines that the performance of the Work relative to any Schedule Milestone dates or the Required Substantial Completion Date has not progressed or reached the level of completion required by the Contract Documents, and such delays are not subject to extension of Contract Time as set forth in Clause E5, then Princeton University may require that the Contractor develop, submit within ten (10) days of demand, and execute and perform under a time Recovery Plan as defined in Clause E6 (and which shall include but not be limited to more personnel, overtime and/or double shifts) at Contractor’s sole expense without any increase in the Contract Price or other compensation in order to expedite the progress of construction of the Work and assure completion of the Work in accordance with the remaining Schedule Milestone dates and the Required Substantial Completion Date to Princeton University’s satisfaction. In the event that Contractor disputes any determination by Princeton University that Contractor is obligated to accelerate the Work at Contractor’s expense, provided that Princeton University has issued a Disputed Change Order pursuant to the applicable Clauses of Section H hereof, Contractor shall proceed with such acceleration. (b) Acceleration at Princeton University’s Expense. Princeton University may request the Contractor to accelerate (including more personnel, overtime, and/or double shifts) the completion of the Work or a portion of the Work, at a time when the Contractor is not behind the Project Schedule in the performance of the Work. The Contractor agrees to accelerate the Work at Princeton University’s request, and notwithstanding anything in the Contract to the contrary, the Contractor shall be reimbursed only for the Contractor’s extra labor cost over the amount for regular time during the period of such acceleration, including additional fringe benefit costs, and insurance and taxes incurred by it (unless otherwise not reimbursable by some other provision of the Contract) with respect thereto and only those other actual costs of the Contractor directly related to the acceleration, which have been approved in advance by Princeton University in a written signed Change Order. Time tickets covering said overtime must be correlated to the accelerated/overtime schedule activities and submitted to Princeton University for checking and approval. No Fee, if Contractor otherwise receives a Fee on this Contract, nor additional overhead nor any profit is to be charged by or allowed to Contractor on account of acceleration or costs related thereto, nor shall Contractor be compensated for any lost efficiency or production alleged to have resulted from said overtime work, except as expressly agreed in advance by Princeton University in a written signed Change Order. (c) Princeton University may exercise the rights furnished to it under the Clause E4 as frequently as it deems necessary or favorable. (d) Any rights conferred on Princeton University pursuant to this Clause E4 or in any other portion of the Contract shall neither require Princeton University to exercise such rights for the benefit of the Contractor, nor shall they make Princeton University responsible in any way whatsoever for the Contractor’s obligation to complete the Work of the Project by the Schedule Milestone dates or the Required Substantial Completion Date. | Calendar | Clause E10 - page 186 of 227 | Accordance with the Contract Documents so that Princeton University may occupy, operate or use the Work, or designated portion, for the purpose for which it is intended, and the following have been completed: (1) Certificate of Occupancy. A Certificate of Occupancy (temporary, final or other) is in place that allows legal occupancy for its intended use by Princeton University. (2) Initial Punch List Completed. Except for those items on the consolidated list of final incomplete or uncorrected items included with the letter of Substantial Completion (“Final Punch List”), the Initial Punch List containing comments from, but not limited to, the Architect/Engineer, the Contractor, Princeton University and other consultants approved by Princeton University has been established, posted to the Capital Project Management System, completed, and accepted as complete by Princeton University. (3) Operational Building Systems. Systems are fully operational except for those identified on the list of incomplete or uncorrected items included with the letter of Substantial Completion. (4) Commissioning. Functional testing and certification is complete. Forms and documentation which record the certification and performance of building systems, utility systems and equipment are fully executed and posted to the Princeton Collaborative System. (5) Training. All training required by the Contract Documents is complete unless exempted by Princeton University. (6) As-Built Drawings that accurately depict the installed condition of all Work must be posted to the Capital Project Management System. Without limitation, As-Built Drawings shall include any Work that deviates from approved shop drawings and other submittals, as well as drawing schedules, as-built equipment, product data, etc. (7) Operation and Maintenance Manuals. Operation and maintenance manuals are complete, posted to the Capital Project Management System, and printed copies have been delivered to Princeton University. (8) Site and Landscaping Work. Work is complete except for items included on the punch list. (9) Warranties. Warranties are executed, accepted by Princeton University, and posted to the Capital Project Management System. (10) Project Card Access & Campus Security (CACS). Work is complete, fully operational and has been electronically accepted through the Princeton University ATP commissioning. Security systems and/or exterior CACS doors labels are installed. (11) Cleaning. The Project is clean. The interior and exterior of building (including windows) and site are free of dirt, dust, and debris. Princeton University has accepted the Project as clean and agrees to commence housekeeping activities on a mutually agreeable date (12) Contractor has complied with all other requirements in the Contract Documents that are a condition of Substantial Completion or are required by Princeton University to be completed or performed by Contractor as a condition of achieving Substantial Completion. | E12 - page 187 of 227 | Contractor shall achieve final completion of the Work of the entire Project for the purpose of determining the time of Final Payment (as defined in Clause I3) when: all certificates and permits necessary for permanent occupancy of the Project by Princeton University have been obtained; all Final Punchlist Work has been completed and approved by Princeton University in its discretion; all warranties, guaranties, affidavits and waivers of liens and releases have been delivered to Princeton University; all obligations set forth in Clause F2 (As-Builts) and F3 (Operating and Maintenance Manuals) have been achieved; and all other obligations of Contractor under the Contract have been fully performed as determined by Princeton University for the limited purpose of determining the time when Final Payment may be made. Notwithstanding anything to the contrary in this Clause E12 or the Contract Documents, Contractor shall be deemed to have reached final completion if it has achieved all other requirements for final completion but for the failure to secure a permanent certificate of occupancy for the Project if such failure is through no fault of the Contractor (or those for whom the Contractor is responsible) and outside the reasonable control of Contractor. By determining that Contractor has achieved final completion for the purpose of authorizing Final Payment, Princeton University does not waive any rights, Claims (as defined in Clause J3) and/or other claims, remedies, or defenses under the Contract in any manner whatsoever. The Final Payment will then be made in accordance with the payment provisions of this Contract. | Yes | Clause E1, Paragraph C - Schedule Milestones. The Contractor shall, in conjunction with Princeton University, create and thereafter maintain all schedule activities, including a group of milestone activities that shall be included in and tied to the Project Schedule (the “Schedule Milestones”). Contractor shall prepare its schedule to include, at a minimum, the following Schedule Milestones: Contractual Start (defined by the Effective Date of the Contract), Substantial Completion, Certificate of Occupancy, Princeton University’s “Move-In” process, Early Completion date (if one is proposed). Schedule Milestones shall also specify start date, end date, and duration for Submittals (as defined in Clause F1) and main building system elements of the Work, grouped by building area, and should include, in addition to the previous listed Schedule Milestones herein, as a minimum: Submittals, Site Mobilization, Demolition, Foundation/Excavation, Substructure, Superstructure (frame/bearing walls), Building Enclosure to water-tight condition, MEP Systems (including temporary systems, permanent power, and rough inspections), Conveying Devices, Interior Construction, Finishes, Final Inspections, Punch List, Move-In, Occupancy, and Contract Close Out.has context menu | Clause E-12, Clause I1 | 10% | Section I, Paragraph J4 - Page 200 of 227 | Reduction in Retainage for All Types of Contracts. (i) When the Contractor achieves Substantial Completion of all of the Work pursuant to all requirements of the Contract Documents, and the Final Punchlist and punch list completion schedule have been approved by Princeton University and the Architect/Engineer, then Princeton University shall pay all amounts due and remaining unpaid to Contractor, less whatever portion of the Retainage Princeton University deems appropriate, in its discretion, to continue to hold until final completion and Final Payment to protect any of its interests under the Contract, and less two hundred percent (200%) of the estimated cost to complete the Work on the punch list, as solely determined by Princeton University. (ii) Notwithstanding the preceding, when a Subcontractor has satisfactorily completed its Work (other than Work related to building-wide systems and finishes), Contractor may request payment for one hundred percent (100%) of the Subcontract amount, and Princeton University may consent, in its sole discretion, to release portions of the Retainage for Costs of the Work relating to any such early stage completed Subcontracts prior to Substantial Completion or final completion. As an additional condition to release of 100% of the Retainage of a Subcontractor (if so agreed by Princeton University in its sole discretion), the Subcontractor shall submit all Project close-out documents including, but not limited to, record documents/As-Built Drawings, operations and maintenance manuals, warranties and correction guarantees, a final lien waiver and release in the form required by this Contract, and if applicable, consent of surety to release of Retainage and Final Payment. In no event shall any interest be due and payable by Princeton University to Contractor, any Subcontractor or any other party on any of the sums retained by Princeton University pursuant to any of the terms or provisions of the Contract, including but not limited to Retainage. has context menu. | Yes | Yes |  | Section 1, paragraph f - Page 199 0f 227 (f) Applications for Payment may include the cost of material or equipment not incorporated in the Work, but delivered and suitably stored at the site or in an approved off-site location if: (1) Payment for material delivered to locations other than the Site is specifically authorized by this Contract. (2) The Contractor furnishes evidence satisfactory to Princeton University in its discretion that Contractor has acquired free and clear title to such material and that the material will be used to perform this Contract. (3) Storage and security procedures for the material have been approved by Princeton University, satisfactory evidence of insurance covering such material (with Princeton University named as an additional insured) has been provided to Princeton University, procedures for identifying and segregating the material (whether by serial numbers, tagging, photographs or other methods) have been approved by Princeton University, and the form and substance of bills of sale transferring title to Princeton University (if and when directed by Princeton University) have been approved by Princeton University (all such approvals in Princeton University’s discretion); (4) Contractor assumes all risk of loss to the material, remains liable for delivery to and installation at Site, and for warranting the material as required by the Contract; and, (5) All other documentation required by Princeton University has been provided by Contractor. | 30 days - Clause I, paragraph k | NA | NA | Section J, Clause 4 | Article 8 and GC Article E9 | 0 | 0 | [5 empty] | Clause F4, page 189 of 227 CLAUSE F4 WARRANTIES AND GUARANTEES (a) One-Year Warranty. In addition to the warranties and guarantees set forth elsewhere in this Contract, the Contractor upon request of Princeton University shall promptly correct all failures or defects in its scope of the Work for a period of one (1) year after the actual date of Substantial Completion, or the date of acceptance of Princeton University, whichever is later. Warranties and guarantees for equipment accepted prior to the date of Substantial Completion shall be in effect for one (1) year after the date of Substantial Completion. Should the Contractor fail to promptly correct any failure or defect, Princeton University may take whatever actions it deems necessary to remedy the failure or defect and the Contractor shall promptly reimburse Princeton University for any expenses or damages it incurs as a result of the Contractor’s failure to correct the failure or defect. (b) The warranties and guarantees set forth in this Clause F4 shall be in addition to all other warranties, express, implied, or statutory. Nothing in this Clause F4 shall be construed to establish a period of limitations with respect to Princeton University’s right to bring a Claim (as defined in Clause J3) and/or other claims for defective work under applicable law. In addition, the warranty obligations set forth in this Clause F4 shall survive termination of the Contract, and shall not limit, but shall be in addition to Princeton University’s other remedies for defective work. (c) The Contractor will collect all warranties and submit same to the Architect/Engineer for review and approval. The Contractor shall endeavor to obtain warranties from Subcontractors and suppliers that run directly for the benefit of Princeton University. (d) Warranty Inspection. The Contractor shall provide services in conjunction with an inspection, approximately 10 months from date of Substantial Completion. Visual inspection shall be made with Princeton University and the Architect/Engineer to determine whether correction of Work is required in accordance with provisions of the Contract Documents has context menu |  | Clause F2 - Page 188 of 227 CLAUSE F2 AS-BUILT DRAWINGS (a) During the construction phase, the Architect/Engineer may, when authorized by Princeton University, revise the issued-for-construction Drawings and issue revised Drawings to the Contractor. For plans, and other drawings wherever possible, these revisions will be made to the electronic files with paper copies issued to the Contractor. When field conditions that were not accommodated for during construction coordination cause the Contractor’s installation to deviate from the Drawings or the approved Shop Drawings, the Contractor is responsible to edit and maintain as-built drawings based on, and in the same native format as, the approved Shop Drawing files (i.e., .dwg, .RVT). The Contractor as-built drawings shall be maintained regularly, weekly at a minimum, to reflect the precise routing of installed Work. Failure by the Contractor to comply with the foregoing shall constitute cause for denial of applicable progress payment. (b) The Contractor shall maintain throughout construction, on-site and/or via CPMS, accurately updated as-built drawings. The Contractor will submit, as a prerequisite for obtaining Substantial Completion, the final as-built drawing files in electronic and paper copy. The Architect/Engineer will review these documents for accuracy prior to submission to Princeton University. (c) Failure on the part of the Contractor or a Subcontractor at any tier to fulfill its obligations under paragraph (b) above shall be just cause for Princeton University to withhold final payment from the Contractor until compliance with the complete requirements of this section is demonstrated to the satisfaction of Princeton University. | Clause E12 - Page 187 of 227 | CLAUSE E12 FINAL COMPLETION AND FINAL PAYMENT (a) Contractor shall achieve final completion of the Work of the entire Project for the purpose of determining the time of Final Payment (as defined in Clause I3) when: all certificates and permits necessary for permanent occupancy of the Project by Princeton University have been obtained; all Final Punchlist Work has been completed and approved by Princeton University in its discretion; all warranties, guaranties, affidavits and waivers of liens and releases have been delivered to Princeton University; all obligations set forth in Clause F2 (As-Builts) and F3 (Operating and Maintenance Manuals) have been achieved; and all other obligations of Contractor under the Contract have been fully performed as determined by Princeton University for the limited purpose of determining the time when Final Payment may be made. Notwithstanding anything to the contrary in this Clause E12 or the Contract Documents, Contractor shall be deemed to have reached final completion if it has achieved all other requirements for final completion but for the failure to secure a permanent certificate of occupancy for the Project if such failure is through no fault of the Contractor (or those for whom the Contractor is responsible) and outside the reasonable control of Contractor. By determining that Contractor has achieved final completion for the purpose of authorizing Final Payment, Princeton University does not waive any rights, Claims (as defined in Clause J3) and/or other claims, remedies, or defenses under the Contract in any manner whatsoever. The Final Payment will then be made in accordance with the payment provisions of this Contract. (b) Other than as specifically provided in this Contract, neither any progress payment nor Final Payment to the Contractor, nor partial or full utilization or occupancy of the Work for any purpose by Princeton University, nor any other act or omission by Princeton University shall be interpreted or construed as an acceptance of any Work which is not strictly in compliance with all Contract Documents. |  | Article 7, paragraph G and H, Clause 16 (g) Testing. Princeton University will provide geo-technical, structural, mechanical, chemical, air and water pollution tests for hazardous materials and other laboratory and environmental tests, inspections, and reports required by law. The Design Builder shall inform Princeton University of all surveys, investigations, inspections, or tests (collectively “Investigations”) which should be performed for the proper design and construction of the Project, but which are not within the scope of Design Builder’s Design Services or other Work under this Contract, and render advice as to when such Investigations should be performed to avoid any delay to the completion of the Project. The Design Builder shall assist Princeton University in preparing all information and instructions needed to enable Princeton University to solicit proposals for any such Investigations and to engage appropriate subconsultants to perform such Investigations. The Design Builder shall review the results of all Investigations as they apply to Design Builder’s design of the Project and take them into account appropriately in designing the Project. (h) Hazardous Materials. Princeton University will provide services relating to hazardous or toxic waste removal, including but not limited to, detection and abatement of all such hazards. CLAUSE B16 HAZARDOUS MATERIALS DISCOVERED ON THE SITE (a) In the event the Contractor encounters on the Site material reasonably believed to constitute an environmental hazard, including but not limited to asbestos, mold, soil contamination, underground storage tanks, construction debris (e.g., non-native soils), the Contractor shall immediately stop work in the affected area and report the conditions to Princeton University and the Architect/Engineer in writing. Princeton University will be responsible for testing, abatement and/or mitigation as required by current state and federal regulations. The Work in the affected area shall be resumed only after the Contractor has received written notice from Princeton University that the environmental hazard has been removed, abated, and/or resolved using the applicable current state and federal regulatory standards. (b) In the event the Contractor encounters lead-based paint in target housing (as defined by the Princeton University Office of Environmental Health and Safety) or child-occupied facilities that needs to be disturbed, the Contractor shall notify Princeton University and the Architect/Engineer in writing and comply with the requirements of 40 CFR Part 745, Part E, Environmental Protection Agency Renovation, Repair and Painting Rule. Certified Lead Renovator documentation for the Contractor and all affected Subcontractors shall be provided upon request by Princeton University. | no specific delay | CLAUSE L3 MONTHLY STATUS REPORTS (a) The Contractor shall prepare a monthly status report based on a template format provided by Princeton University that contains, without limitation to other requirements for same as may be provided elsewhere in the Contract, the following items: (1) An executive summary consisting of a clear and concise statement of the Contractor’s opinion of the state of the Project, a narrative of the project cost and schedule status, an outline of remedial action plans required by all team members to meet the project cost and schedule requirements and a narrative of the outstanding items of information or decisions that must be made to progress the Work. (2) For GMP Type Contracts: A construction cost report that shows the approved budget, costs committed and paid do date, the anticipated cost for each budget line item and the variance of each budgeted line item and total to the anticipated cost. (3) For CPFF Type Contracts: A construction cost report that shows the then-approved Target Price breakdown, costs committed and paid do date, the anticipated cost for each Target-Price line item and the variance of each budgeted line item and total to the anticipated cost. (4) A significant risks/major issues list with assigned responsibility and planned date for required resolution. (5) A summary of the commitments, anticipated items, and transfers against the Contractor’s Construction Contingency within the GMP budget. (6) A schedule report that compares the baseline schedule to the current version and an explanation of the variance between the schedules. Also include an action plan to recover any negative variance from the approved baseline, an explanation of how past productivity has influenced the updated logic and durations, and explanation(s) for the cause of any delays and the party responsible for the cost of the related recovery efforts. (7) Monthly cash flow and manpower reports that compare an approved baseline to actual and projected cash flows and manpower forecasts. Also, include an explanation of the cause for any variance between the actual/current projections and the baseline. (8) Progress photographs of the Project. (9) Project metrics as deemed important by the entire team such as the number of outstanding shop drawings and RFI’s, Architect/Engineer and Princeton University response time. Also, include a narrative of the metric data and its impact on the Project. Do not include the logs used to track this information. (10) A summary of major outstanding quality issues including schedules and remedies to correct the conditions. (11) A summary of the follow-up actions taken from the previous month’s reports and any outstanding issues that still require action and by which team members. (12) A summary of the posting of digital archiving documents to the Capital Project Management System including as-built drawings, record submittals, maintenance manuals, commissioning reports and warranty letters. | No |  | Yes | Yes | Prevailing Wage | No | NA | Yes |  | NA | IMC
6 | 15 | 2024-06-06 | Custom Contract | GMP | No | NA | Yes | Yes | $1,000/day - 0-2 weeks after contractual substantial completion date $2,500/day - after two weeks beyond contractual substantial completion date |  | 2.5 | Owner | NA | NA | NA | Yes | No | No | No |  | NA |  | Drawing list, Geotech Report, DD Outline Specs, RFI Response Log, Lighting Schedule, Light Fixture Cut Sheets |  | Contractor required to notify owner of errors, contractor responsible for cost associated with errors if owner is not notified and contractor should have known about error. |  | NA | No | No |  | NA |  | No | NA |  | No | No | Yes |  | Contingency shared savings 50/50 |  | No | No | Buyout Savings to be reallocated to contractor contingency | No | K | 2024 |  | Costs necessarily incurred by contractor per rates in exhibit K in proper performance of the work and actually paid by contractor |  | contractor may use but must provide monthly report including back up to substantiate proper use. | Use of contingency for general conditions must be reported and approved by owner prior to use. | Reimbursable | Full back-up required | Yes | Exhibit C | 10 | NA | 5 | 2.5 | .1 | cost submitted for IMC labor as required for the change | 1 | NA |  | NA | NA | NA |  | CPM schedule required, monthly updates required, milestone date changes via CO only |  | NA |  | Schedule delay must be processed via CO | NA |  | NA | Cal | 1 | (i) quantity, quality, and completion per the contract docs (ii) Arch has certified substantial completion (iii) owner occupancy does not include punch list completion | 1 | must be within 30 days of substantial completion, all work complete including punch list | No |  | NA | 10% until substantial completion | 10% until substantial completion | NA | No | No |  | NA | NA | NA | NA | 16 | 14 | 10 | 10 | [5 empty] | (a) new materials (b) installed in workmanlike manner (c) compliance with legal requirements (d) confirm with agreement and contract docs (e) free from defects |  | must be submitted upon substantial completion | NA | NA |  | reimbursable | NA | NA | No |  | Yes | Yes | Non-Union | Yes | Contract, terms and conditions, Exhibit A (SOW), C-303 (site plan), Qualifications and Clarifications | No |  | NA | Not mentioned in contract - owner carrying policy
7 | 9 | 2023-08-21 | A201 - Design Bid Build Standard | GMP | No | A201 Section 15.1.6 Both parties agree to waiver of consequential damages without limitation | Yes | Yes | A133 Section 2.3.1.3 Multiple terms Tiered LDs for different sections of the project and different timeframes. Reference |  | 2.5% all costs per rate sheet | Owner | NA, by Owner | $100k deductible | There is not a standalone exhibit. This is addressed in A201, 11.3.7 | Yes | No | No | No |  | None, not required |  | A1.33 1.1 The Contract Documents consist of this Agreement, Conditions of the Contract (General, Supplementary and other Conditions), Drawings, Specifications, Addenda issued prior to the execution of this Agreement, other documents listed in this Agreement, and Modifications issued after execution of this Agreement, all of which form the Contract and are as fully a part of the Contract as if attached to this Agreement or repeated herein. |  | A133 2.1.4 extent of responsibility If the Construction Manager recognizes that portions of the Drawings and Specifications are at variance with applicable laws, statutes, ordinances, codes, rules and regulations, the Construction Manager shall promptly notify the Architect and Owner in writing. Such notification of items of which Construction Manager becomes aware must take place before the Construction Manager or any of its Subcontractors undertakes the relevant work contained therein. The Construction Manager is not required to ascertain that the Drawings and Specifications are in accordance with applicable laws, statutes, ordinances, codes, rules and regulations, or lawful orders of public authorities, but the Construction Manager shall promptly report to the Architect and Owner any nonconformity discovered by or made known to the Construction Manager as a request for information in such form as the Architect may require. |  | A2.01 3.4.2 Except in the case of minor changes in the Work authorized by the Owner in accordance with Sections 3.12.8 or 7.4, the Contractor may make substitutions only with the consent of the Owner, after evaluation by the Architect and in accordance with a Change Order or Construction Change Directive. | No | No |  | None, not required |  | Yes | None, not required |  | Yes | Yes | Yes |  | None, all savings accrues to Owner via deduct change order at completion of project. |  | No | No | None, silent | No | Exhibit B | 2023 |  | A133 Article 6 Costs of the Work |  | A133 5.3.6 Construction Manager will be required to furnish documentation to the Owner evidencing expenditures charged to the contingency and the reasons therefore. Contingency may be used by the Construction Manager for Cost of the Work items for which Construction Manager is entitled to reimbursement under Article 6 below. All expenditures from the contingency shall be included in a current monthly Project cost reports to be submitted by the Construction Manager to the Owner, Owner’s Representative and Architect along with the monthly updated construction schedule. | A133 5.3.6 Construction Manager will be required to furnish documentation to the Owner evidencing expenditures charged to the contingency and the reasons therefore. Contingency may be used by the Construction Manager for Cost of the Work items for which Construction Manager is entitled to reimbursement under Article 6 below. All expenditures from the contingency shall be included in a current monthly Project cost reports to be submitted by the Construction Manager to the Owner, Owner’s Representative and Architect along with the monthly updated construction schedule. | Other | None stated in the agreement | No | Silent | 10% overhead and 5% profit | Silent | 2.75% | 2.5% | 0.1% | Silent | 1% | NA, no bond |  | A201 15.1.5.2 If adverse weather conditions are the basis for a Claim for additional time, such Claim shall be documented by data substantiating that weather conditions were abnormal for the period of time, could not have been reasonably anticipated and had an adverse effect on the scheduled construction. | A201 15.1.2 Claims by the Contractor must be initiated within 21 days after occurrence of the event giving rise to such Claim or within 21 days after the Contractor first recognizes the condition giving rise to the Claim, whichever is later. | Silent |  | A201 3.3.4.1 The Contractor has reviewed the completion dates and times set forth in the Contract Documents, agrees that such dates and times are reasonable and commits to achieve them. The Contract Sum includes costs associated with completion by those dates and times, including, but not limited to, costs associated with Contractor’s original plan and schedule that may include out-of-sequence work, come-back work, stand-by work, stacking of trades, coordination with the schedules and work of separate contractors, allowing sufficient time, work and storage areas, and site access for separate contractors to timely progress and complete their work, overtime, expediting and acceleration that may be required to complete the Work by those dates and times. In the event that the Owner requires Work to be performed out-of-sequence (from what is set forth in the original plan and schedule) and/or requires Contractor to coordinate the Work with the work performed by Owner’s other contractors, the Contractor will reasonably work with Owner to ensure the Work is performed as efficiently as possible (from a time and cost perspective) while accommodating such out-of-sequence Work and/or other contractors in accordance with industry standards, provided that Contractor shall have the right to make a Claim for any actual proven costs incurred by Contractor in connection therewith. |  | A133 2.3.2.7 The Construction Manager shall record the progress of the Project. On a monthly basis, or otherwise as agreed to by the Owner, the Construction Manager shall submit written progress reports to the Owner and Architect, showing percentages of completion and other information required by the Owner. The Construction Manager shall also keep, and make available to the Owner and Architect, a daily log containing a record for each day of weather, portions of the Work in progress, number of workers on site, identification of equipment on site, problems that might affect progress of the work, accidents, injuries, and other information required by the Owner. |  | This is a very broad question. Reference A133, 2.3.1.3 for full clause regarding schedule, LDs and delays. | A201 15.1.2 Claims by the Contractor must be initiated within 21 days after occurrence of the event giving rise to such Claim or within 21 days after the Contractor first recognizes the condition giving rise to the Claim, whichever is later. |  | A201 8.3.2 Where Contractor is entitled to an extension of the Contract Time pursuant to the terms of Section 8.3.1 above, Contractor is entitled to costs or expenses associated with acceleration of Work relating to such delays (where Owner requests such acceleration in writing) and out-of-sequence work (e.g., winter protection costs), as well as actual, documented out-of-pocket costs and expenses incurred by Contractor to the extent attributable solely to such extension of the Contract Time (without the addition or payment of any Contractor’s Fee or profit thereon). | A201 8.1.4 The term “day” as used in the Contract Documents shall mean calendar day unless otherwise specifically defined. | A133 2.3.1.3 | A133 2.3.1.3 Substantial Completion for each Scheduled Phase shall consist of the stage of construction in accordance with the Contract Documents for such phase such that the owner can legally occupy or utilize the area including, without limitation, the issuance of certificates of occupancy; provided however, that Construction Manager’s obligation to obtain any certificate of occupancy shall be deemed satisfied to the extent all Work required to be completed by Construction Manager to obtain such certificate of occupancy has been completed but such certificate of occupancy cannot be obtained solely because work to be completed by third parties beyond Contractor’s control, such as utility companies, inspectors of authorities having jurisdiction to grant certificates of occupancy, Owner’s separate contractors and vendors, has not been completed. | A201 9.10 | A201 9.10.2 Neither final payment nor any remaining retained percentage shall become due until the Contractor submits to the Architect (1) an affidavit that payrolls, bills for materials and equipment, and other indebtedness connected with the Work for which the Owner or the Owner’s property might be responsible or encumbered (less amounts withheld by Owner) have been paid or otherwise satisfied, (2) a certificate evidencing that insurance required by the Contract Documents to remain in force after final payment is currently in effect and will not be canceled or allowed to expire until at least 30 days’ prior written notice has been given to the Owner, (3) a written statement that the Contractor knows of no substantial reason that the insurance will not be renewable to cover the period required by the Contract Documents, (4) consent of surety, if any, to final payment; (5) a marked up set of drawings including all changes in the Work made during the construction process, and (6) other data establishing payment or satisfaction of obligations, such as receipts, releases and waivers of liens, claims, security interests or encumbrances arising out of the Contract, from Contractor, all Subcontractors and anyone else who could create or file a lien with respect to the Project Site under applicable law if not paid the full amount to which such entity is entitled in connection with the Work, to the extent and in such form as may be designated by the Owner. If a Subcontractor refuses to furnish a release or waiver required by the Owner, the Contractor may furnish a bond satisfactory to the Owner to indemnify the Owner against such lien. If such lien is filed or remains unsatisfied after payments are made, the Contractor shall indemnify and promptly pay to the Owner or any other person or entity all money that the Owner may be compelled to pay in discharging such lien, including all costs and reasonable attorneys’ fees. 9.10.3 As a condition precedent to final payment, the Contractor shall also submit to the Owner (a) original guarantees and warranties obtained by the Contractor with respect to the Work, properly indexed and placed in a loose-leaf binder, (b) complete installation, operation and maintenance manuals relating to equipment and materials used in the Work, including, without limitation, all manufacturer’s literature, properly indexed and placed in a loose-leaf binder, (c) all inspection reports, permits and certificates of occupancy and other licenses necessary for the occupancy of the Project, properly indexed and placed in a loose-leaf binder, (d) a certificate evidencing that al insurance required by the Contract Documents shall remain in full force and effect after final payment is made, and that such insurance will not be cancelled or terminated until at least thirty (30) days prior written notice has been given to the Owner and the Owner’s lender, if any, and (e) any and all other items required to be submitted by the Contractor pursuant to the Contract Documents. The requirements that must be satisfied for final payments as described in this Subparagraph 9.10.3 shall apply to final payment upon final completion of all of the Work and final payment which is to occur under this Contract prior thereto as a result of the termination of this Contract by either party in accordance herewith. Such payment shall be made under terms and conditions governing final payment, except that it shall not constitute a waiver of claims. | Yes | PhaseScheduled Phase Substantial Completion Date Common Areas / Leasing Office August 21, 2024 Apartments Phase 1B and Garage Phase 1A (Building B and Parking Garage)October 16, 2024 Retail Shell Phase 1C (Building A Retail)February 19, 2025 Apartments Phase 2 (Building C/D)March 25, 2025 Apartments Phase 3 (Building A)April 2, 2025 | A133 Article 7 | Retainage withheld hereunder shall be in the amount of ten percent (10%) until the Work is fifty percent (50%) complete. At the time that the Work is fifty percent (50%) complete, (i) Contractor shall have the right to submit an invoice for release of fifty percent (50%) of the retainage amounts then being held by Owner, and (ii) retainage withheld on all progress payments from and after the date on which the Work is fifty (50%) complete until Substantial Completion shall be five percent (5%). In addition one hundred percent (100%) payment (including retainage related thereto) shall be made on a line item basis within sixty (60) days of final completion of the following items as approved by the Owner’s lender: concrete, steel, masonry, elevators, windows, Prefab wall panels/trusses, waterproofing, roofing, Doors/Frames/Hardware, appliances, specialties, dumpsters, survey, and others as mutually agreed to by the parties. Owner agrees to use commercially reasonable efforts to secure lender’s approval of final payment for the aforementioned trade items. | A133 7.1.11 as noted above | Retainage withheld hereunder shall be in the amount of ten percent (10%) until the Work is fifty percent (50%) complete. At the time that the Work is fifty percent (50%) complete, (i) Contractor shall have the right to submit an invoice for release of fifty percent (50%) of the retainage amounts then being held by Owner, and (ii) retainage withheld on all progress payments from and after the date on which the Work is fifty (50%) complete until Substantial Completion shall be five percent (5%). In addition one hundred percent (100%) payment (including retainage related thereto) shall be made on a line item basis within sixty (60) days of final completion of the following items as approved by the Owner’s lender: concrete, steel, masonry, elevators, windows, Prefab wall panels/trusses, waterproofing, roofing, Doors/Frames/Hardware, appliances, specialties, dumpsters, survey, and others as mutually agreed to by the parties. Owner agrees to use commercially reasonable efforts to secure lender’s approval of final payment for the aforementioned trade items. | No | Yes |  | A133 6.5.6 An approved cost of the work: Costs of materials and equipment suitably stored off the site at a mutually acceptable location, subject to the Owner’s prior written approval. A201 9.3.2 Unless otherwise provided in the Contract Documents, unless agreed to in writing by Owner there shall be no payments made on account of materials and equipment delivered and suitably stored at the site for subsequent incorporation in the Work. Any stored materials and equipment for which payment is made shall be used within 30 days of placement at the site, and such items shall be organized, protected from the elements, grouped together and may be counted in a reasonable period of time and that they are not on-site for any unreasonable period of time. Miscellaneous items such as screws, clamps, nails, etc. shall not be acceptable as stored materials. If approved in advance in writing by the Owner, payment may similarly be made for materials and equipment suitably stored off the site at a location agreed upon in writing. Payment for materials and equipment stored on or off the site shall be conditioned upon compliance by the Contractor with procedures satisfactory to the Owner to establish the Owner’s title to such materials and equipment or otherwise protect the Owner’s interest, and shall include the costs of applicable insurance, storage and transportation to the site for such materials and equipment stored off the site. The passage of title to such materials and equipment to the Owner shall not relieve the Contractor from the reasonalbe responsibility for the care and protection of such materials and equipment, and it shall be the Contractor's reasonable responsibility for their safekeeping and usability at the time they are to be incorporated as part of the Work. It is agreed and understood that Owner shall carry Builder’s Risk insurance covering such stored materials. | 30 | 30 | A201 9.7 Subject to Sections 9.5.1 and 9.5.2 above, if the Architect does not issue a Certificate for Payment, through no fault of the Contractor, within twenty days after receipt of the Contractor’s Application for Payment, or if the Owner does not pay the Contractor within twenty days after the date established in the Contract Documents the amount certified by the Architect or awarded by binding dispute resolution, then the Contractor may, upon seven additional days’ written notice to the Owner and Architect, stop the Work until payment of the amount owing has been received. Provided the Contractor’s election to stop the Work was proper, the Contract Time shall be extended appropriately and the Contract Sum shall be increased by the amount of the Contractor’s reasonable costs incurred in connection with shut-down, delay and start-up, plus interest as provided for in the Contract Documents. Notwithstanding anything to the contrary, this Paragraph 9.7 shall not allow the Contractor to stop the Work to the extent that the Owner’s non-payment of the Contractor is as a result of a good faith dispute and the Owner has provided the Contractor with written notice of such good faith dispute. | A133 Article 9 | A133 Article 10 A201 Article 14 | Zero, silent | 7 | [5 empty] | A201 3.5 The Contractor warrants to the Owner and Architect that materials and equipment furnished under the Contract will be of good quality and new unless the Contract Documents require or permit otherwise. The Contractor further warrants that the Work will conform to the requirements of the Contract Documents and will be free from defects for a period of one (1) year after Final Payment is made, excluding latent defects not uncoverable in such period for which Contractor shall remain responsible thereafter, and other applicable warranties which expressly extend beyond such one (1) year period. Work, materials, or equipment not conforming to these requirements will be considered defective. The Contractor’s warranty excludes remedy for damage or defect caused by abuse, alterations to the Work not executed by the Contractor, improper or insufficient maintenance, improper operation, or normal wear and tear and normal usage. If required by the Architect, the Contractor shall furnish satisfactory evidence as to the kind and quality of materials and equipment. This remedy is in addition to, and not in limitation of, any other remedies Owner may have at law or in equity. § 3.5.1 The Contractor further agrees to furnish any manufacturer warranties required in accordance with the Contract Documents for the Work prior to final payment. All warranties shall be assignable by Contractor and Contractor agrees to take any actions necessary to assign such warranties to Owner. The Contractor shall forward guarantee and warranty registration cards to the manufacturers in the name of the Owner showing the date of acceptable Substantial Completion of the Work as the beginning date for guarantee and warranty periods. |  | A201 9.10.2 A condition of substantial completion = ; (5) a marked up set of drawings including all changes in the Work made during the construction process | A133 Article 7.2 | Numerous Reference A133, Article 7.2 |  | A201 3.7.4 Concealed or Unknown Conditions. If the Contractor encounters conditions at the site that are (1) subsurface or otherwise concealed physical conditions that differ materially from those indicated in the Contract Documents or (2) unknown physical conditions of an unusual nature, that differ materially from those ordinarily found to exist and generally recognized as inherent in construction activities of the character provided for in the Contract Documents, the Contractor shall promptly provide notice to the Owner and the Architect before conditions are disturbed and in no event later than 21 days after first observance of the conditions. The Architect will promptly investigate such conditions and, if the Architect determines that they differ materially and cause an increase or decrease in the Contractor’s cost of, or time required for, performance of any part of the Work, will recommend an equitable adjustment in the Contract Sum or Contract Time, or both. If the Architect determines that the conditions at the site are not materially different from those indicated in the Contract Documents and that no change in the terms of the Contract is justified, the Architect shall promptly notify the Owner and Contractor in writing, stating the reasons. If either party disputes the Architect’s determination or recommendation, that party may proceed as provided in Article 15. Notwithstanding anything to the contrary contained in this subparagraph 3.7.4, no adjustment in the Contract Sum or Contract Time shall be made to the extent an unknown or concealed condition was discoverable by a visual inspection of the Site. | 21 days | Monthly progress report - A201, 8.2.5 | Yes |  | No | Yes | Non-Union | No | A133 A201 Exh A GMP Report R2 dated 6/2/23 Exh B Reimbursable general conditions / personnel rates Exh C insurance certificate Numerous ancillary documents - reference the document list within the GMP report | No |  | None found | IMC responsible for the first $50k of the $100k deductible
8 | 5 | 2023-05-08 | A102 - GMP Cost Plus Fee | GMP Cost Plus Fee | No | NA | Yes | Yes | If Substantial Completion is not attained by 30 days after the Substantial Completion Date, Contractor shall pay Owner $3,500 per day for the first 30 days and $7,500 per day for each day thereafter past the Substantial Completion Date as liquidated damages for each day that Substantial Completion extends beyond the Substantial Completion Date. The liquidated damages will be capped at Contractor's Fee. | Consequential: A201 15.5.7. Liquidated: A102 5.1.6. | 2.5% | Owner | NA - Builders Risk by Owner | NA - Builders Risk by Owner | Not referenced in Contract. Exhibit F (Qualifications and Clarifications) notes that Builder's Risk Insurance to be provided by Owner. | Yes | No | Yes | No | A201 - 11 | NA | A201 - 1.1.1 | The Contract Documents consist of the Agreement between the Owner and Contractor, Conditions of the Contract (General, Supplementary and other Conditions), Drawings, Specifications, Addenda issued prior to execution of the Contract, other documents listed in the Agreement, and Modifications issued after execution of the Contract. | A201 - 3.2 | - The Contractor has visited the site, become generally familiar with local conditions under which the Work is to be performed, and correlated personal observations with requirements of the Contract Documents. This provision does not include subsurface conditions not visible to the Contractor and not shown on contract plans or Owner supplied borings. - Before starting each portion of the Work, the Contractor shall carefully study and compare the various Drawings and other Contract Documents relative to that portion of the Work, as well as the information furnished by the Owner pursuant to Section 2.3.4, shall take field measurements of any existing conditions related to that portion of the Work and shall observe any conditions at the site affecting it. - Any design errors or omissions noted by the Contractor during this review shall be reported promptly to the Architect and the Owner. - The Contractor shall give the Architect and Owner notice of any additional Drawings, Specifications or instructions required to define the Work in greater detail, or to permit the proper progress of the Work. | A201 - 3.4.2 | The Contractor may propose a substitution in a written request delivered to the Architect and the Owner setting forth a full explanation, reasons, adjustments, etc. | Yes | No | Separate agreement. Not referenced in Contract. | NA | A102 - 5.2.5.1 | Yes | Not referenced in Contract; however, Owner requested 3 bids. | Contractor shall identify Line Item Buyout Savings and Line Item Holds. | Yes | Yes | Yes | NA | NA | A102 - 10.3 | Yes | Yes | All buyout savings shall revert to the Owner upon Final Completion. | Yes | Exhibit D | 2023 | A102 - 7.1 | The Cost of the Work shall include only the items set forth in Article 7 pursuant to the rates set forth on Exhibit D. | A102 - 5.2.5 | The Contingency shall be an amount available to reimburse the Contractor for work not identified or quantified by the Contractor in its cost estimate, such as: (a) estimating and purchasing errors; (b) premium time to maintain the progress of the Work in accordance with the Project schedule due to an action or inaction by the Contractor or any Subcontractor (provided that the Contractor shall require Subcontractors to absorb in their base Subcontracts all premium time due to failure of the Subcontractor to properly man the Project or organize the Work); (c) unforeseen construction problems (except to the extent that, as a contractor experienced in the construction of projects similar to the Project, the Contractor should have foreseen such problems); (d) ordinary or seasonal weather conditions; and (e) Work identified or reasonably inferable from the Contract Documents, but not completely detailed in such documents. For purposes hereof, “reasonably inferable” shall mean reasonably necessary in order to complete any system or finished product. Notwithstanding anything to the contrary herein contained: (i) the Contingency may only be used for costs which are included in the Cost of the Work, as defined in Section 7.1, (ii) the Contingency may not be used for costs which are excluded from the Cost of the Work, as set forth in Section 8.1, (iii) INTENTIONALLY DELETED (iv) the Contingency may not be used to pay for costs due to unforeseen conditions (subject to other conditions of this Contract or the A201 General Conditions), overages in “Allowances” or Scope Changes, all of which shall be subject to Change Orders in accordance with Article 6, and (v) the Contractor shall be required to obtain the Owner’s written consent in advance of incurring costs during any calendar month in excess of twenty-five thousand dollars ($25,000.00) that the Contractor proposes be charged to the Contingency. The Owner agrees that it shall not unreasonably withhold or delay its consent to any request from the Contractor to properly use the Contingency pursuant to clauses (iii), (iv) or (v) above, recognizing that the Owner will collaborate with the Contractor in order to enable the Contractor to achieve the Project schedule. In order to enable the Owner to monitor the Contractor’s compliance with the provisions of this Section 5.2.5, the Contractor shall, commencing as of the execution and delivery of this Contract and continuing until Final Completion: (a) submit to the Owner a detailed monthly (or more frequently, if the Owner has a reasonable basis for requiring the same more frequently) Contingency log and projection for review by the Owner of all Contingency expenditures, and (b) prior to incurring any cost which may be charged to the Contingency in excess of twenty-five thousand dollars ($25,000.00), the Contractor shall submit a written request to the Owner for reimbursement of such cost, together with an explanation of the reason such cost is to be incurred. | See Item 53 above | Reimbursable | With each Application for Payment, the Contractor shall submit payrolls, petty cash accounts, receipted invoices or invoices with check vouchers attached, and any other evidence required by the Owner or Architect to demonstrate that payments already made by the Contractor on account of the Cost of the Work equal or exceed progress payments already received by the Contractor plus payrolls for the period covered by the present Application for Payment, less that portion of the progress payments attributable to the Contractor’s Fee. In addition to the other required items, each Application for Payment shall be accompanied by the following, all in form and substance satisfactory to Owner: .1 Duly executed Partial Waiver and Subordination of Mechanics’ and Materialmen’s Liens from the Contractor (in the form attached hereto as Exhibit G) and all such Subcontractors and such sub-Subcontractors and suppliers as the Owner may request (in the form attached hereto as Exhibit H) establishing payment or satisfaction of the payment of all amounts requested by the Contractor in previous Applications for Payment for which the Contractor has received payment; .2 Copies of applications for payment submitted by Subcontractors and copies of invoices from suppliers, substantiating the amounts the Contractor has requested for such Subcontractors and suppliers in the Contractor’s Application for Payment; .3 Copies of receipts, payrolls, invoices and other documentation to substantiate the amount the Contractor has requested in the Application for Payment for General Conditions Costs; and .4 Such other information, documentation and materials in such form and substance as the Owner or the Owners’ construction lender may reasonably require. | Yes | A102 - 7.1 | 15% | Not to exceed 20% (Subcontractor plus lower tiers) | 2.5% | 2.5% | 0.1% | Cost of the work on change orders for staffing is acceptable | 1% | P&P Bond is NA. SDI Markup is 1.2%. | A201 - 8.3.5 | No extension of time shall be granted on account of adverse weather conditions except as provided for in this paragraph. For purposes of this Agreement, "adverse weather" is defined as when because of weather conditions: (1) a state emergency or other declaration is made by the Governor of Pennsylvania directing non-essential workers to not report to work; or (2) Work cannot safely progress including, without limitation, winds that exceed the applicable manufacturer’s recommendation or local regulation for the safe use of a hoist, crane or other equipment (3) such weather conditions exist that are unordinary and that significantly hinder the performance of the Work. | 5 days | 0 | A201 - 3.10 | The Contractor shall submit for the Owner’s and Architect’s information a Contractor’s construction schedule for the Work, a final accepted version of which shall be attached to the A102 Agreement as Exhibit L (the “Construction Schedule”). Such schedule shall not exceed time limits current under the Contract Documents, shall be revised at appropriate intervals as required by the conditions of the Work and Project (but in no event less frequently than monthly), shall be related to the entire Project to the extent required by the Contract Documents, and shall provide for expeditious and practicable execution of the Work. The Construction Schedule and all updates thereto shall be in a detailed, precedence-style critical path method (CPM) format satisfactory to the Owner and the Architect and shall: (1) provide a graphic representation of material activities and events that will occur during performance of the Work; (2) indicate a proposed cash flow schedule based on anticipated monthly requisitions by the Contractor through final completion; (3) identify key dates for Owner-provided or Architect-provided information and materials; and (4) set forth dates that are critical in ensuring the timely and orderly completion of the Work in accordance with the requirements of the Contract Documents, including but not limited to each and all of the Substantial Completion Dates. | A201 - 3.9.5 | The Contractor shall keep, and make available to the Owner and Architect, a daily log containing a record for each day of weather, portions of the Work in progress, number of workers on site, identification of equipment on site, problems that might affect progress of the work, accidents, injuries, and other information required by the Owner. | A201 - 8.3 | If the Contractor is delayed at any time in the commencement or progress of the Work by any of the following: (1) an act or neglect of the Owner or Architect, of an employee of either, or of a Separate Contractor; (2) changes ordered in the Work by the Owner; (3) industry-wide, city-wide or other labor disputes affecting the construction industry generally or labor employed by a Separate Contractor or any of the Owner’s tenants (as opposed to affecting only the Contractor, any Subcontractor or the Project), fire, pandemic, epidemic, governmental order, unusual delay in deliveries, unavoidable casualties, adverse weather conditions subject to Section 8.3.5, or other causes beyond the Contractor’s control; (4) by delay authorized by the Owner pending mediation or (5) by other causes that the Contractor asserts, and the Owner determines, justify delay (each singly, an "Excusable Delay," and collectively, "Excusable Delays"), then the Milestone Dates and/or the Contract Time shall be extended by Construction Change Directive for such reasonable time as the Owner may determine, subject, however, to the following: .1 The Contractor acknowledges that no adjustments to any Milestone Date or the Contract Time shall be made unless the events described above have the effect of delaying completion of components of Work on any critical path indicated in the Construction Schedule. The Contractor shall be entitled to reallocate any time saved in the completion of any of the particular activities in the Construction Schedule to the time permitted for the completion of any other activities; provided, however that in no event shall any such reallocation result in any adjustments to any Milestone Date or the Contract Time and/or result in any extension of the time originally allocated in the Construction Schedule for the completion of components of Work on any critical path indicated in the Construction Schedule; and .2 The Contractor further acknowledges and agrees that adjustments to any Milestone Dates and the Contract Time shall be permitted in connection with any of the events described above only to the extent that the delays resulting therefrom (1) are not caused by, or could not have been avoided by the exercise of reasonable efforts of the Contractor, (2) could not be limited or avoided by the Contractor's timely notice to the Owner of the delay, (3) could not be mitigated by the exercise of reasonable efforts by the Contractor, and (4) have an impact of at least one (1) day; and, .3 Notwithstanding anything contained herein to the contrary, a permitted adjustment to any Milestone Date or the Contract Time shall not increase the Guaranteed Maximum Price unless specifically permitted in writing by Owner and as set forth in Article 8.3.6. | A201 - 15.1.6.1: 21 days (per Notice requirements in 15.1.3) | A201 - 3.10.5 | In the event (1) that the performance of any element of the Work on the critical path of construction has not progressed or reached the level of completion required by the Construction Schedule and (2) the progress of the Work is not brought back into compliance with the Construction Schedule on the date proposed by the Corrective Plan, or the Contractor otherwise fails to comply with the Corrective Plan, the Owner shall have the right to order the Contractor to take corrective measures to expedite the progress of the Work, including, without limitation, (a) working additional shifts or overtime, (b) supplying additional manpower, equipment and facilities and (c) other similar measures (hereinafter referred to collectively as "Extraordinary Measures"). Such Extraordinary Measures shall continue until the progress of the Work complies with the stage of completion required by the Contract Documents. The Owner's right to require Extraordinary Measures is solely for the purpose of ensuring the Contractor's compliance with the Construction Schedule: .1 The Contractor shall not be entitled to an adjustment in the Contract Sum in connection with Extraordinary Measures required by the Owner under or pursuant to Section 3.10.5; .2 The Owner may exercise the rights furnished the Owner under or pursuant to this Section 3.10.5 as frequently as reasonably necessary to ensure that the Contractor's performance of the Work complies with the elements of the Work on the critical path of construction set forth in the Construction Schedule. | A201 - 8.1.14: The term “day” as used in the Contract Documents shall mean calendar day unless otherwise specifically defined. | A102 - 4.3 and A201 - 9.8 | Substantial Completion of the entire Work shall be achieved when (a) the Work is sufficiently complete in accordance with the Contract Documents so the Owner can commence beneficial occupancy of the Project, (b) the Architect has issued a Certificate of Substantial Completion as provided in Section 9.8.4 below, (c) the Contractor has obtained all government approvals required or necessary to use or occupy the space where all or any of the Work was performed including, but not limited to, either a final, unconditional certificate of occupancy or a temporary certificate of occupancy that permits occupancy of the entire Project and is subject to conditions acceptable to the Owner, in the Owner’s reasonable judgment, and (d) the Owner, Contractor and Architect have agreed upon the punch-list. | A201 - 9.10 | Upon receipt of the Contractor’s or the Owner’s written notice that the Work is ready for final inspection and acceptance and upon receipt of a final Application for Payment, the Architect and Owner will promptly make such inspection. When the Owner finds the Work acceptable under the Contract Documents and the Contract fully performed, the Owner will promptly approve Contractor’s final Application for Payments. ________ Without limiting any other conditions to final payment, as set forth in the Contract Documents, to the extent consistent with the Contractor's Work under the Contract Documents, the Contractor shall be required to submit the following to the Owner and Architect, as conditions to the issuance of final payment: .1 final documents of similar nature to those required by the Contract Documents for any monthly payments hereunder; .2 all final permits, approvals (including, without limitation, the approval of the Owner's insurance company, if required) certificates (including, without limitation, certificates in respect of electrical systems and life safety systems) and authorizations for use and occupancy of the Project required by any authority having jurisdiction, other than any building permits, temporary and unconditioned permanent and full certificate of occupancy, the securing of which permit and certificate(s) is the responsibility of the Owner; .3 formally prepared "as built" drawings, records and related data including all field notes of all the Work in the form of reproducible drawings and in an electronic format acceptable to the Owner; .4 all operating and maintenance manuals, parts lists, the final version of the Project Directory, and repair source lists; .5 all guarantees and warranties to which the Owner is entitled hereunder; .6 satisfactory proof that all claims, including taxes, arising out of the Work (including any claims of Subcontractors or suppliers) have been released or bonded; .7 a certificate of insurance for product liability and completed operations, for the three-year period following final completion; .8 a final statement of accounting for all allowances in form satisfactory to the Owner and the Lender; .9 if required by the Owner or the Lender, other data establishing payment or satisfaction of all such obligations, and releases and final unconditional waivers of liens arising out of the Contract, to the extent and in form reasonably satisfactory to the Owner; .10 delivery of all spare parts required to be submitted pursuant to the Contract Documents; and .11 final releases from the Contractor in the form attached hereto as Exhibit I and all Subcontractors in the form attached hereto as Exhibit J, which include (1) a certification that payrolls, bills for materials and equipment, and other indebtedness connected with the Work for which the Owner or the Owner's property might be responsible or encumbered (less amounts withheld by Owner) have been paid or otherwise satisfied, or will be paid from proceeds of final payment, (2) a certification that the Contractor knows of no substantial reason that the insurance will not be renewable to cover the period required by the Contract Documents, and (3) a release of the Owner from the Contractor and each Subcontractor of and from any and all Claims whatsoever then existing or thereafter at any time arising under the Contract Documents, whether known or unknown, except for: (i) Claims of third parties which are not known by the Contractor at the time of execution of such release, (ii) Claims based upon the Claims of third parties which are known to the Contractor at the time of execution of such release and identified by the Contractor to the Owner in writing and (iii) unsettled Claims previously asserted by the Contractor against the Owner in accordance with all requirements of the Contract Documents. | No | NA | A102 - 12.1.8 | 10% | A102 - 12.1.8.2 | Upon fifty (50%) percent of Substantial Completion of the Work, Contractor may submit for a reduction of the retainage, so that the remaining retainage shall not be less than 5% of the Contract Sum. The retained amount shall be reduced to five (5%) percent on all future applications for payment. | No | No | A102 - 12.1.7.1.2 | The cost of materials and equipment delivered and suitably stored at the site for subsequent incorporation in the Work or, if approved in writing in advance by the Owner, materials suitably stored off the site at a location agreed upon in writing (less retainage in accordance with Section 12.1.8), but not to exceed, without the consent of the Owner, the portion of the Guaranteed Maximum Price allocated to such stored materials in the schedule of values | A102 - 12.1.3: Payment by the thirtieth (30th) day of the month following the Submission Date. | A201 - 9.7 | If the Owner does not pay the Contractor within seven days after the date established in the Contract Documents the amount approved by the Owner pursuant to Section 9.5.1, then the Contractor may, upon seven additional days’ notice to the Owner and Architect, stop the Work until payment of the amount owing has been received. The Contract Time shall be extended appropriately and the Contract Sum shall be increased by the amount of the Contractor’s reasonable costs of shutdown, delay and start-up, plus interest as provided for in the Contract Documents. | A102 - 13 and A201 - 15 | A102 - 14 and A201 - 14 | "at any time" | 7 days | 21 days | 60 days | Not referenced. See Item 103. | Not referenced. See Item 103. | A201 - 3.5 | Excerpts: 3.5.1 The Contractor warrants to the Owner and Architect that materials and equipment furnished under the Contract will be of good quality and new unless otherwise required or permitted by the Contract Documents, that the Work will be free from defects not inherent in the quality required or permitted and that the Work will conform to the requirements of the Contract Documents. 3.5.4 The Contractor shall procure and deliver to the Owner, no later than the date claimed by the Contractor as the date of Substantial Completion, all warranties required by the Contract Documents. 3.5.5 All warranties under this Section 3.5 shall commence as of the date of Substantial Completion of the Work. In no event shall the commencement of the use of building systems in connection with system testing and trial operations prior to the Substantial Completion of the entire Project be deemed to commence the term of any warranty, it being understood and agreed that any such warranty shall not commence until the Substantial Completion of the entire Project and that Contractor shall obtain, at no additional cost to Owner, any extended warranties required in connection therewith. 3.5.6 The Contractor agrees to assign to the Owner, at the time of Substantial Completion of the Work, all manufacturer's warranties required by the Contract Documents relating to materials and labor used in the Work and further agrees to perform the Work in such manner so as to preserve all such manufacturer's warranties. 3.5.7 In addition to any warranties described above or contained in the description of the Work attached hereto, Contractor agrees to guarantee all work and to replace without cost to Owner any and all defects due to imperfect workmanship or defects in materials and equipment and to pay for any damages resulting therefrom which shall manifest themselves within one (1) year from the date of Substantial Completion of the Work. | A201 - 9.10.2 | Excerpt: Contractor shall be required to submit the following to the Owner and Architect, as conditions to the issuance of final payment: .2 all final permits, approvals (including, without limitation, the approval of the Owner's insurance company, if required) certificates (including, without limitation, certificates in respect of electrical systems and life safety systems) and authorizations for use and occupancy of the Project required by any authority having jurisdiction, other than any building permits, temporary and unconditioned permanent and full certificate of occupancy, the securing of which permit and certificate(s) is the responsibility of the Owner; .3 formally prepared "as built" drawings, records and related data including all field notes of all the Work in the form of reproducible drawings and in an electronic format acceptable to the Owner; .4 all operating and maintenance manuals, parts lists, the final version of the Project Directory, and repair source lists; .5 all guarantees and warranties to which the Owner is entitled hereunder; .10 delivery of all spare parts required to be submitted pursuant to the Contract Documents; | A102 - 12.2 and A201 - 9.10 | 12.2.1 Final payment, constituting the entire unpaid balance of the Contract Sum, shall be made by the Owner to the Contractor when .1 the Contractor has fully performed the Contract, except for the Contractor’s responsibility to correct Work as provided in Article 12 of AIA Document A201–2017, and to satisfy other requirements, if any, which extend beyond final payment; .2 the Contractor has submitted a true and accurate final accounting for the Cost of the Work and final Application for Payment; and .3 a final Certificate for Payment has been issued by the Architect in accordance with Section 12.2.2.; .4 the Contractor has provided to Owner a complete set of required close-out documents, including all warranties, as-built drawings, CAD files, manuals for the operation and maintenance of all equipment, certificates of occupancy, permits, keys, attic stock and any other documentation necessary for the occupancy, operation, and maintenance of the Work and Project. | A201 - 3.7.4 | If conditions are encountered at the site that are (1) subsurface or otherwise concealed physical conditions that differ materially from those indicated in the Contract Documents or (2) unknown physical conditions of an unusual nature that differ materially from those ordinarily found to exist and generally recognized as inherent in construction activities of the character provided for in the Contract Documents, then notice by the observing party shall be given to the other party promptly before conditions are disturbed and in no event later than 14 days after first observance of the conditions. | 14 days | Monthly Report, including Cost Report and Schedule Progress Report |  | A201 - 9.9 | Yes | Yes | Non-Union | Yes | A102 A201 Exhibit A: Insurance and Bonding Requirements Exhibit A-1: Owner Indemnified Parties / Additional Insureds Exhibit B: Plans and Elevations, Concept Renderings, Basis of Design Report Exhibit C: Schedule of Values for GMP Exhibit D: Contractor's Rate Schedule Exhibit E: Contractor's Key Personnel Exhibit F: Contractor's Qualifications and Clarifications Exhibit G: Contractor's Partial Waiver and Subordination of Lien Exhibit H: Subcontractor's Partial Waiver and Subordination of Lien Exhibit I: Contractor's Final Release and Indemnification Agreement Exhibit J: Subcontractor's/Supplier's Final Release and Indemnification Agreement Exhibit K: RESERVED Exhibit L: Construction Schedule Exhibit M: Responsible Contractor Policy Exhibit N: Contractor's Rules and Regulations Exhibit O: Site Logistics Plan Exhibit P: Closeout Checklist | No | NA | NA
17 | 4 | 2022-07-18 | A102 - GMP Cost Plus Fee | A133-2019 Cost of work plus fee with a GMP | No | 15.1.7 Waiver of Claims for Consequential DamagesThe Contractor and Owner waive Claims against each other for consequential damages arising out of or relating to this Contract. This mutual waiver includes.1 damages incurred by the Owner for rental expenses, for losses of use, income, profit, financing, business and reputation, and for loss of management or employee productivity or of the services of such persons; and.2 damages incurred by the Contractor for principal office expenses including the compensation of personnel stationed there, for losses of financing, business and reputation, and for loss of profit, except anticipated profit arising directly from the Work This mutual waiver is applicable, without limitation, to all consequential damages due to either party’s termination in accordance with Article 14. Nothing contained in this Section 15.1.7 shall be deemed to preclude assessment of liquidated damages, when applicable, in accordance with the requirements of the Contract Documents. | Yes | Yes | Article 6.1.6: Insert the following: “Liquidated Damages. The Construction Manager agrees that it will pay to the Owner, as liquidated damages for delay, the sum of Five Hundred Dollars ($500.00) for each calendar day after the date scheduled for Substantial Completion of the Work until the Contractor achieves Substantial Completion of the Work. Such liquidated damages are agreed to by the Construction Manager, not as a penalty, but as a reasonable forecast of the substantial damages that the Owner will incur should Substantial Completion of the Work be delayed, and in view of the agreed difficulty of accurately specifying and ascertaining such delay damages. Such liquidated damages shall be Owner’s sole monetary remedy for delay in achieving Substantial Completion of the Work unless such liquidated damages are deemed to be an unenforceable penalty, in which case Owner shall be entitled to its actual delay damages. Imposition of such liquidated damages shall not relieve the Construction Manager from its obligation to achieve the date of Substantial Completion as required by the Contract Documents, nor limit the Owner’s non-monetary remedies, such as termination for default. Owner may deduct all such liquidated damages from the Construction Manager’s Applications for Payment or make take any such other action(s) Owner may deem necessary to enforce its entitlement to such liquidated damages against the Construction Manager and its Surety, if any.” | Article 15 | 2.5% | Owner | 1% | NA | Article 11.3.1 | Yes | No | No | No | B.3.4 | NA | Amendment A133, Section a.3.1.1 | Section 2.1 in Executed contract and IMC GMP Proposal Qualifications | Article 3.1 Precon Phase | The Construction Manager shall exercise reasonable care in performing its Preconstruction Services. The Owner and Architect shall be entitled to rely on, and shall not be responsible for, the accuracy, completeness, and timeliness of services and information furnished by the Construction Manager. The Construction Manager, however, does not warrant or guarantee estimates and schedules except as may be included as part of the Guaranteed Maximum Price. The Construction Manager is not required to ascertain that the Drawings and Specifications are in accordance with applicable laws, statutes, ordinances, codes, rules and regulations, or lawful orders of public authorities, but the Construction Manager shall promptly report to the Architect and Owner any nonconformity discovered by or made known to the Construction Manager as a request for information in such form as the Architect may require. | 3.12.8 | The Work shall be in accordance with approved submittals except that the Contractor shall not be relieved of responsibility for deviations from the requirements of the Contract Documents by the Architect’s approval of Shop Drawings, Product Data, Samples, or similar submittals, unless the Contractor has specifically notified the Architect of such deviation at the time of submittal and (1) the Architect has given written approval to the specific deviation as a minor change in the Work, or (2) a Change Order or Construction Change Directive has been issued authorizing the deviation. The Contractor shall not be relieved of responsibility for errors or omissions in Shop Drawings, Product Data, Samples, or similar submittals, by the Architect’s approval thereof. Except in the case of minor changes in the Work approved by the Architect in accordance with Section 3.12.8 or ordered by the Architect in accordance with Section 7.4, the Contractor may make substitutions only with the consent of the Owner, after evaluation by the Architect and in accordance with a Change Order or Construction Change Directive The Contract Sum is based upon the products, materials, systems and equipment required by the Contract Documents without exception. Where the Contract Documents list one or more manufacturers or brand name products, materials, systems and equipment as acceptable, the Contract Sum is, in each instance, based upon one of the listed manufacturers or brand name products, materials, systems and equipment, or, if the Contract Sum is based upon the substitution of an "or equal" manufacturer or product, material, system or equipment, the Contractor has in each instance either: (a) sought and received the Owner's written approval for the substitution; or (b) complied with all requirements for substitutions under the further provisions of these General Conditions. | Yes | No | 5.1.3 | Hourly billing rates for Preconstruction Phase services include all costs to be paid or incurred by the Construction Manager, as required by law or collective bargaining agreements, for taxes, insurance, contributions, assessments and benefits and, for personnel not covered by collective bargaining agreements, customary benefits such as sick leave, medical and health benefits, holidays, vacations and pensions, and shall remain unchanged unless the parties execute a Modification If the Preconstruction Phase services covered by this Agreement have not been completed within ( ) months of the date of this Agreement, through no fault of the Construction Manager, the Construction Manager’s compensation for Preconstruction Phase services shall be equitably adjusted. |  | No | 3 | Those portions of the Work that the Construction Manager does not customarily perform with the Construction Manager’s own personnel shall be performed under subcontracts or other appropriate agreements with the Construction Manager. The Owner may designate specific persons from whom, or entities from which, the Construction Manager shall obtain bids. The Construction Manager shall obtain bids from Subcontractors, and from suppliers of materials or equipment fabricated especially for the Work, who are qualified to perform that portion of the Work in accordance with the requirements of the Contract Documents. The Construction Manager shall deliver such bids to the Architect and Owner with an indication as to which bids the Construction Manager intends to accept. The Owner then has the right to review the Construction Manager’s list of proposed subcontractors and suppliers in consultation with the Architect and, subject to Section 9.1.1, to object to any subcontractor or supplier. Any advice of the Architect, or approval or objection by the Owner, shall not relieve the Construction Manager of its responsibility to perform the Work in accordance with the Contract Documents. The Construction Manager shall not be required to contract with anyone to whom the Construction Manager has reasonable objection. | Yes | Yes | No | Section 3.2.11 No shared savings. | By submitting a Guaranteed Maximum Price proposal, the Construction Manager agrees that all buy out savings, discounts earned, unused allowances and other savings shall be returned to the Owner without sharing with the Construction Manager, unless the Owner agrees otherwise in writing. Savings shall be identified no later than in the final Application for Payment | Section 3.2.11 No shared savings | Yes | No | By submitting a Guaranteed Maximum Price proposal, the Construction Manager agrees that all buy out savings, discounts earned, unused allowances and other savings shall be returned to the Owner without sharing with the Construction Manager, unless the Owner agrees otherwise in writing. Savings shall be identified no later than in the final Application for Payment | No | Exhibit D | 2022 | Article 7 | Article #7 in AIA CMP Agreement | 11.1.15 Include in each payment app, provide supporting documentation 11.1.5.3 | The Owner acknowledges that the Guaranteed Maximum Price Proposal may include an amount, not to exceed ___ percent (__%) of the Direct Cost of the Work (the "Contingency"), intended to cover refinement of details of design within the scope and standards of quality and quantities on which the Construction Budget was based; costs arising during construction that were not anticipated or not adequately anticipated by Construction Manager at the time of preparing the Guaranteed Maximum Price Proposal; errors in estimating; costs due to omission of construction related items from bid packages; cost overruns resulting from variations between bids and budgeted amounts; correcting minor defects in the Work if the party responsible therefor cannot be determined; and costs, exclusive of legal fees unless agreed to otherwise in writing at the Owner’s sole discretion, resulting from disputes with Subcontractors (hereinafter referred to as “Contingency Costs”). Construction Manager may charge sums (without any markup for Construction Manager’s Fee) to Contingency for the reasons set forth in this Paragraph, provided (1) the costs therefore are identified as reimbursable in Article 6 of this Agreement; (2) the Construction Manager has submitted detailed documentation supporting the amounts requested; and (3) the Construction Manager has received the prior written approval of the Owner for any item which may cost more than $5,000.00. The Construction Manager will track all items pending, obligated and spent against the Contingency and provide a written report to the Owner with each monthly Application for Payment and as otherwise requested by the Owner. When the Guaranteed Maximum Price is agreed upon by the parties the Contingency will be converted to a fixed dollar-sum and in no event shall the Contingency increase after the acceptance of the Guaranteed Maximum Price Proposal. Construction Manager shall bear all costs described in this Paragraph in excess of the Contingency.” | Approval with Monthly Pay App | Capped | With each Application for Payment, the Construction Manager shall submit payrolls, petty cash accounts, receipted invoices or invoices with check vouchers attached, and any other evidence required by the Owner or Architect to demonstrate that payments already made by the Construction Manager on account of the Cost of the Work equal or exceed progress payments already received by the Construction Manager, plus payrolls for the period covered by the present Application for Payment, less that portion of the progress payments attributable to the Construction Manager’s Fee | Yes | Article 10; Keep Accounting Records for Three Years | 10% for self performed | 5% | 5% | 2.5% | 0.1% | Defined Rates | 1% | NA | 8.3, 15.1.6.2 | If adverse weather conditions are the basis for a Claim for additional time, such Claim shall be documented by data substantiating that weather conditions were abnormal for the period of time, could not have been reasonably anticipated, and had an adverse effect on the scheduled construction. Claims by either the Owner or Contractor, where the condition giving rise to the Claim is first discovered prior to expiration of the period for correction of the Work set forth in Section 12.2.2, shall be initiated by notice to the other party and to the Initial Decision Maker with a copy sent to the Architect, if the Architect is not serving as the Initial Decision Maker. Claims by either party under this Section 15.1.3.1 shall be initiated within 21 days after occurrence of the event giving rise to such Claim or within 21 days after the claimant first recognizes the condition giving rise to the Claim, whichever is later | 21 | None | 3.1.4 | When Project requirements in Section 4.1.1 have been sufficiently identified, the Construction Manager shall prepare and periodically update a Project schedule for the Architect’s review and the Owner’s acceptance. The Construction Manager shall obtain the Architect’s approval for the portion of the Project schedule relating to the performance of the Architect’s services. The Project schedule shall coordinate and integrate the Construction Manager’s services, the Architect’s services, other Owner consultants’ services, and the Owner’s responsibilities; and identify items that affect the Project’s timely completion. The updated Project schedule shall include the following: submission of the Guaranteed Maximum Price proposal; components of the Work; times of commencement and completion required of each Subcontractor; ordering and delivery of products, including those that must be ordered in advance of construction; and the occupancy requirements of the Owner. | 3.3.2.4 | The Construction Manager shall keep, and make available to the Owner and Architect, a daily log containing a record for each day of weather, portions of the Work in progress, number of workers on site, identification of equipment on site, problems that might affect progress of the work, accidents, injuries, and other information required by the Owner | 8.3 | If the Contractor is delayed at any time in the commencement or progress of the Work by (1) an act or neglect of the Owner or Architect, of an employee of either, or of a Separate Contractor; (2) by changes ordered in the Work; (3) by labor disputes, fire, unusual delay in deliveries, unavoidable casualties, adverse weather conditions documented in accordance with Section 15.1.6.2, or other causes beyond the Contractor’s control; (4) by delay authorized by the Owner pending mediation and binding dispute resolution; or (5) by other causes that the Contractor asserts, and the Architect determines, justify delay, then the Contract Time shall be extended for such reasonable time as the Architect may determine. See article 15 for more information. 8.3.1.1 If the Contractor is delayed at any time in the commencement or progress of the Work by an act or neglect of the Owner or Architect, or of an employee of either, or of a separate contractor employed by the Owner; by changes ordered in the Work; by economic industry-wide strikes or labor disputes not caused by Contractor and which are beyond Contractor’s reasonable ability to avoid or mitigate; by order of government; by fire, unusual delay in deliveries not caused by the Contractor or its Subcontractors or suppliers; by unavoidable casualties; by delay authorized by the Owner pending formal mediation or litigation; or by other causes beyond the Contractor’s control, then the Contract Time shall be equitably adjusted by Change Order but only if, and only to the extent that, substantiation is provided by the Contractor in accordance with the further provisions of the Contract Documents that such delay: (a) will prevent the Contractor from achieving Substantial Completion within the Contract Time; and (b) is not, was not or would not have been caused or contributed to by any other event, transaction or occurrence for which the Contractor is not entitled to an extension in the Contract Time under the Contract Documents. The Contractor further acknowledges and agrees that adjustments in the Contract Time will be permitted for a delay only if, and only to the extent that, substantiation is provided by the Contractor in accordance with the further provisions of the Contract Documents that such delay: (i) is not caused, or could not have been anticipated, by the Contractor, (ii) could not be limited or avoided by the Contractor’s timely notice to the Owner of the delay, and (iii) is of a duration not less than one (1) day. The Contractor shall give written notice to the Owner and Architect within twenty-one (21) calendar days after the occurrence of any event which the Contractor claims will justify an equitable adjustment of the Contract Time under this Section. Delay by a Subcontractor, Sub-subcontractor or supplier shall not constitute an event for which the Contractor is entitled to an equitable adjustment of the Contract Time, nor shall it be presumed that a change in the Work shall entitle the Contractor to an extension of the Contract Time. f the Owner is delayed in the performance of its obligations at any time during the commencement or progress of the Work by economic industry-wide strikes or labor disputes not caused by Owner and which are beyond Owner’s reasonable ability to avoid or mitigate; by fire, unusual delay in deliveries not caused by the Owner or its separate contractors or suppliers; by order of government; by unavoidable casualties; or by other causes beyond the Owner’s control, then the time for the Owner’s performance of such obligations shall be equitably adjusted. | 21 | 8.3.1.1 | If the Contractor is delayed at any time in the commencement or progress of the Work by an act or neglect of the Owner or Architect, or of an employee of either, or of a separate contractor employed by the Owner; by changes ordered in the Work; by economic industry-wide strikes or labor disputes not caused by Contractor and which are beyond Contractor’s reasonable ability to avoid or mitigate; by order of government; by fire, unusual delay in deliveries not caused by the Contractor or its Subcontractors or suppliers; by unavoidable casualties; by delay authorized by the Owner pending formal mediation or litigation; or by other causes beyond the Contractor’s control, then the Contract Time shall be equitably adjusted by Change Order but only if, and only to the extent that, substantiation is provided by the Contractor in accordance with the further provisions of the Contract Documents that such delay: (a) will prevent the Contractor from achieving Substantial Completion within the Contract Time; and (b) is not, was not or would not have been caused or contributed to by any other event, transaction or occurrence for which the Contractor is not entitled to an extension in the Contract Time under the Contract Documents. The Contractor further acknowledges and agrees that adjustments in the Contract Time will be permitted for a delay only if, and only to the extent that, substantiation is provided by the Contractor in accordance with the further provisions of the Contract Documents that such delay: (i) is not caused, or could not have been anticipated, by the Contractor, (ii) could not be limited or avoided by the Contractor’s timely notice to the Owner of the delay, and (iii) is of a duration not less than one (1) day. The Contractor shall give written notice to the Owner and Architect within twenty-one (21) calendar days after the occurrence of any event which the Contractor claims will justify an equitable adjustment of the Contract Time under this Section. Delay by a Subcontractor, Sub-subcontractor or supplier shall not constitute an event for which the Contractor is entitled to an equitable adjustment of the Contract Time, nor shall it be presumed that a change in the Work shall entitle the Contractor to an extension of the Contract Time.” |  | A.2 | Phase 1 Aug 25th 2023 |  |  | Yes | Phase 1 Aug 25th 2023 | Article 11 | 10% | 11.1.8.3 | There shall be no reduction of retainage until final payment. Upon Substantial Completion, the retainage may, with the Owner’s prior written approval, be reduced to five per cent (5%) with respect to particular Subcontractors.” | No | No | No, 25% has been approved case-by-case by Jeannie | Unless otherwise provided in the Contract Documents, payments shall be made on account of materials and equipment delivered and suitably stored at the site for subsequent incorporation in the Work. If approved in advance by the Owner, payment may similarly be made for materials and equipment suitably stored off the site at a location agreed upon in writing. Payment for materials and equipment stored on or off the site shall be conditioned upon compliance by the Contractor with procedures satisfactory to the Owner to establish the Owner’s title to such materials and equipment or otherwise protect the Owner’s interest, and shall include the costs of applicable insurance, storage, and transportation to the site, for such materials and equipment stored off the site. Title to all material whether stored on or off the site shall be vested in Owner, as evidenced by documentation satisfactory in form and substance to Owner and he Owner’s Construction Lender, if any, including without limitation, recorded financing statements, UCC filings and UCC searches. With each Application for Payment, Contractor shall submit to the Owner a written list identifying each location where materials are stored off the Project site and the value of materials at each location. Contractor shall procure insurance satisfactory to Owner for materials stored off the Project site in an amount not less than the total value thereof. The consent of any surety shall be obtained to the extent required prior to payment for any materials stored off the Project site. Representatives of Owner and the Owner’s Construction Lender, if any, shall have the right to make inspections of the storage areas at any time. Such materials shall be (i) protected from diversion, destruction, theft and damage to the satisfaction of the Owner and the Owner’s Construction Lender, if any, (ii) specifically marked for use on the Project and (iii) segregated from other materials at the storage facility.” | One Month | 14.1.2 | If the Work is stopped for a period of ninety (90) consecutive days (and such stoppage was not contemplated in the construction schedule) through no breach of contract, act or fault of the Contractor or a Subcontractor, Sub-subcontractor or their agents or employees or any other persons or entities performing portions of the Work under direct or indirect contract with the Contractor, because of : (a) the issuance of an order of a court or other public authority having jurisdiction that requires all Work to be stopped; or (b) an act of government, such as a declaration of national emergency that requires all Work to be stopped, then, upon fifteen (15) days’ prior written notice to the Owner of its intention to do so, the Contractor may declare a constructive termination for convenience of its employment under the Contract and receive from the Owner the compensation to which the Contractor is entitled under Section 14.1.3. If the Architect or Owner, as applicable, has not issued a Certificate for Payment and has not notified the Contractor of the reason for withholding certification as provided in Section 9.4.1, or if the Owner, without legally sufficient justification or excuse, has not made payment on a Certificate for Payment within fourteen (14) days after the date on which such payment was due under the Contract Documents, then, upon thirty (30) days’ prior written notice to the Owner of its intention to do so, the Contractor may terminate its employment under the Contract and receive from the Owner the compensation to which the Contractor is entitled under Section 14.1.3. | 12 | 14 | 7 | 7 |  | 7 |  |  | 3.5.1 | The Contractor warrants to the Owner and Architect that materials and equipment furnished under the Contract will be of good quality and new unless the Contract Documents require or permit otherwise. The Contractor further warrants that the Work will conform to the requirements of the Contract Documents and will be free from defects. Work, materials, or equipment not conforming to these requirements, including unapproved substitutions, may be considered defective. The Contractor’s warranty does not cover damage or defect caused by abuse that is not the Contractor’s responsibility, alterations to the Work not executed by the Contractor, improper or insufficient maintenance, improper operation, or normal wear and tear and normal usage. If required by the Owner or Architect, the Contractor shall furnish satisfactory evidence as to the kind and quality of materials and equipment. In addition: See section 3.5.X in Supplement | 3.2 |  | 11.2 | For Progress Payments and Final Payment, if the Owner disputes any amounts stated in an invoice or Application for Payment, then the Owner must notify the Construction Manager in writing thirty (30) calendar days after the end of the billing Period during which the invoice or Application for Payment was submitted (“Notice of Dispute),” (unless prior written notice that the Owner disputes the Contractor’s right to payment has already been provided – for example, prior notice of deficient work). Such Notice of Dispute must be specific as to those items within the invoice or Application for Payment that are disputed. If such Notice of Dispute is not given within the specified period, such lack of notice shall not constitute acceptance of the work performed, but the invoice may be deemed to be accepted as submitted.” |  |  |  |  | Yes | Yes, upon architects inspection. | Yes | Yes | Prevailing Wage | Yes |  | No | B.2.5.1 | B.2.5.1 Cyber Security Insurance for loss to the Owner due to data security and privacy breach, including costs of investigating a potential or actual breach of confidential or private information.
18 | 19 | 2025-01-28 | Custom Contract | GMP plus fee with guaranteed max | No | N/A | Yes | Yes | 30 day grace period, $2,500 per day from day 31 to day 60. $4,500 per day from day 61 to day 90. $9,000 per day from day 91 on. |  | 2.5 | Owner | NA | Waiting on Policy Issuance | Waiting on owner's policy. Due 3/4/2025 | No | No | No | No |  | Struck Out |  | Article 1.1.1: the contract documents are numerated in the agreement between the owner and contractor (hereinafter the agreements) and consist of the agreement, conditions of the contract (genera, Supplementary, and other conditions), drawings, specification, addenda issued prior to the execution of the contract, other documents listed in the agreement, and modification issued after execution of the contract. The contract documents are complimentary, and what is called for by any one of shall be binding as if called for by any one of shall be binding as if called for by all. Anything that may be required or reasonably implied or inferred by the contract documents, or any one or more of them, shall be provided by the contractor as part of the work. A modification is (1) a written amendment to the contract signed by both parties, (2) a change order, (3) a construction change directive, or (4) a written order for a minor chance in the work issued by the architect unless specifically enumerated in the agreement, the contract documents do not include the advertisement or invitation to bid, instruction to bidders, sample forms, other information furnished by the owner in anticipation of receiving bids proposals, the contractor's bid or proposal, or portions of addenda relating to bidding or proposal requirements |  | 3.1.14.5: Review all design documents and construction documents and use best efforts to identify any failure to comply with any applicable laws, including but not limited to applicable building codes. Construction Manager shall advise owner and architect of any failure of the design documents or construction documents to comply with applicable laws that construction manager identifies. Construction manager shall not however by virtue of this review become liable for architects failure to design the project in accordance with all applicable laws. |  | 3.12.8: the work shall be in accordance with approved submittals except that the contractor shall not be relieved of responsibility for deviations from the requirements of the contract documents by the architects approval of shop drawings, product data, samples, or similar submittals unless the contractor has specifically notified the architect of such deviation at the time of submittal and (1) the architect has given written approval to the specific deviation as a minor change in the work, or (2) a change order or construction change directive has been issued authorizing the deviation. The contractor shall not be relieved of responsibility for errors or omission in shop drawings, product data, samples or similar submittals by the architects approval thereof. | Yes | Yes |  | 5.1.1: $100,000 subject to completion of preconstruction phase by January 9 2025 |  | No | NA |  | Yes | Yes | Yes |  | 6.1.7.1: savings are defined as the difference between (a) the cost of work plus the construction managers fee, and (b) the guaranteed maximum price, if the cost of the work plus the construction managers fee is less than the guaranteed maximum price. After first deducting from savings the full amount of any unused allowance items and any unused contingency fund items, owner shall pay construction manager a sum equal to 25% of the remaining savings, provided, however, that the total amount of savings paid to the construction manager shall not exceed the amount of construction managers fee as set forth in section 6.1.2 of the agreement. said payment shall be made to construction manager at the time of final payment. |  | Yes | Yes | 6.1.7.2: Construction manager shall include in the SOV a line item for buyout savings. As construction manager awards subcontracts for the work, any buyout savings shall be added to buyout savings, while any buyout overruns shall be deducted from buyout savings. Construction Manager shall include an accounting of the buyout savings in each monthly report. Buyout savings may not be transferred to any other line item without prior written approval of the owner, which approval shall be within owners reasonable discretion. Any buyout savings remaining at the end of the project shall be subject to shared savings pursuant to section 6.1.7.1 | Yes | Exhibit D | Custom |  | 7.1: The term cost of work shall mean costs necessarily incurred by the construction manager in the proper performance of the work. The cost of work shall include only the line items set forth in sections 7.1 through 7.7. |  | The GMP includes a Contingency fund for unknown and unforeseeable risks that are not included directly or by inference in the SOV and the costs of which are not directly or by inference precluded by and previsions of the Agreement. The construction manager shall not make any distribution in excess of $25,000 from the contingency fund without owner's prior written approval which shall not be unreasonably withheld. The contingency fund may be used for items such as unanticipated local market conditions, material price increases, labor and materials conditions, bidder and subcontractor defaults, construction managers estimating error, and interfacing omissions between and from the various work categories. The contingency fund may not be used to correct defective work or other negligent acts of the construction manager or its subcontractors or suppliers, except to the extent permissible under section 7.7.3. |  | Reimbursable | Not Specified | Yes | 7.1 thru 7.8. defines reimbursable costs, but not what costs are considered general conditions. | 10% Overhead, 5% Profit | Article 6.1.4 of A133: no more than 10% overhead and 5% profit. The total markup on any change order for subcontractors of all tiers shall not exceed 25% of the cost of the work of the change, exclusive of construction manager's fee. | 2.75 | 2.5 | 0.1 | as applicable per article 6.1.3.3 | 1% | NA |  | General delay provisions per 8.3.1. | 2 | 0 |  | Per Article 8. |  | 3.3.2.4: The construction manager shall keep and make available to the owner and Architect, a daily log containing a record for each day of weather, portions of the work in progress, number of workers on site, identification of equipment on site, problems that might affect progress of the work, accidents, injuries, and other information required by the owner. |  | General Delay provisions per 8.3.1 | 2 days |  | Per article 8.5 | 8.1.4: the term "day" as used in the contract documents shall mean calendar day unless otherwise specifically defined. | 3.4.3 | Construction manager shall achieve substantial completion of all work not later than November 28, 2025. | 3.4.4 | Final completion of all the work including without limitation, including any required certificates of occupancy or other similar governmental authorizations and all punchlist items, shall be achieved no later than 60 days following substantial completion. | Yes | Construction commencement: 3/25/2025 TI Work Commencement: 6/10/2025 Building Weather-tight: 8/7/2025 Final Completion: 1/2/2026 | Article 5.2 | 10% except on general conditions and insurance | 11.1.8.2 | At 75% complete and upon written request it can be reduced to 5% | No | No |  | 11.1.10: Except with the owners written approval, th construction manager shall not make advance payments to suppliers for materials or equipment which have not be delivered and suitably stored on site. | 30 | Article 9.7 A201 | Article 9.7 A201: If the architect does not issue a certificate for payment, through no fault of the contract within 7 days after receipt of the contractors application for payment, or if the owner does not pay the contractor within seven days after the date established in the contract documents, the amount certified by the architect or awarded by binding dispute resolution, then the contractor may upon 7 additional days notice to the owner and architect, stop the work until payment of the amount owing has been received. The contract time shall be extended appropriately and the contract sum shall be increased by the amount of the contractors reasonable costs of shutdown, delay and start-up, plus interest as provided for in the contract documents. | Article 15 of A201 | Article 14 of A201 | Immediately | 7 Days | [5 empty] | Per provisions in Article 3.5 in A201 |  | 3.11: The contractor shall maintain at the project site, the contract documents including change orders, construction change directives, and other modifications in good order and marked currently to indicate field changes and selections made during construction, and the approved shop drawings, product data, samples, and similar required submittals. These shall be in electronic form or paper copy, available to the architect and owner, and delivered to the architect for submittal to the owner upon completion of the work as a record of the work as constructed. | Article 9.10 of A201 | Upon receipt of the contractors notice that the work is ready for final inspection and acceptance and upon receipt of final application for payment, the architect will promptly make such inspection. When the architect finds the work acceptable under the contract documents and the contract fully performed, the architect will promptly issue a final certificate for payment stating that to the best of the architects knowledge, information, and belief, and on the basis of the architects on site visits and inspections, the work has been completed in accordance with the contract documents and that the entire balance found to be due the contractor and noted in the final certificate is due and payable. The architect's final certificate for payment will constitute a further representation that conditions listed in section 9.0.2 as precedent to the contractors being entitled to final payment have been fulfilled. |  | Per provisions in Article 10.3 of the general conditions. of A201 | Immediately | - Monthly Commitment Log - Monthly Contingency tracking log - Monthly Buyout Savings Tracking Log - Monthly construction schedule update - Submittal/RFI logs - GMP Accounting records including change order logs. - Site safety reports - Actual/Projected cash flow reports - Monthly progress photos | No |  | Yes | Yes | Non-Union | Yes | A. GMP Summary B. Project Team C. Contractor affidavit, release and waiver of liens on progress payment D. Reimbursable cost rates E. Document List F. Allowances Summary G. Qualifications and Clarifications H. Project Schedule I. Logistics Plan | No |  | None | Article 11.2.4 - IMC to pay up to $25,000 of the deductible.
9 | 7 | 2023-06-02 | A102 - GMP Cost Plus Fee | GMP (Cost + Fee) | No | N/A | Yes | Yes | One Thousand and 00/100 Dollars per day ($1,000.00/day) for days 1-15 days after the Contract Time Two Thousand and 00/100 Dollars per day ($2,000.00/day) for days 16-30 after the Contract Time; and Three Thousand and 00/100 Dollars per day ($3,000.00/day) beginning on the 31st day after the Contract Time and continuing until the Contractor achieves Substantial Completion. |  | 2.5 | Owner | N/A | 25000 | 11.3.1 | No | No | No | No |  | N/A |  | The Contract Documents consist of the Agreement between the Owner and Contractor (hereinafter the Agreement), Conditions of the Contract (General, Supplementary and other Conditions), Drawings, Specifications, Addenda issued prior to execution of the Contract, other documents listed in the Agreement, and Modifications issued after execution of the Contract. |  | Standard AIA A201 Terms, Article 3.2 |  | Standard AIA A201 Terms, Article 3.4.2, However the GMP clearly states that "We have assumed "or equal" and "non-proprietary" for all products" | Yes | No |  | $21,824.00 - Lump Sum |  | Yes | (3) if possible, if and when the value is over $150,000 |  | Yes | Yes | Yes |  | 50/50 |  | Yes | Yes | 12.1.5.3 Should there be savings from any particular line item once that line item buyout is complete, the Contractor shall reallocate the savings into a separate line item designated as “Buyout Savings”. This “Buyout Savings” shall function as the aggregate repository for use in balancing line items until buyout is complete. The Buyout Savings is to be exhausted prior to the Contractor requesting the Agent’s approval for any reallocation of the construction contingency. | No | D | 2023 |  | 7.1.1 The term Cost of the Work shall mean costs necessarily incurred by the Contractor in the proper performance of the Work. The Cost of the Work shall include only the items set forth in this Article 7 pursuant to the rates set forth on Exhibit D |  | The Contingency, when agreed upon by the Owner and the Contractor as set forth below and subject to the conditions in this Section 5.2.5, shall be an amount available to reimburse the Contractor for work not reasonably identified or reasonably quantified by the Contractor in its cost estimate, such as: (a) estimating and purchasing errors; (b) premium time to maintain the progress of the Work in accordance with the Project schedule due to an action or inaction by the Contractor or any Subcontractor (provided that the Contractor shall require Subcontractors to absorb in their base Subcontracts all premium time due to failure of the Subcontractor to properly man the Project or organize the Work); (c) unforeseen construction problems (except to the extent that, as a contractor experienced in the construction of projects similar to the Project, the Contractor should have foreseen such problems); (d) extrordinary or unusual seasonal weather conditions; and (e) Work not identified or reasonably inferable from the Contract Documents, but not completely detailed in such documents. | Anything over $10,000 in a month aggregate | Reimbursable | So far, monthly summary sheet | Yes | No definition | 15% | Not stated | 2.5% | 2.5% | 0.1% | As Incurred | 1% | 0% |  | 8.3.5 Notwithstanding anything to the contrary in any of the Contract Documents, the Contractor acknowledges and agrees that no extension of time shall be granted on account of adverse weather conditions except as provided for in this paragraph. For purposes of this Agreement, "adverse weather" is defined as when because of weather conditions: (1) a state emergency or other declaration is made by the Governor of Pennsylvania directing non-essential workers to not report to work; or (2) Work cannot safely progress including, without limitation, winds that exceed the applicable manufacturer’s recommendation or local regulation for the safe use of a hoist, crane or other equipment (3) such weather conditons exist that are are unordinary and that significantly hinder the performance of the Work. Written notice of adverse weather must be delivered by the Contractor to the Owner within five (5) days following such adverse weather and if the Contractor fails to so deliver written notice of adverse weather to the Owner by such time, the Contractor shall have no right to seek an extension of the Contract Time on account of such adverse weather. | 5 | 0 |  | Monthly schedule update with Monthly Report |  | None |  | 15.1.3.1 - 21 Days to make a claim from first "recognition". 8.3.2 Claims relating to time shall be made in accordance with Article 15 | See 61, 15 Days |  | No mention of acceleration, other than mention of the corrective plan in 3.10.4 | Calendar | 8.1.3 and 9.8 | 9.8.1 Substantial Completion of the entire Work shall be achieved when (a) the Work is sufficiently complete in accordance with the Contract Documents so the Owner can commence beneficial occupancy of the Project, (b) the Architect has issued a Certificate of Substantial Completion as provided in Section 9.8.4 below, (c) the Contractor has obtained all government approvals required or necessary to use or occupy the space where all or any of the Work was performed including, but not limited to, either a final, unconditional certificate of occupancy or a temporary certificate of occupancy that permits occupancy of the entire Project and is subject to conditions acceptable to the Owner, in the Owner’s reasonable judgment, and (d) the Owner, Contractor and Architect have agreed upon the punch-list. However, the completion of the Elevator is excluded. The County and Fire Marshall will NOT issue a TCO or CO. In addition, our qualifications states "Proposal assumes completion without Certificate of Occupancy" and "The current project design is not adequate to achieve Beneficial Occupancy and Certificate of Occupancy" and "TI contractor is responsible to provide Beneficial Occupancy and Certificate of Occupancy." | 4.3.4 | 4.3.4 Contractor agrees to and shall achieve full and final completion of the entire Work, including, but not limited to, punch list, clean up and demobilization (“Final Completion”), within a reasonable time after Substantial Completion, but in all events within Thirty (30) days thereafter (the “Final Completion Date”). | No | N/A | 9 | 10%, except for General Conditions, Fee and Insurances | 12.1.11 | 12.1.11 The Agent and the Contractor shall agree upon a mutually acceptable procedure for review and approval of payments to Subcontractors, and the percentage of retainage held on Subcontracts, and the Contractor shall execute subcontracts in accordance with those agreements. | Yes | Yes |  | Allowed with proper backup | First day of the next month. So July Payment, due September 1st. | 9.7 | 9.7 Failure of Payment If the Owner does not pay the Contractor within seven days after the date established in the Contract Documents the amount approved by the Owner pursuant to Section 9.5.1, then the Contractor may, upon seven additional days’ notice to the Owner and Architect, stop the Work until payment of the amount owing has been received. The Contract Time shall be extended appropriately and the Contract Sum shall be increased by the amount of the Contractor’s reasonable costs of shutdown, delay and start-up, plus interest as provided for in the Contract Documents. | 13 | 14 | 0 | 7 | [5 empty] | 1 year from Substantial Completion |  | Hard Copies at Final Completion | 9.10 | 9.10.1 Upon receipt of the Contractor’s or the Owner’s written notice that the Work is ready for final inspection and acceptance and upon receipt of a final Application for Payment, the Architect and Owner will promptly make such inspection. When the Owner finds the Work acceptable under the Contract Documents and the Contract fully performed, the Owner will promptly approve Contractor’s final Application for Payments |  | 3.7.4 If conditions are encountered at the site that are (1) subsurface or otherwise concealed physical conditions that differ materially from those indicated in the Contract Documents or (2) unknown physical conditions of an unusual nature that differ materially from those ordinarily found to exist and generally recognized as inherent in construction activities of the character provided for in the Contract Documents, then notice by the observing party shall be given to the other party promptly before conditions are disturbed and in no event later than 14 days after first observance of the conditions. | 14 | Allowance Status, Contingency Status, Schedule Update, Executive Summary | No |  | Yes | Yes | Non-Union | No | Seriously? Exhibit A – Insurance Requirements (2 pages) Exhibit A-1 – Owner’s Instructions (2 pages) Exhibit B – Scope of Work Documents - Drawings, Specifications and Addenda (4 pages) Exhibit C Schedule of Values, Scope of Work, Qualifications and Clarifications (10 pages) Exhibit D – Contractor’s Rate Schedule (3 pages) Exhibit E – Contractor’s Key Personnel (1 page) Exhibit F – Closeout Document Requirements (2 pages) Exhibit G – Contractor’s Partial Waiver and Subordination of Lien (1 page) Exhibit H – Subcontractor Partial Waiver and Subordination of Lien (1 page) Exhibit I – Contractor’s Final Release and Indemnification Agreement (1 page) Exhibit J – Subcontractor’s/Supplier’s Final Release and Indemnification Agreement (1 page) Exhibit K – INTENTIONALLY OMMITTED Exhibit L – Construction Schedule (4 pages) Exhibit L-1 – Logistics Plan (1 page) | No |  | Silent, but 12.1.1 has our standard language about changing payment information. | Owner
10 | 14 | 2023-02-28 | Custom Contract | GMP (Guaranteed Maximum Price) [1.1] | No | 8.5.1 Construction Manager acknowledges that its completion of the Work after the Required Completion Date may cause substantial consequential damages to Owner consisting of damages including but not limited to: 8.5.1.1 Additional carry costs, including interest and internal cost of funds; 8.5.1.2 Loss of rents; 8.5.1.3 Loss of prospective tenants of the building which is to be constructed pursuant to this Agreement; and 8.5.1.4 Claims for damages due to breaches of the leases because of failure to deliver the leased premises within the time periods stated in the leases. 14.16.1 Construction Manager and Owner waive Claims against each other for consequential damages arising out of or relating to this Agreement. This mutual waiver includes .1 damages incurred by the Owner for rental expenses, for losses of use, income, profit, financing, business and reputation, and for loss of management or employee productivity or of the services of such persons; and .2 damages incurred by the Construction Manager for principal office expenses including the compensation of personnel stationed there, for losses of financing, business and reputation, and for loss of profit except profit for completed Work. 14.16.2 This mutual waiver is applicable, without limitation, to all consequential damages due to either party’s termination in accordance with Article 13. Nothing contained in this Section 14.16 shall be deemed to preclude an award of liquidated damages, when applicable, in accordance with the requirements of the Contract Document | Yes | Yes | 8.5.2 In the event that Substantial Completion of the Work does not occur within forty-five (45) days after the Required Completion Date for the entire Project (the “Delay Damages Date”), Construction Manager shall pay to Owner as reimbursement for Owner’s additional carry costs an amount equal to Three Thousand Five Hundred Dollars ($3,500) per day for each day that Substantial Completion of the Work is delayed beyond the Delay Damages Date. Such damages (a) are a reasonable estimate of Owner’s additional carry costs, (b) shall not be considered a penalty, (c) shall be payable by Construction Manager to Owner from time to time upon demand and (d) are intended to be Owner’s exclusive remedy for delay. Without in any way limiting Owner’s ability to exercise all rights and remedies available to Owner, whether arising hereunder or at law or in equity, Owner shall have the right to offset any damages incurred by Owner as a result of Construction Manager completing the Work or a portion thereof after a Required Completion Date against any payment due from Owner to Construction Manager under this Agreement. 14.16.2 This mutual waiver is applicable, without limitation, to all consequential damages due to either party’s termination in accordance with Article 13. Nothing contained in this Section 14.16 shall be deemed to preclude an award of liquidated damages, when applicable, in accordance with the requirements of the Contract Documents |  | 2.5% [Exhibit J, IMC Rate Sheet] | Owner | n/a | 11.3.1 Owner shall purchase and maintain Builder’s Risk Property insurance upon the entire Work at the Site in an amount not less than the full insurable completed value thereof. This insurance will remain in force from the commencement of the Work until the date the completed Work is acceptable by Owner. This insurance shall cover the interest of Owner, and shall name Construction Manager as an additional insured. This insurance will insure against the perils of fire, extended coverage, theft, vandalism and malicious mischief and whatever other so-called “All Risk” perils Owner shall deem appropriate. This insurance shall apply only to the Work and materials delivered to and suitably stored at the Site. The risk of loss or damage to materials, supplies or other property away from the Site, in storage, while being fabricated, or in transit to the Site is that of Construction Manager and will not be covered by this insurance. This insurance will not include coverage for tools, machinery and equipment that are owned by, the responsibility of, or in the care, custody or control of Construction Manager, Subcontractors or Sub-Subcontractors. This insurance may include a deductible amount of not more than $5,000 or whatever mandatory higher deductibles are required by the insurance underwriter or are selected by Owner. Any loss or damage sustained to the Work prior to completion and acceptance by Owner that is not covered by this insurance due to the operation of the deductible clause shall be the responsibility of Owner and included in the “Cost of the Work”; provided, however, that Construction Manager shall be responsible for the deductible amount (up to a $5,000 deductible) in connection with losses or damage to materials stored on Site caused by theft or vandalism. Any claims for such theft or vandalism up to $5,000 shall not be recognized by Owner. | do not have a copy of the policy yet | Yes | No | Maybe | Maybe |  | 11.4.1 If requested by Owner in writing, Construction Manager shall obtain, and thereafter maintain at all times during the performance of the Work, performance and labor and material payment bonds, each in form and substance satisfactory to Owner and Owner’s lenders The penal sum for each such bond shall be in an amount equal to the Guaranteed Maximum Price. Such bonds shall be issued by an independent corporate surety of recognized financial standing with executive offices in the continental United States, satisfactory to Owner and Owner’s lenders. The cost of the premiums for such bonds has not been included in the Guaranteed Maximum Price; if Owner requires that such bonds be provided, the Guaranteed Maximum Price shall be increased to reflect an amount not more than 1.00% of the Guaranteed Maximum Price. In addition, upon request Owner shall confirm to Construction Manager’s bond issuer upon its request, the availability of funding for the Project. If Owner shall require such bonds, Construction Manager shall obtain and at all times thereafter during the performance of the Work, maintain a performance bond and a labor and material payment bond, each with a dual obligee rider naming Owner as obligee thereunder (and, if required by Owner, naming Owner’s lender(s) as an obligee(s) thereunder). The performance and payment bonds shall be in such forms as Owner shall reasonably require. In lieu of providing such bonds, Construction Manager may deliver to Owner an irrevocable letter of credit issued for Owner’s benefit by a bank satisfactory to Owner, in an amount not less than the Guaranteed Maximum Price and with a term of not less than twenty-four (24) months or such shorter period of time approved by Owner and Owner’s lender. Owner may draw upon such letter of credit upon Construction Manager’s Default hereunder and apply the proceeds to any damages incurred by Owner. |  | 1.1.1 THE CONTRACT DOCUMENTS The Contract Documents consist of this Agreement between Owner and Construction Manager (the “Agreement”), including the exhibits attached hereto (including the Construction Manager’s proposal attached as Exhibit “E” hereto), the Drawings and Specifications, addenda issued prior to execution of this Agreement, other documents listed in this Agreement and Modifications issued after execution of this Agreement. A Modification is (i) a written amendment to this Agreement signed by both parties, (ii) a Change Order, (iii) a Construction Change Directive, (iv) any Guaranteed Maximum Price Amendment (as defined below), or (v) a written order for a minor change in the Work issued by Owner or Developer (hereinafter defined) pursuant to Section 7.4. Unless specifically enumerated in this Agreement, the Contract Documents do not include other documents such as bidding requirements (advertisement or invitation to bid, Instructions to Bidders, sample forms, Construction Manager’s bid or portions of addenda relating to bidding requirements). |  | 3.5.1 Construction Manager shall carefully study and compare the Contract Documents with each other and with information furnished by Owner or Architect pursuant to Subsection 2.2.1 and shall at once report to Owner and Architect errors, inconsistencies or omissions discovered or any variances from applicable laws, statutes, ordinances, building codes, rules, regulations or any lawful orders of any governmental body, or any public or quasi-public authority. If Construction Manager performs any construction activity knowing it involves a recognized error, inconsistency or omission in the Contract Documents without such notice to Architect, Construction Manager shall assume appropriate responsibility for such performance and shall bear an appropriate amount of the attributable costs for correction. |  | 3.15.8 Construction Manager shall not be relieved of responsibility for deviations from requirements of the Contract Documents by Architect’s approval of Shop Drawings, Product Data, Samples or similar submittals unless Construction Manager has specifically informed Architect in writing of such deviation at the time of submittal and Architect has given written approval to the specific deviation. Construction Manager shall not be relieved of responsibility for errors or omissions in Shop Drawings, Product Data, Samples or similar submittals by Architect’s approval thereof. | Yes | No |  | All precon costs since last submitted/approved invoice to be carried to production budget as agreed. 9.1.1 For the Construction Manager’s Preconstruction Phase Services as described in Article 3 of this Agreement, Owner shall pay Construction Manager on a time and materials basis including permitted reimbursable costs (the “Preconstruction Monthly Amount”). The Preconstruction Monthly Amount shall include the salaries noted on Exhibit “J” attached hereto of the Construction Manager’s personnel providing Preconstruction Phase Services on the Project and the Construction Manager’s costs for the mandatory and customary contributions and benefits related thereto, such as employment taxes and other statutory employee benefits, insurance, sick leave, holidays, vacations, employee retirement plans and similar contributions. 9.1.2 If the commencement of the Project is abandoned prior to the execution of a Guaranteed Maximum Price Amendment, the Preconstruction Services shall be terminated and the Construction Manager shall be entitled to receive a monthly fee of Ten Thousand Dollars ($10,000.00) for each month that Construction Manager performs Preconstruction Services (the “Preconstruction Fee”). If applicable, the Preconstruction Fee shall be paid thirty (30) days after termination of the Preconstruction Services. In the event that Construction Manager provides no services for a month, the Preconstruction Fee shall not accrue. The Preconstruction Phase costs shall accrue during the Preconstruction Phase but shall be paid at the earlier to occur of (i) the first Application for Payment during the Construction Phase or (ii) thirty (30) days after Owner delays the Project for three (3) months from anticipated commencement of September 2022. 9.1.3 In the event Construction Manager continues to perform Preconstruction Phase Services during the Construction Phase, Owner shall pay Construction Manager for such Preconstruction Phase Services in accordance with Subsection 9.1.1 above and the cost of such Preconstruction Phase Services shall not be included in the Cost of the Work |  | Yes | 5.2.1 Unless otherwise stated in the Contract Documents or the bidding requirements, Construction Manager, as soon as practicable after the execution of this Agreement, shall furnish in writing to Owner through Architect the names of persons or entities (including those who are to furnish materials or equipment fabricated to a special design) proposed for each principal portion of the Work. Owner will promptly reply to Construction Manager in writing stating whether or not Owner or Architect, after due investigation, has reasonable objection to any such proposed person or entity. Construction Manager shall request bids from Subcontractors and/or materialmen and shall review such bids with Owner. Prior to entering into any Subcontract or purchase order, Construction Manager shall deliver to Owner copies of all requests for bids sent to prospective Subcontractors, all bids submitted to Construction Manager and a spreadsheet analysis setting forth the reasons for recommending acceptance of a bid. Owner will then determine, with the advice of Construction Manager, which bids will be accepted. The prior written approval of Owner shall be required for all subcontracts and purchase orders in excess of $25,000 and for all change orders issued with respect to such subcontracts and purchase orders. All forms of agreement with Subcontractors shall be approved by Owner prior to the execution of such agreements by Construction Manager and Subcontractor. Such approved forms of agreement shall become part of the Contract Documents. |  | Yes | No | No |  | 9.2.1.3 Upon completion of the Work, an accounting will be made to Owner of the Cost of the Work, and should the actual final cost, as adjusted pursuant to this Agreement, including Construction Manager’s Fee, be less than the Guaranteed Maximum Price, one hundred percent (100%) of the savings shall accrue to Owner. 9.2.1.4 .....If, at the completion of the Work any sums remain in the Contingency, such sums shall not constitute “savings” and, accordingly, Construction Manager shall not be entitled to share in any portion thereof. |  | Yes | No | 9.2.1 Owner agrees to reimburse Construction Manager for the Cost of the Work pursuant to this Article 9. In full consideration of the full and complete performance of the Work and all other Construction Phase obligations of Construction Manager hereunder, Owner shall pay to Construction Manager a sum of money equal to the “Contract Sum”. The Contract Sum is the total of (i) the Cost of the Work, as hereinafter defined, and (ii) Construction Manager’s Fee, as hereinafter defined, subject to adjustment as provided in this Agreement. The Contract Sum shall not exceed a “Guaranteed Maximum Price” as hereinafter established pursuant to the terms of this Section. Once so established, the Guaranteed Maximum Price shall not be adjusted except as expressly provided in this Agreement. Owner and Construction Manager hereby agree the Guaranteed Maximum Price will be established when the Drawings and Specifications are further developed, and at such time, Owner and Construction Manager shall execute one or more amendments to this Agreement to confirm the actual Guaranteed Maximum Price for the Project (each, a “Guaranteed Maximum Price Amendment”). Once the actual Guaranteed Maximum Price is established for all or a portion of the Project, a line item breakdown of the Guaranteed Maximum Price for such scope of Work shall be attached hereto as Exhibit “H”. Construction Manager may reallocate proven savings in one line item to overages in another, subject to Owner’s prior approval, which shall not be unreasonably withheld, by Change Order modifying Exhibit “H”. Construction Manager must notify Owner in a monthly budget report of all proposed reallocations it being understood that Owner reserves the right to disapprove any and all reallocations for expenditures that would be considered unreasonably excessive for General Conditions or Work performed directly by Construction Manager and not delegated to Subcontractors. “Construction M’s Fee” is to be an amount equal to two and three quarters percent (2.75%) of the Cost of the Work excluding the amount allocated for General Conditions. Owner and Construction Manager hereby acknowledge and agree that based upon the proposed Project budget as of the date hereof, the General Conditions costs, which are defined as those categories of cost listed on Exhibit “I” attached hereto (the “General Conditions”), the estimated amount allocated for General Conditions shall be established by Owner and Construction Manager and set forth in a Guaranteed Maximum Price Amendment. The estimated amount of the General Conditions set in a Guaranteed Maximum Price Amendment shall be subject to adjustment upon the mutual agreement of Owner (not to be unreasonably withheld) and Construction Manager as the Project progresses. | Yes | J | 2023 - Updated to 2024 in Amendment 01 |  | 9.2.3 The term “Cost of the Work” shall mean costs necessarily incurred in the proper performance of the Work and paid by Construction Manager. Such costs shall be at rates per Exhibit “J” and not higher than the standard paid in the locality of the Work, except with the prior written consent of Owner, and shall include the items set forth in this Subsection 9.2.3 (read 9.2.3.1-.20) |  | 9.2.1.4 The “Contingency” provided in the Guaranteed Maximum Price plus accumulated line item savings, that Owner agrees to allow Contractor to utilize, are the maximum sums available to cover costs that would increase the Cost of the Work and result from unforeseen conditions and events not evident to Owner or Construction Manager at the time of execution of this Agreement, and that would not constitute a Change Order under Article 7, such as (i) refinement of details of design within the scope and standard of quality and quantities on which the Guaranteed Maximum Cost was based, (ii) Intentionally Deleted, (iii) correction of minor defects or omissions in the Work (which have not resulted from the negligence of Construction Manager or anyone acting through or under Construction Manager), and (iv) delays due to labor disputes and unusually severe weather that would not give rise to a Change Order under Subsection 8.3.1. The proposed use of the Contingency shall be submitted by Contractor and decided upon on a monthly basis by Owner. No sums may be charged to the Contingency except upon approval by Owner, which shall not be unreasonably withheld, and then only to the extent that such funds have been paid, or are to be paid, by Construction Manager. If, at the completion of the Work any sums remain in the Contingency, such sums shall not constitute “savings” and, accordingly, Construction Manager shall not be entitled to share in any portion thereof. | see response to item #42 | Other | none defined, but we show hours charged per person and costs thereof | Yes | all project staff in 01 codes except VDC; all GRs are in 50 codes | 7.1.7 If Construction Manager intends to use any of its own forces for Work authorized by Change Order, Construction Manager shall notify Owner of such decision and Owner shall have the right to require Construction Manager to obtain and evaluate for Owner competitive bids for such Work. Owner shall then have the option to require Construction Manager to accept one (1) of the bids or to permit Construction Manager to perform such Work with its own forces. Construction Manager shall include in each subcontract a clause providing that, with respect to a Change Order, each Subcontractor’s mark-up for overhead and profit shall not exceed fifteen percent (15%) of the amount which such Subcontractor will receive for furnishing labor or materials in connection with such Change Order. Notwithstanding the foregoing, in no event shall the aggregate mark-up for overhead and profit on all tiers of Subcontractors exceed fifteen percent (15%) with respect to a Change Order. | see response to item #48 | 7.1.6 Changes in the Work accomplished by Change Order or Construction Change Directive shall not cause any modification to Construction Manager’s Fee, except as follows: If upon completion of the Work, the net of all additive and deductive changes (except for Allowance work, the fee for which shall not be adjusted) have resulted in an increase in the Guaranteed Maximum Price (as defined in Subsection 9.2.1), then Construction Manager’s Fee shall be increased by two and three quarters percent (2.75%) of the amount by which the adjusted Guaranteed Maximum Price exceeds the initial Guaranteed Maximum Price; if the net of all additive and deductive changes (except for Allowance work, the fee for which shall not be adjusted) have resulted in a decrease in the Guaranteed Maximum Price, then Construction Manager’s Fee shall not be reduced, it being understood and agreed that Construction Manager’s Fee shall not be subject to any reduction by reason of any savings achieved by Construction Manager in the Cost of the Work or changes in scope. | 2.5% (Exhibit J rate sheet) | 0.1% (Exhibit J rate sheet) | Undefined in Agreement. 5% markup initially on C/S however was later rejected and removed for remaining PCCOs | 1% (Exhibit J rate sheet) | 0% (unless P&P bond is added, then 1%) |  | 8.3.1 If Construction Manager is delayed at any time in the progress of the Work by the occurrence of any of the following events (each a “Force Majeure Event”): (i) strikes, lockouts or labor disputes, not caused by, or within the reasonable control of Construction Manager; (ii) substantially adverse weather which are abnormally severe (ascertained by reference to the official records of the National Oceanic and Atmospheric Administration applicable to the Villanova, PA area for the previous five (5) years) which delays or precludes construction of the Work and which could not be reasonably anticipated by Construction Manager | The Contract Time takes into account normally anticipatable adverse weather which will materially interfere with the timely prosecution of the Work. Construction Manager shall not be entitled to changes in the Contract Sum or Required Completion Date due to weather conditions which do not meet the criteria set forth in the first sentence of this Section 8.3.1. Owner shall not be required to keep a record of days of precipitation or low temperatures and the burden of proof with respect to weather delays shall be upon Construction Manager. Upon the occurrence of a Force Majeure Event, the Construction Manager shall be entitled to reimbursement for all reasonable additional costs including General Conditions costs for such period of delay to the extent such period of delay impacts the critical path of the Project Schedule. Construction Manager will send a written claim, with supporting documentation, for any requested extension of time by notice to Owner, indicating the existence of a situation constituting a Force Majeure Event, given within (5) business days or as soon as practicable after the event occurs for which such claim is made and Construction Manager shall notify Owner of the nature and probable duration of such delay as soon as practicable after Construction Manager knows of such delay. Construction Manager agrees to use all reasonable efforts to shorten and minimize the impacts of any such Force Majeure Event. | see answer to item #56 |  | Ref. Article 3.13 |  | 3.12.3.6 Maintain a daily log, showing actual performance, manpower utilized, weather conditions, and other pertinent data. Such daily log is to be submitted to Owner on a weekly basis. 3.13.2 ...Construction Manager shall also keep and make available to the Owner, Developer and Architect, a daily log containing a record for each day of weather conditions, portions of the Work in progress, number of workers on the Project site, identification of equipment on the Project site, problems that may affect progress of the Work, accidents, injuries and any other information required by Owner or Owner’s lender. |  | Ref. Article 8.3 - Force Majeure & weather impacts and notice within 5 days of event or awareness of event | Construction Manager will send a written claim, with supporting documentation, for any requested extension of time by notice to Owner, indicating the existence of a situation constituting a Force Majeure Event, given within (5) business days or as soon as practicable after the event occurs for which such claim is made and Construction Manager shall notify Owner of the nature and probable duration of such delay as soon as practicable after Construction Manager knows of such delay. Construction Manager agrees to use all reasonable efforts to shorten and minimize the impacts of any such Force Majeure Event. 8.3.4 Any claim for extension of time pursuant to Subsections 8.3.1 or 8.3.2 shall be made in writing to Owner not more than ten (10) days after the Construction Manager knew or should have known the commencement of the delay; otherwise it shall be waived by Construction Manager and no extension of the Required Completion Date may occur. In the case of a continuing delay due to a single cause, Construction Manager shall provide fourteen (14) day updates on the delay to Owner. Construction Manager shall provide an estimate of the probable effect of such delay on the progress of the Work. Such estimate shall include a breakdown in reasonable detail of the reasons for such request for extension and the number of days of delay estimated to be attributable to each source of delay listed in such estimate. No extension of time due to a source of delay not expressly listed in such application may be asserted by Construction Manager after the expiration of the aforesaid ten (10) day period. |  | 8.4.1 Without limiting the generality of Subsection 8.3.3, in the event of delay due to acts or omissions to act by Construction Manager, Subcontractors, or anyone acting under or through Construction Manager (“Inexcusable Delay”), Owner may direct that the Work be accelerated by means of overtime, additional crews or additional shifts or re-sequencing of the Work. All such acceleration shall be at no cost to Owner. In the event of any delay contemplated by Subsections 8.3.1 and 8.3.2, Owner may similarly direct acceleration and Construction Manager agrees to perform same on the basis of reimbursement of direct cost (i.e., premium portion of overtime pay, additional crew, shift or equipment cost and such other items of cost requested in advance by Construction Manager and approved in writing by Owner), plus the Construction Manager’s Fee in accordance with Article 7, but expressly waives any other compensation therefor unless otherwise agreed in writing in advance of performing the accelerated Work. In the event of any acceleration requested pursuant to this Subsection, Construction Manager shall provide promptly a plan including its recommendations for the most effective and economical acceleration. | 8.1.4 The term “day” as used in this Agreement and in the Contract Documents shall mean calendar day, unless otherwise specifically defined. | 9.8 | 9.8.1 When Construction Manager considers that the Work, or a designated portion thereof which is acceptable to Owner, is nearing Substantial Completion as defined in Subsection 8.1.3, Construction Manager shall provide to Owner and Architect written notice thereof not less than ten (10) business days prior to the date that Construction Manager intends to deliver the Certificate of Substantial Completion as required by this Section. Along with such notice, Construction Manager shall simultaneously submit to Owner and Architect a list of items (the “Punchlist”) which must be completed or corrected as a condition to final payment. If Owner agrees that the Work or such designated portion is Substantially Complete, Owner, Construction Manager and Architect shall inspect the Work or such designated portion and supplement the Punchlist with any additional items which must be completed or corrected as a condition to final payment. The failure to include any items on such list does not alter the responsibility of Construction Manager to complete all Work in accordance with the Contract Documents and to satisfy all conditions precedent to final payment. When Architect and Developer on the basis of an inspection and with the approval of Owner, determine that the Work, or a designated portion thereof, is Substantially Complete, and provided that all conditions precedent to Substantial Completion in the Specifications have been satisfied, Architect, in consultation with Owner, shall then prepare a certificate confirming the occurrence of Substantial Completion (“Certificate of Substantial Completion”) on AIA Form G704 or other form acceptable to Owner, shall state the responsibilities of Owner and Construction Manager for security, maintenance, heat, utilities, damage to the Work and insurance, and shall fix the time within which Construction Manager shall finish all items on the Punchlist, provided, however, that all items on the Punchlist | 9.9.1 | 9.9.1 “Final Completion” is the completion of all Work, including Punchlist and incomplete or defective Work, as determined by the Owner. Upon receipt of written notice from Construction Manager to Owner and Architect that the Work is ready for final inspection and acceptance, Architect and Owner will promptly make such inspection and, when Architect and Owner find the Work acceptable under the Contract Documents and the Contract Documents fully performed, including, without limitation, the close-out conditions precedent described in the Specifications, Architect, upon mutual agreement with Owner, will promptly issue a “Certificate of Final Completion” stating without reservation that, on the basis of Architect’s observations and inspections, the Work has been completed in accordance with the terms and conditions of the Contract Documents. | No | n/a | 9.5 (Progress Payments); 9.9 (Final Payment) | 10% [9.5.5] | 9.5.5 | 9.5.5 Notwithstanding anything to the contrary in this Agreement, Owner shall have the right to retain ten percent (10%) of each Progress Payment otherwise due Construction Manager under this Agreement until at least thirty (30) days after the Architect issues a Certificate of Final Completion and Owner, and, if applicable, Owner’s lender have accepted the Work, and Construction Manager has complied with all conditions precedent to final payment, including those set forth in Section 9.8. Upon Construction Manager’s request, Owner, in Owner’s sole and absolute discretion, and with the consent of Owner’s lender, may authorize the release of retainage due designated Subcontractors upon final completion of their scope of work and delivery by such Subcontractors of the appropriate certifications and lien releases required under this Agreement | No | No |  | 9.4.7 Other than for suitably stored materials as set forth in Subsection 9.4.5, Owner will not advance progress payments for Subcontractor engineering, Shop Drawing preparation, mobilization or insurance costs, all of which are incidental to the award of the Subcontract and the subsequent performance of the Work; however, Subcontractor may include such costs (limited to a one time maximum of two percent (2%) of the Subcontract amount) only in a payment request submitted after the commencement of Work by Subcontractor on the property. In the event Subcontractor has purchased a performance and payment bond, Owner will advance progress payments for the cost of same upon request and upon receipt of a copy of the invoice for the premium. If a Subcontractor is required to make a material deposit to secure material price or delivery date for the following categories of materials: Sitework, Precast Concrete, Structural Steel, Mass Timber Frame, Glass, Metal Panels, Elevators, Electrical Equipment, HVAC Equipment, then Owner will advance progress payments for the cost of same upon request and upon receipt of a copy of the invoice or purchase order; provided however that (i) each such deposit shall be no more than twenty-five percent (25%) of the total cost of the applicable material cost, (ii) Owner reserves the right to contract with, and pay such material deposit directly to, the applicable supplier, and (iii) Owner shall not be required to pay any deposit to which Owner’s construction lender objects. | 9.5.1 After Developer, Owner and the Architect have approved the Application for Payment, Owner shall make payment in the manner and within the time provided in the Contract Documents, but in no event later than thirty (30) days after receipt of an Application for Payment in form acceptable to Owner and Architect. | 9.7.1 | 9.7.1 If Owner (except as provided in Subsection 9.6.1) does not pay Construction Manager amounts not disputed within ten (10) days after the date established in the Contract Documents, any amount approved by Developer and Architect, then Construction Manager may, upon fifteen (15) additional days’ written notice to Owner, stop the Work until payment of the amount owing has been received. The Contract Sum shall be increased by the amount of Construction Manager’s reasonable costs of shut-down, delay and start-up, which shall be effected by appropriate Change Order in accordance with Section 7.2. Nothing in this Section shall be deemed to authorize or permit Construction Manager to stop the Work in the event of a dispute over any sum claimed to be due by Construction Manager so long as Owner has paid Construction Manager all sums not in dispute | 4.4 and 4.5 | 13.1 | 7 [13.2.1] | 7 [13.2.1] | [5 empty] | 3.8.1 Construction Manager warrants to Owner that all materials and equipment furnished under this Agreement shall be free of liens and be of good quality and new unless otherwise required or permitted by the Contract Documents, that the Work will be free from defects in materials and workmanship, and that the Work will conform with the requirements of the Contract Documents. Work, materials and equipment not conforming to these requirements, including substitutions not properly approved and authorized, shall be considered defective. Construction Manager shall cause to be corrected all defective Work in accordance with the terms and conditions of Section 12.2. Construction Manager’s warranty excludes damage or defects caused by abuse, modifications not performed by Construction Manager, Subcontractors or Sub-Subcontractors, improper or, following the completion of the Work, insufficient maintenance, improper operation, or wear and tear under normal usage. If required by Architect or Owner, Construction Manager shall furnish satisfactory evidence as to the kind and quality of materials and equipment. Upon completion of the Work, Construction Manager shall provide to Owner all manufacturer’s warranties applicable to components of the Work pursuant to the terms of Section 9.8.1 hereof. |  | 3.12.3.3 Maintain a set of plans and specifications to reflect as-built conditions for use of others in producing record drawings; maintain an on-site library of sources for material, labor, services, approved shop drawings and samples. .4 Assist Architect in preparing and making available to Owner at least two (2) sets of as-built drawings and specifications of all equipment and construction items, manuals, brochures and other documents required by Owner. | 9.9.2 | 9.9.2 Neither the final payment nor the remaining retainage shall become due until Architect issues his Certificate of Final Completion, Developer, Owner and Owner’s lender accept the Work and approve the final Application for Payment and Construction Manager submits to Architect, Developer, and Owner (i) an affidavit, in form and substance satisfactory to Owner and, if applicable, Owner’s construction and permanent lenders, that all payroll, bills for materials and equipment, and other indebtedness connected with the Work for which Owner or Owner’s property might in any way be responsible or encumbered, have been paid or otherwise satisfied, (ii) consent of surety, if any, to final payment, (iii) a certificate evidencing that insurance required by the Contract Documents to remain in force after final payment is currently in effect and will not be canceled or allowed to expire until at least 30 days’ prior written notice has been given to Owner, (iv) a written statement that Construction Manager knows of no likely reason that the insurance will not be renewable to cover the period required by the Contract Documents, (v) other data establishing payment or satisfaction of such obligations, such as receipts, releases and waivers of liens, claims, security interests or encumbrances arising out of the Work, to the extent and in such form as may be designated by Owner, and releases of liens and claims confirming that Construction Manager and all Subcontractors, Sub-subcontractors, Suppliers and Subconsultants have released and waived all liens and claims and rights to file liens against the Site that any such party may have in the form appended hereto as Exhibit “M-1” and Exhibit “M-2”, (vi) an electronic CAD set and two paper sets of “as built” drawings, all operation and/or maintenance manuals relating to the Work and any special tools and appliances necessary or appropriate to the proper maintenance and/or operation of any part Subcontractor of any tier or any Subconsultant refuses to furnish a release or waiver required by Owner, Construction Manager may, to the extent permitted by Owner’s construction and/or permanent lender, and solely within Owner discretion, furnish a bond and escrow account satisfactory to Owner to indemnify Owner against any such lien. If any such lien remains unsatisfied after all payments are made, Construction Manager shall promptly refund to Owner all monies that the latter may be compelled to pay in discharging such lien, including all costs and reasonable attorneys’ fees that are not paid for any reason out of the escrow fund. |  | see Article 10.1 | 7 days (same as all other issues) | 3.13.2 (Monthly Report; Suppliers/Fabricators Report; others upon request by Owner and Owner's Lender) 10.2.12 Safety Reports (upon accident) | No |  | Yes | Yes | Union | No | EXHIBIT "A" Legal Description of the Site EXHIBIT "B" Drawings and Specifications EXHIBIT "C" Reserved EXHIBIT "D" Schedule of Values EXHIBIT "E" Proposal of Construction Manager EXHIBIT "F" Site Affidavit EXHIBIT "G" Project Schedule EXHIBIT "H" Breakdown of the Guaranteed Maximum Price EXHIBIT "I" General Conditions Items EXHIBIT "J" Billing Rates for Field Personnel EXHIBIT "K-1" Construction Manager’s Form of Progress Payment and Releases of Liens EXHIBIT "K-2" Subcontractor’s Form of Progress Payment and Releases of Liens EXHIBIT "L" Intentionally Omitted EXHIBIT "M-1" Construction Manager’s Form of Final Payment and Releases of Liens EXHIBIT "M-2" Subcontractor’s Form of Final Payment and Releases of Liens EXHIBIT “N” Health, Safety and Environmental Requirements EXHIBIT “O” Low VOC Requirements EXHIBIT “P” Mold Operations and Maintenance Plan Requirements EXHIBIT “Q” Subcontractor Insurance Requirements | No |  | n/a | see answer to item #15 as well as: 11.3.1.2 If the property insurance obtained by Construction Manager requires minimum deductibles or Construction Manager voluntarily elects to have such deductibles, Construction Manager shall pay costs not covered because of such deductibles. If Owner or insurer increases the required minimum deductibles above the amounts identified above or if Owner elects to purchase this insurance with voluntary deductible amounts greater than $5,000, Owner shall be responsible for payment of the additional costs not covered because of such increased or voluntarily deductibles. If deductibles are not identified in the Contract Documents, Owner shall pay costs not covered because of deductibles.
11 | 24 | 2025-10-06 | A102 - GMP Cost Plus Fee | GMP | Yes | Owner or Engineer shall not be liable for any consequential damages. | Yes | Yes | 7500 per calendar day for each day past the actual substantial. 1000 per calendar day for each day the actual date of final completion exceeds (30) days after the actual substantial completion. |  | 1.5 | IMC | 26.22 | 6111968 |  | Yes | No | No | Yes |  | Contractor shall furnish 100% performance and payment bonds covering faithful performance of the contract and the payment of all obligations |  | Reference Article 1 |  | Reference Article 2.3 &1 |  | Contractor has specifically informed the architect and owner in writing of such devisation at the time of submittal and (1) the Architect and Owner have given written approval to the specific deviation as a minor change in the work, or (2) a Change Order or Construction Change Directive has been issued authorizing the deviation. | Yes | No |  | At cost per Exhibit N |  | No | 3 |  | No | Yes | Yes |  | 30% to the owner and 70% to the contractor for cost savings declared by contractor in months (1) through (3) of the agreement term. |  | Yes | No | Reference Article 5.2.6 | No | Exhibit N |  |  | Reference Article 7.1 |  | Reference Exhibit S | Reference Exhibit S | Other | Staffing hour reports | Yes | 01 will be staff , 50 other | 15 | N/A Typ. 5 | 3 | 1.2 | 0.1 | 2.5 | 1 | N/A |  | "(a) the weather experienced at the Project site during the term of this Agreement is more severe than the adverse weathel anticipated for the Project location during any given month, (b) the unusually severe weather must actually cause a delay to the criticai path for the completion of the Project, and (c) the delay must be beyond the control and without the fault or negligence of the Contractor. If the conditions of this Section 8.7.7 .3 are met, the delay(s) shall be referred to a ""Weather" | (5) Days after the contractor knows | Reference Article 8.1.72 |  | Exhibit A |  | 3.10.4 |  | See Article 4.3 |  |  | Within (5) days to provide notice and (30) days to realize actual impact. | 603 (Calendar Days) from Authorization to proceed | A102 Article 4.3 | A102 Article 4.3 | A102 Article 4.312 | A102 Article 4.312 | Yes | 5 Model Units to be completed 120 Calendar Days before Substantial Completion |  |  | 12.1.8 | (50%) of work is complete contractor may request owner not retain any additional amounts from subsequent progress payments. Only (25% of remaining retainage may be withheld by Owner prior to audit completion which shall be completed no later than thirty (30) days after substantial completion. | No | No |  | Brightview pays up to an established value on stored materials. | 30 Days | A201 Article 9.7 (7) Days | A201 Article 9.7 | A201 Article 15 | #4 | Does not state | (7) Days | [5 empty] | 1 Year from Substantial Completion |  | Item 10 Under Quals & Clarifications As-Builts by Owner | 12.2.1 | 1) Fully performed the contract except for the contractors responsibility to correct work. 2) Final Cerificate for Payment has been issued by the Architect and approved by the Owner and Lender 4) The Owner has received final waivers and releases of lien and claims from contractor contingent upon payment from the owner 5) Final certificate of costs has been submitted and approved by the Owner & Lender 6) other conditions to final payment set forth in the contract documents have been satesfied by the contractor. |  | (l) subsurface or otherwise concealed physical conditions that differ materially from those indicated in the Conhact Documents or (2) unknown physical conditions ofan unusual nature, that diffet materially from those ordinarily found to exist and generally recognized as inherent in construction activities of the character provided for in the Contract Documents, the Contractot shall promptly provide notice, in writing, to the Owner and the Architect as soon as practicable before conditions are disturbed and in no event later than fourteen (14) days after first observance ofthe conditions. The Architect will promptly investigate such conditions and, where appropriate, will recommend an equitable adjustment in the Contract Sum or Contract Time, or both. If the Architect determines that the conditions at the site are not materially different from those indicated in the Contract Documents and that no change in the terms of the Contract is justified, the Architect shall promptly notiff the Owner and Contractor in writing, stating the reasons. If either party disputes the Architect's detennination or recomrnendation, that parfy may proceed as provided in Article 15. No adjustment shall be made for any condition encountered if notice is not given within fourteen (14) days after the Contractor first observes or discovers the unknown or concealed conditions. | 14 Days | Monthly Report | No |  |  |  | Non-Union | No | Exhibit A - Insurance and Bonds , Exhbit A - Construction Schedule, Exhibit B - Qualifications and Clarifications, Exhibit C - Schedule of Values, Exhibit D - (Intentionally Omitted), Exhibit E - Drawings and Specifications, Exhibit F - Intentionally Omitted, Exhibit G1-4- Conditional & Unconditional Lien Waivers, Exhibit H - White Glove Standards, Exhibit I - Environmental / Geotechnical Reports, Exhibit J - List of Entities for Insurance Purposes, Exhibit K - Sub Default Insur Plan, Exhibit L - Responsibility Matrix, Exhibit M - Form of Contractor Notice of Substantial Completion Date, Exhibit N - Reimbursable General Conditions Expenses, Exhibit O - Form of Construction Change Directive, Exhibit P - Warranty Process Standard, Builders Risk Reqs, Exhibit R - Delegated Design Items, Exhibit S - Modifications to Cost Savings Provisions & Buyout Risk Contingency, | No
19 | 13 | 2024-01-17 | A102 - GMP Cost Plus Fee | A102 | No | N/A | No | Yes | Article 5.1.6 - Contractor fail to achieve substantial completion of Phase 1 by date established in Paragraph 4.3, $40 per unit per day for each calendar day until substantial completion is achieved. LD's shall not exceed 50% of the Contractor's fee. |  | 2.5% | Owner | N/A | N/A | N/A - Reference article 15.5.1 | Yes | No | Yes | No |  | Article 15.5.2 - Unless the Lender requires P&P bond, the contractor is not required to furnish P&P bond. P&P was excluded and documented in GMP qualifications. |  | Reference Article 1 The Contract Documents. Includes Agreement, General Conditions, Drawings, Specifications, Addenda, other listed docs. |  | A201 Article 3.2 - become familiar with the site and contract documents. Because the Contract documents are complementary, the contractor shall before starting each portion of work, carefully study and compare the carious CD's relative to that portion of the work and take field measurements of existing work. Promptly report to the Architect any errors, inconsistencies or omissions discovered. |  | Article 3.4.2 - Contractor can only make substitutions with consent of owner after evaluation by Architect. | Yes | Yes |  | $60,000 of Precon costs were included in GMP |  | No | N/A |  | No | Yes | Yes |  | 75% to Owner, 25% to Contractor distributed at final payment |  | No | No | N/A | No | Exhibit C | 2023 |  | Costs necessarily incurred by the contractor in the performance of the work and set forth in Article 7. |  | N/A | N/A | Other | N/A - Will provide standard GC backup or anything that is requested by bank | Yes | N/A - We will do standard 01 vs 50 Code Split | Not Stated - Will use 15% |  | 3% | 2.5% | 0.1% | Actual Costs | 1% | N/A |  | Article 15.1.6.2 - If adverse weather conditions are the basis for a claim for additional, such claim shall be documented by data substantiating that weather conditions were abnormal for the period of time, could not have been reasonably anticipated, and had an adverse effect on the scheduled construction. | N/A | N/A |  | The schedule shall contain detail appropriate for the project, including (1) the date of commencement of the work, intern schedule milestone dates, and the date of substantial completion, (2) an appointment of the work by construction activity and (3) the time required for completion of each portion of work. The schedule shall provide for the orderly progression of the work to completion and shall not exceed time limits current under the Contract documents. The schedule shall be revised at appropriate intervals as required by the conditions of the work and project. |  |  |  | N/A | N/A |  | N/A | N/A | Article 4 | 22-23 months for construction only. | Article 9.10 | Work completed in accordance with the Contract Documents. | No | N/A | Article 12 | 10% | Article 12.1.8.2 | When the project is 50% complete as determined by the total amount determined in accordance with 5.1.6.1, no further retainage is to be withheld on the last 50% of the project. | Yes | Yes |  | N/A | 30 | 9.7 | After (7) of established in the contract documents, then contractor may, upon 7 days notice to Ower and Architect, stop the work until payment of the amount owing has been received. | Article 13 | Article 14 | N/A | 7 days | [5 empty] | Article 3.5 - Contract warrants to the Owner and architect that materials and equipment furnished under the contract will be of good quality and new unless the CD require of permit otherwise. Free of defects. |  | All submittals, PD, samples, etc. shall be made available upon completion of the work as a record of the work as constructed. | Article 12.2 | Final payment shall be made no later than 30 days after the issuance of the Architect's final certificate for payment. |  | Article 10.3 | Immediately | Cost/Budget Reports Monthly Report | No |  | Yes | Yes | Non-Union | Yes | Exhibit A - Precon Agreement Exhibit B - GMP Exhibit C - Reimbursable Cost of Work Sheet Exhibit D - Sample Cert of Insurance | No |  | N/A | Owner
20 | 10 | 2023-09-28 | Custom Contract | GMP (similar to AIA 102) | No | 13.15 (mutually waived) | Yes | Yes | 3.08 (i) Tenant: If a tenant lease for all or a portion of that Building is under negotiation or executed as of the applicable Milestone Date for Substantial Completion, the liqudiated damages shall be Four Thousand Dollars ($4,000) per day commencing on the fifteenth (15th) day after the Milestone Date for Substantial Completion of that Building to and until Substantial Completion is achieved. (ii) No Tenant: If a tenant lease is not under negotiation or executed for any portion of the Building as of the applicable Milestone Date for Substantial Completion, the liqudiated damages shall be Two Thousand Dollars ($2,000) per day commencing on the thirtieth (30th) day after the Milestone Date for Substantial Completion of that Building and continuing for the next six (6) calendar months that follow, and Five Thousand Five Hundred Dollars ($5,500) per day thereafter, to and until Substantial Completion of that Building is achieved. |  | 2.5% (8.04b) | Owner | n/a | TBD (we don't have a copy of the policy yet - expected March 2024) | TBD | Yes | No | Yes | No |  | n/a can't bond sub out of SDI unless Owner agrees |  | ? |  | 1.01b The intent of the Contract Documents is for General Contractor to perform all necessary scheduling, procurement, supervision, construction and construction management services and supply all necessary labor, materials, equipment and related work and services for the Project, including all things reasonably inferable from the Contract Documents as being necessary to fully complete the Work and obtain the intended results in accordance with the requirements of the Contract Documents, including, but not limited to, the GMP and the Project Schedule (as such terms are defined below). The Contract Documents are complementary, and what is required by one shall be as binding as if required by all. Performance by General Contractor shall be required only to the extent consistent with the Contract Documents and reasonably inferable from them as being necessary to complete the Work in accordance with the Contract Documents. |  | 2.05 a, b, c - substitutions requirements (equal or better value; provide credit if necessary; prove it's equal; can only use if specified product is unavailable or doesn't work as designed, manufacturer refuses to guarantee product, or per Owner direction) | No | No |  | it was a bid job |  | Yes | 5 |  | Yes | No | Yes |  | 100% owner |  | Yes | No | SECTION 4.05 Buy Out Savings. Except in the case of a replacement pursuant to Section 2.03(h) above, if General Contractor enters into a Subcontract after execution of the Agreement, General Contractor shall update the Schedule of Values to reflect the actual Subcontract price for that scope of work. If the Subcontract price is less than the value attributed to such Work in the Schedule of Values, the difference shall be referred to as “Buy Out Savings.” If the Subcontract price is more than the value attributed to such Work in the Schedule of Values, the difference shall be referred to as “Buy Out Losses.” The Contingency shall be increased or decreased, as applicable, by the net amount of Buy Out Savings, after accounting for all Buy Out Losses, and the Schedule of Values shall be updated accordingly; provided, however, that in no event shall the GMP be increased on account of any Buy Out Losses. | Yes | B2 | 2023 |  | SECTION 5.01 Cost of Work. “Cost of Work” means the costs listed in this Section 5.01 to the extent that they are incurred in the proper performance of the Work and have been or will be paid by General Contractor, at rates not higher than the standard paid in the locality of the Project, except with the prior consent of Owner. The rates set forth in Exhibit B2 (General Conditions Costs Matrix) and Exhibit B5 (Unit Pricing) will be charged to the extent applicable. The Cost of Work is limited to the following: read a) through m) see 5.02 for general conditions costs see 5.03 for costs not to be reimbursed |  | SECTION 4.06 Contingency. Contingency shall be used by General Contractor to cover unanticipated expenses which are necessary to complete the Work and for which General Contractor is not entitled to a Change Order; provided, however, that notwithstanding anything to the contrary herein, in no event shall Contingency be used for the costs of correcting non-conforming or defective Work, costs arising from the gross negligence or willful misconduct of General Contractor or its Subcontractors, or costs within the scope of coverage of any SDI Policy or payment or performance bond. Owner has the right to determine the allocation of the Contingency, and the Contingency shall not be used without Owner’s prior written authorization in each instance, which shall not be unreasonably withheld or delayed. General Contractor’s use of the Contingency for schedule recovery shall not exceed One Hundred Thousand dollars ($100,000) in the aggregate. Owner shall retain any portion of the Contingency that is not expended in accordance with this Section. | need prior authorizatoin | Reimbursable | full backup of all costs | Yes | SECTION 11.01 Maintenance. General Contractor shall prepare and maintain complete records of costs incurred by General Contractor in the performance of the Work, which records shall be adequate to determine the Cost of Work and the Price and in such format and detail as is acceptable to Owner. General Contractor shall preserve such records for a period of five (5) years after Final Payment hereunder. Owner shall, at no cost to Owner, have access to the Work at all reasonable times and the right to audit General Contractor’s books, records, correspondence, instructions, drawings, receipts, vouchers and memoranda, relating to the Work or any costs charged to Owner. Owner or its representative may audit General Contractor’s records at any time during the term of this Agreement and for a period not to exceed five (5) years after Final Payment. If an audit reveals overcharges, General Contractor shall promptly reimburse Owner the amount of the overcharges, plus interest at the rate of one-and-one-half percent (1.5%) per month from the time that Owner paid such overcharges. | 15% on all adds and deducts | 0% | 2% | 0% | 0% | 0% | 0% | 0% |  | See Exhibit K - weather exhibit for days per month included in contract 1.05 hh “Force Majeure” means unusually severe adverse weather conditions not reasonably foreseeable or reasonably anticipated (as determined on the basis of the past ten (10) year weather records collected by the National Oceanic and Atmospheric Administration, as shown in Exhibit K); strikes or labor disputes that arise for reasons other than a dispute at or directly involving General Contractor or the Project; riots, war or insurrection; or acts of God or other similar causes that are unavoidable, unforeseeable and beyond the control of General Contractor, any Subcontractor or anyone for whose acts they may be liable. 1.05 yyy “Weather Day” means means a day on which General Contractor is unable to perform more than four (4) hours of critical path activities due solely to weather and not due to (i) the act or omission of General Contractor or any Subcontractor; (ii) the bankruptcy or insolvency of General Contractor or any Subcontractor; (iii) the failure of Architect or any Consultant or Contractor to perform any portion of the Work in accordance with the terms of its subcontract; (iv) the negligence or willful misconduct of General Contractor or any Subcontractor; or (v) a breach or default by General Contractor under this Agreement; provided, however, that in no event shall a Weather Day include a Sunday, a federal holiday or any other day on which, prior to the weather event, no Work was scheduled. 3.05 d General Contractor shall give Owner notice of a Weather Day within two (2) business days. Such notice must include, at minimum, a description of the weather on the day(s) in question, the number of hours worked on such day(s), the critical path activities that were scheduled for such day(s), and documentation supporting General Contractor’s assertions in the notice. Failure to provide notice in accordance with this Section shall be deemed a waiver of General Contractor’s right to claim such Weather Day(s) as a Force Majeure Delay. | 2 | see exhibit K for monthly breakdown |  | 3.05b General Contractor shall, no less frequently than monthly, and more often if requested by Owner, update and submit its Project Schedule to Owner for review and approval with a level of detail acceptable to Owner. Any updates or changes to the Project Schedule shall (i) take into account all reasonably foreseeable events (including, without limitation, weather delay, cost increases due to supply shortages and inflation), (ii) not exceed or modify the Milestone Dates and other time limits under the Contract Documents, as such time limits may be adjusted under the Contract Documents, (iii) take into consideration any other work being performed at the Project Site, (iv) provide for the expeditious and practicable execution of the Work, and (v) identify the total amount of unused float for Work performed as of that date. General Contractor shall cooperate with Owner in revising the Project Schedule as deemed necessary by Owner. |  | 2.02y - need to keep daily log |  | see #56 above | 2 |  | 7.03e (i) In the event of a Force Majeure Delay or a Compensable Delay, and subject to the provisions of Section 7.03, General Contractor shall be entitled to an extension of the Milestone Dates to the extent that (i) such delay impacts the critical path of the Project Schedule, and (ii) such delay will prevent General Contractor from achieving Substantial Completion by the applicable Milestone Date but only if the performance of the Work is not, was not, or would not have been delayed by any other cause for which General Contractor is not entitled to an extension under the Contract Documents. In the alternative, the Owner may direct General Contractor to accelerate the Work, in which case the Milestone Dates shall not be extended to the extent of the acceleration but the GMP shall be increased by the additional Cost of Work (excluding General Conditions Costs) incurred by General Contractor due solely to such acceleration, without any markup for Fee in the event of a Force Majeure Delay or with a markup for Fee in the event of a Compensable Delay. The foregoing shall be General Contractor’s sole remedy for Force Majeure Delay except as otherwise stated in Section 7.03(e)(ii) below. | calendar | 9.01 | “Substantial Completion” means that point in the progress of the Work when the Work or designated portion thereof is sufficiently complete in accordance with the Contract Documents to enable Owner or its tenants to use and occupy the Project or the agreed, defined portion of the Project, for its intended use, and (i) only minor punch list items or similar minor corrective work remains to be completed and does not adversely affect the capability of the Project to operate and function safely in the ordinary course of business; (ii) General Contractor has received and delivered to Owner a temporary (or partial) certificate of use and occupancy (or equivalent) and any other permits or approvals necessary to allow use and occupancy of the Project, or the agreed, defined portion thereof, accompanied by a written undertaking by General Contractor to deliver to Owner a permanent certificate of occupancy at the earliest possible time; (iii) Owner has been afforded clear and unobstructed access to the Building twenty-four (24) hours per day, seven (7) days per week; and (iv) all sitework that is part of the Work has been completed to the extent necessary for Owner to occupy and use the Work. | 9.02 | “Final Completion” means the point at which General Contractor has completed all of the Work, including Punch List Items, in accordance with the Contract Documents. | No | SC 3/11/25 FC 4/9/25 | 6.03 | 10% (6.03 g ii) | n/a | n/a | Yes | Yes |  | 6.03c To the extent approved by Owner in writing, Applications for Payment may include amounts for materials and equipment delivered and suitably stored at the site or off the site for subsequent incorporation into the Work. Requests for payment for materials or equipment stored off the site shall be accompanied by the following: (i) evidence that the materials or equipment are safely and suitably stored in a bonded warehouse, or other location approved by Owner in writing, with appropriate insurance coverage; (ii) photographs of the materials and equipment; and (iii) evidence that the materials or equipment are specific to the Project. Owner may approve or deny such requests in its sole discretion and subject to any conditions Owner deems necessary to establish Owner’s title to such materials and equipment or to otherwise protect Owner’s interests. General Contractor shall remain responsible for all risk of loss to materials and equipment stored on or off site notwithstanding Owner’s approval of off-site storage or payment for such materials or equipment. | 30 (6.03 g i) | n/a | n/a | XII | 10.03 and 10.04 | 10 (10.04) | 7 (10.02 a) | [5 empty] | SECTION 2.07 Warranty. General Contractor covenants and warrants to Owner, its successors as owner of the Project Site, other designees and any tenant or occupant of the Buildings and their respective successors and assigns that the Work shall: (a) conform to the requirements of the Contract Documents; (b) be of good quality and free from defects in materials or workmanship, latent or otherwise, and shall be constructed in accordance with the Construction Documents; (c) conform to Applicable Laws in effect at the time of completion of the Work; (d) incorporate only new materials and equipment; and (e) be free of all Liens, stop notices and other encumbrances arising out of or related to the Work. |  | 2.02 y must maintain as-builts; due 30 days after SC and to be submitted in order to receive final payment | 6.05 | 6.05 punchlist complete affidavit subs list and disbursement records final unconditional releases and waivers of lien (IMC and subs) insurance docs consent of surety certification by GCs that all work was completed in accordance with Contract Documents as-builts warranties O&Ms certificates, licenses, permits, permanent certificate of occupancy payment due 45 days after the above is all submitted |  | SECTION 2.10 Hazardous Materials. General Contractor and Subcontractors shall not bring any Hazardous Materials on to the Project Site, except as necessary to perform the Work. General Contractor warrants that those performing Work that involves the use of Hazardous Materials are properly trained and legally permitted to do so to the extent required by Applicable Laws. General Contractor and Subcontractors shall comply with the Contract Documents, OSHA regulations and all Applicable Laws regarding the handling of any Hazardous Materials. With respect to Hazardous Materials not brought to the Project Site by General Contractor or any Subcontractor, if General Contractor encounters any Hazardous Materials or substances that it has reason to believe may be Hazardous Materials, General Contractor shall immediately stop Work in the affected area and report the condition to Owner in writing. General Contractor shall not resume Work in the affected area until directed by Owner. If General Contractor disputes Owner’s direction or if the parties dispute General Contractor’s right to an adjustment of the GMP or the Milestone Dates with respect to the Hazardous Materials or substances at issue, the parties shall resolve the dispute pursuant to Article XII. To the fullest extent permitted by Applicable Laws, General Contractor shall indemnify Owner from any and all costs, damages or losses incurred by Owner as a result of General Contractor’s failure to comply with the requirements of this Section 2.10. | 5 (7.03 c) | monthly owner report (see 3.06) | No |  | Yes | Yes | Union | Yes | EXHIBIT A – PROJECT SITE EXHIBIT B – GMP DOCUMENTS Exhibit B1 Schedule of Values Exhibit B2 General Conditions Costs Matrix Exhibit B3 Allowances & Alternates Exhibit B4 Qualifications and Clarifications Exhibit B5 Unit Pricing EXHIBIT C – DRAWINGS, SPECIFICATIONS & REFERENCE DOCUMENTS EXHIBIT D – PROJECT SCHEDULE EXHIBIT E – KEY PERSONNEL EXHIBIT F – FORM OF LIEN WAIVERS EXHIBIT G – SITE LOGISTICS PLAN EXHIBIT H – AWARD LETTER EXHIBIT I – CITY OF PHILADELPHIA ECONOMIC OPPORTUNITY PLAN EXHIBIT J – CCIP MANUAL EXHIBIT K – WEATHER EXHIBIT | Yes |  | n/a | TBD
21 | 16 | 2024-08-26 | A101 - Stipulated Sum | Lump Sum | No | Contractor is not entitled to payment for consequential damages | Yes | Yes | $2,000 daily, capped at 1/2 contract sum. Begins after 30 day grace period following contract substantial completion date (225 Calendar Days after NTP) |  | Not a CCIP Project | Owner | By owner | By Owner | Not provided in executed contract | Yes | No | Yes | Maybe |  | NA |  | For purposes of the agreement between Owner and Contractor, the “Contract Documents” consist of the Agreement for Construction between Owner and Contractor (inclusive of Exhibits A and C thereto, the “Agreement”), Conditions of the Agreement for Construction (General, Supplementary and other Conditions), Drawings, Specifications, addenda issued prior to execution of the Agreement, other documents listed in the Agreement and Modifications issued after execution of the Contract. A “Modification” is (1) a written amendment signed by both parties, (2) a Change Order, (3) a Construction Change Directive, (4) a written order for a minor change in the Work issued by Design Professional, or (5) a clarification of the interpretation of the Contract Documents or any specifications issued by Design Professional or made by Owner’s Designated Representative. |  | 14.2.1 Because the Contract Documents are complementary, before starting each portion of the Work, Contractor shall carefully study and compare the various Drawings and other Contract Documents relative to that portion of the Work, as well as any additional information furnished by Owner or Design Professional, shall take field measurements of any existing conditions related to that portion of the Work, and shall observe any conditions at the Project Site affecting the Work. Contractor shall not be liable to Owner for damage resulting from errors, inconsistencies or omissions in the Contract Documents, provided Contractor gives notice to Owner’s Designated Representative and Design Professional of any errors, omissions or inconsistencies promptly following Contractor’s discovery thereof. If Contractor performs any construction activity knowing it involves a recognized error, inconsistency or omission in the Contract Documents without such notice to Owner’s Design Representative and the Design Professional, Contractor shall assume appropriate responsibility for such performance and shall bear an appropriate amount of the attributable costs for correction. 14.2.1.1 The exactness of grades, elevations, dimensions, or locations given on any Drawings issued by Design Professional, or the work installed by other contractors, is not guaranteed by Owner. Contractor shall, therefore, satisfy itself as to the accuracy of all grades, elevations, dimensions, and locations. In all cases of interconnection of its Work with existing or other work, it shall verify at the Project Site all dimensions relating to such existing or other work. Any errors due to Contractor’s failure to so verify all such grades, elevations, dimensions, or locations shall be promptly rectified by Contractor without any additional cost to Owner. 14.2.2 Any design errors or omissions noted by Contractor during this review shall be reported promptly to Owner’s Designated Representative. 14.2.3 If Contractor believes that additional cost or time is involved because of clarifications or instructions issued in response to Contractor’s notices or requests for information pursuant to the terms hereof, Contractor shall make Claims as provided herein. If Contractor fails to perform the obligations of Sections 14.2.1 and 14.2.1.1, Contractor shall pay such costs and damages to Owner as would have been avoided if Contractor had performed such obligations. |  | The Work shall be in accordance with approved submittals except that Contractor shall not be relieved of responsibility for deviations from requirements of the Contract Documents by Design Professional’s and Owner’s Designated Representative’s approval of Shop Drawings, Product Data, Samples or similar submittals unless Contractor has specifically informed Design Professional and Owner’s Designated Representative in writing of such deviation at the time of submittal and (1) Design Professional and Owner’s Designated Representative have given written approval to the specific deviation as a minor change in the Work, or (2) a Change Order or Construction Change Directive has been issued authorizing the deviation. Contractor shall not be relieved of responsibility for errors or omissions in Shop Drawings, Product Data, Samples or similar submittals by Design Professional’s and Owner’s Designated Representative’s approval thereof. | No | No |  | NA |  | No | NA - completed under competetive bid |  | No | No | No |  | N/A - Project is lump sum. |  | No | No | N/A - Project is lump sum. | No | Not Provided | Not Provided |  | The term “Work” means the construction services required by the Contract Documents, whether completed or partially completed, and includes all other labor, materials, equipment and services to be provided by Contractor to fulfill Contractor’s obligations. The Work may constitute the whole or a part of the Project. |  | Contingency is used for unexpected costs within contract defined cost of work items. | Monthly reported contingency log. | Lump Sum | N/A - Lump Sum | No | The general conditions of this Agreement shall be the Owner’s General Conditions of the Agreement for Construction, a copy of which is attached hereto as Exhibit B (“General Conditions”). Terms not defined herein that are defined in the General Conditions shall have the meanings ascribed to them therein. | 10% as total payment for overhead and profit | Not provided for in prime agreement | 10% as total payment for overhead and profit | Not a CCIP project | Undefined. Strategize with management prior to first change order | Undefined. Strategize with management prior to first change order | Undefined. Strategize with management prior to first change order | Undefined. Strategize with management prior to first change order |  | If adverse weather conditions are the basis for a Claim for additional time, such Claim shall be documented by data substantiating that weather conditions were abnormal for the period of time, could not have been reasonably anticipated and had an adverse effect on the scheduled construction. No Claim based on weather delays shall be permitted in the event that portions of the Work continue during the adverse weather conditions. | 10 Calendar days | Not Provided for in prime agreement |  | Promptly following the date hereof, Contractor shall prepare and submit for Owner’s Designated Representative’s and Design Professional’s information a Contractor’s construction schedule for the Work. The schedule shall not exceed time limits currently set forth in the Contract Documents, shall be revised at appropriate intervals as required by the conditions of the Work and Project and as specifically set forth in the Contract Documents, shall be related to the entire Project to the extent required by the Contract Documents, and shall provide for expeditious and practicable execution of the Work. |  | Contractor shall provide monthly written reports to Owner’s Designated Representative and Design Professional on the progress of the entire Work on the Project. Contractor shall maintain a daily log containing Subcontractors working on the Project Site, number of workers, insurance requirements compliance, Work accomplished, accidents, claims and problems encountered and other similar relevant data as the Owner may reasonably require. The log shall be available to the Owner, Owner’s Designated Representative, Owner’s lenders and their agents and Design Professional for review, copying and audit at all reasonable times. |  | If Contractor is delayed at any time in the commencement or progress of the Work by an act or neglect of Owner or Design Professional, or of an employee of either, or of a separate contractor employed by Owner, or by changes ordered in the Work, or by labor disputes, fire, unusual delay in deliveries, unavoidable casualties or other causes beyond Contractor's control, or by delay authorized by Owner pending mediation and arbitration, or by other causes which Design Professional determines may justify delay, then the Contract Time (and, if necessary, the Master Project Schedule) shall be extended by Change Order to the extent any such delay will prevent Contractor from achieving Substantial Completion within the Contract Time and if the performance of the Work is not, was not, or would not have been delayed by any other concurrent cause for which Contractor is not entitled to an extension in the Contract Time under the Contract Documents. Contractor further acknowledges and agrees that adjustments in the Contract Time and/or Master Project Schedule will be permitted for a delay only to the extent such delay (i) is not caused, or could not have been, in the exercise of reasonable diligence, prevented by Contractor, (ii) could not be limited or avoided by Contractor’s timely notice to Owner of the delay or reasonable likelihood that a delay will occur, and (iii) is of a duration not less than one (1) day. | 10 calendar days |  | 14.10.5 In the event Owner determines that the performance of the Work has not progressed or reached the level of completion required by the Contract Documents, Owner shall have the right to order Contractor to take corrective measures necessary to expedite the progress of construction, including, without limitation, (i) working additional shifts or overtime, (ii) supplying additional manpower, equipment, and facilities, and (iii) other similar measures (hereinafter referred to collectively as “Extraordinary Measures”). Such Extraordinary Measures shall continue until the progress of the Work complies with the stage of completion required by the Contract Documents. Owner’s right to require Extraordinary Measures is solely for the purpose of ensuring Contractor’s compliance with the Master Project Schedule. 14.10.5.1Contractor shall not be entitled to an adjustment in the Contract Sum in connection with Extraordinary Measures required by Owner under or pursuant to this Subsection 14.10.5 or the remaining Contract Documents. 14.10.5.2 Owner may exercise the rights furnished Owner under or pursuant to this Section 14.10.5 as frequently as Owner deems necessary to ensure that Contractor’s performance of the Work will comply with any milestone date or completion date set forth in the Contract Documents. | calendar | 2.2 | 2.2.1.2 Subject to adjustments of the Contract Time and/or Master Project Schedule (as defined in Section 14.10.3 of the General Conditions) as provided in the Contract Documents, Contractor shall achieve Substantial Completion of the entire Work no later than two hundred twenty five (225) days from the Notice to Proceed, time being of the essence. 2.2.1.3 Remedy for Failure to Keep Schedule. In the event that Contractor does not timely achieve Substantial Completion in accordance with the Schedule, then Contractor shall pay to Owner (or Owner may withhold from payments to Contractor) as liquidated damages but not as a penalty Two Thousand Dollars ($2,000) for each day of such delay, capped at half (1/2) the Contract Sum with a thirty (30) day grace period. Contractor understands that, if Contractor does not timely achieve Substantial Completion, Owner will suffer substantial damages, including the loss of rent, administrative charges and other operating and construction costs and charges. Contractor also acknowledges that the amount of actual damages that Owner suffers in such an event will be difficult to calculate, and that the amount of the liquidated damages is a reasonable estimate of those damages. | not defined | not defined | No | NA | 5 | 10% | 5.1.11 | Reduced to 5% retainage at 50% | No | No |  | May be allowed if previously approved by owner. | 45 | 5.3 | Contractor covenants and agrees to pay, currently as they become due and payable in accordance with the terms of the respective agreements between the parties, all bills for labor, materials, insurance, and all fees of Subcontractors, Sub-subcontractors, material or equipment suppliers and consultants and all other costs and expenses incident to any performance of the Work or any part thereof; provided, however, that subject to the requirements of the respective agreements between the parties, Contractor may, in good faith, dispute and contest any such bill, fee, cost or expense and, in such event, any such item need not be paid until adjudged to be valid. In the event Contractor elects to contest or dispute such item, Contractor shall notify Owner’s Designated Representative of the nature and amount of such dispute. No Application for Payment shall include, and Owner shall not be required to pay, any disputed amount until such dispute or discrepancy has been resolved. Notwithstanding the foregoing, in all events payment shall be made in the manner and within the time prescribed by Law, including, without limitation the Pennsylvania Prompt Payment Act 62 Pa.C.S.A. § 3901, et. seq. | 7 | 8 | Not provided for in contract | Not provided for in contract | [5 empty] | The one (1)-year period for correction of Work shall commence upon final completion regardless of the date of actual performance of the Work. |  | due within 30 days of substantial completion. | 5.2 | Final payment shall be made by Owner to Contractor when (1) the Contract Documents have been fully performed by Contractor (excluding any obligation of Contractor to correct nonconforming Work, as provided in Section 23.2 of the General Conditions, and any obligation of Contractor to satisfy other requirements, if any, which necessarily survive final payment); (2) a final Application for Payment and a final accounting for the Contract Sum have been submitted by Contractor and reviewed by Owner’s accountants; (3) all operational manuals, warranties and other documents have been turned over to Owner; and (4) a final Certificate for Payment has been issued by the Design Professional. |  | If conditions are encountered at the Project Site that are (1) subsurface or otherwise concealed physical conditions which differ materially from those indicated in the Contract Documents; or (2) unknown physical conditions of an unusual nature that differ materially from those ordinarily found to exist and generally recognized as inherent in construction activities of the character provided for in the Contract Documents and, in each instance, could not have been foreseen with reasonable investigation by Contractor, then Contractor shall provide notice to Owner’s Designated Representative promptly before conditions are disturbed and in no event later than ten (10) days after the first observance of the conditions. Owner’s Designated Representative will promptly investigate such conditions and, if they differ materially and cause an increase or decrease in Contractor’s cost of, or time required for, performance of any part of the Work, will recommend an equitable adjustment in the Contract Sum, the Contract Time, the Master Project Schedule, or all. If Owner’s Designated Representative determines that the conditions at the Project Site are not materially different from those indicated in the Contract Documents and that no change in the terms of the Contract Documents is justified, Owner’s Designated Representative shall so notify Owner and Contractor in writing, stating the reasons. No adjustment in the Master Project Schedule, Contract Time or Contract Sum shall be permitted, however, in connection with a concealed or unknown condition that does not differ materially from those conditions disclosed or that reasonably should have been disclosed by Contractor’s (i) prior inspections, tests, reviews, and preconstruction services for the Project, or (ii) inspections, tests, reviews, and preconstruction services that Contractor had the opportunity to make or should have performed in connection with the Project. | 10 days | Weekly issues update captured in OAC meeting minutes. Monthly reports including financial, schedule and an overall project executive | Yes |  | Yes | Yes | Union | No | Exhibit A Project Description Exhibit B General Conditions Exhibit C Description of Contractor’s Services Schedule I Drawings Schedule II Specifications Schedule III Supplementary and Other Conditions | No |  | NA | Not provided in executed contract
12 | 12 | 2023-10-30 | Custom Contract | Guarantee Maximum Price (Custom Contract) | No | Article 4.10 - Contractor and Owner waive claims against each other for Consequential Damages. | Yes | Yes | Article 4.9 - $2,000/day after a 14 cure period from the date of substantial completion. LD's are capped at 50% of Contractor's Fee. |  | Excluded | Owner | N/A | N/A | TBD | Maybe | No | No | No |  | Article 13.4 - If Contractor elects not to use SDI, a P&P bond is required for all subcontractors over a $1mm. |  | Reference Article 1.1 |  | Article 3.4.2 - Contractor has reviewed all documents as identified in 1.1.2. |  | Not Specified but alternates & substitutions are permitting. Contractor shall submit product data and costs adjustments for approval. | No | No |  | Original precon was a NTE of $345,352. Additional precon costs were included in the GMP Submission to cover overage. |  | Yes | Not indicated |  | Yes | Yes | Yes |  | None, all savings is returned to the owner. |  | Yes | No | Article 7.4 - Buyout savings is the aggregate between the initial value (prior to CO's) of commitments and the corresponding GMP trade value. | Yes | Exhibit D | 2023 |  | Article 8 - Costs necessary incurred in the proper performance of the work and paid by the Contractor. Such costs shall be actual costs and shall be at rates per Exhibit C and not higher than the standard paid in the locality of the work........The costs of work shall be reimbursed to the contractor, subject to the GMP price. |  |  | Article 7 - Monthly detailed report of usage | Other | Provided detailed listing of hours and rates | Yes | Exhibit C | Exhibit A - Article N - 15% | 15% | 3% | N/A - Excluded | Not identified | Can be included on case by case basis. | Not identified | SDI @ 1.2% |  | Silent on weather days | Silent on notification to adverse weather delays | Silent on weather days |  | Reference Article 4 - Substantial completion shall be achieved per GMP Schedule milestone. |  | Silent on Daily Log & Manpower T&C's |  | Reference Article 4.5 through 4.7 4.5 - Delay force majeure 4.6 - Cost & Mitigation of contractor delays 4.7 - Owner Delays | N/A |  | N/A | Does not identify | Article 4.1 | Article 4.1 - Obtain substantial completion per the GMP Amendment #2 schedule | Article 4.2 | Article 4.2 - Achieve within (90) days after Substantial Completion | No | N/A | Article 11 | 10% until 50% of work complete. | Article 11.3.1 | Article 11.3.2 - Owner to provide consideration to early release of retainage. | No | No |  | N/A | 30 calendar days following the approval of App for Payment | N/A | N/A | Article 12.2 Claims & Disputes | Article 14 Termination | 7 calendar day notice | 7 calendar day notice | [5 empty] | Article 15.10 Warranty - 1 year from Substantial Completion |  | At end of project, the Contractor shall turn-over one (1) complete set of asbuilts. | Article 11.4 | (30) days after acceptance of certificate of final completion by Architect. |  | Article 7 permits the use of Contingency, Allowances and Buyout Savings to fund for concealed and unknown items. | Article 12.2.6 - (5) days after found | Cost Reports Project Reports (Monthly Report) | No |  | Yes | Yes | Non-Union | Yes | Exhibit A - GMP Amendment Exhibit B - Contractor's Scope of Work Exhibit C - Contractor's Guaranteed Maximum Price Proposal Exhibit D - Owner Change Order Request Document Exhibit E - Owner Change Order Document Exhibit F - Request for Substitution Exhibit G - Field Work Authorization Form Exhibit H - Contractor's Progress Payment Cert & Waiver of Claims and Liens Exhibit H2 - Contractor's Final Payment Cert & Waivers of Claims and Liens Exhibit H3 - Subcontractor's Progress Payment Cert & Waivers of Claims and Liens Exhibit H4 - Subcontractor's Final Payment Cert & Waivers of Claims and Liens Exhibit I - Subcontractor Performance Bond Exhibit I2 - Subcontractor Labor and Material Payment Bond Exhibit I3 - Dual Obligee Rider for Subcontract Surety Bonds Exhibit J - Certificate of Final Completion Exhibit K - Contractor's Warranty Certificate Exhibit L - Project Description - Not used Exhibit M - Legal Description of Site - Not used Exhibit N - Key Owners Consultants - Exhibit O - Project Schedule Exhibit P - Contractor's Org Chart Exhibit Q - Contractor's PreCon Cost Proposal Exhibit R - Contractor's Construction Cost Proposal Exhibit S - Contractor's Markup on Changes Exhibit T - Not Used Exhibit U - Not Used Exhibit V - Not Used Exhibit W - Reference Documents Exhibit X - Not Used Exhibit Y - Not Used | No |  | N/A | Article 13.3 - Owner
22 | 17 | 2024-08-29 | Custom Contract | GMP | No | N/A | Yes | No | $2,500/day capped at 1/2 fee with a 30-day grace period - Article 4.10 |  | 2.5% | IMC | 0.6% | $5K dollar deductible for all perils with the exception of earthquake and flood which is $25K | Builder's Risk provided by IMC | Yes | No | No | Maybe |  | Contractor shall, promptly after Owner’s request, furnish a payment and performance bond (the “Payment and Performance Bond”) to Owner. If Owner makes such request after the GMP Date, such request shall be the subject of a Change Order under the provisions of Article 6 - Article 5.17 |  | "“Contract Documents” means this Agreement (including all exhibits attached hereto), the Design Documents, and the other documents (if any) listed on Exhibit D, which Exhibit D shall be incorporated herein when the GMP Amendment is executed, and the OCIP Insurance Manual, if applicable." - Article 1.21 |  | Review of Contract Documents and Field Conditions. Contractor shall take field measurements and verify field conditions and shall carefully compare such field conditions and other information known to Contractor with the Contract Documents promptly after Contractor receives the Contract Documents, and in any event before commencing activities. Contractor shall promptly notify Owner if Contractor becomes aware of any defect or deficiency in any Contract Documents. Contractor shall perform the Work in accordance with the Contract Documents. Contractors review of the Contract Documents is in Contractor’s role as a General Contractor and not as a design peer reviewer. Contractor’s shall not be responsible for errors, omissions, inconsistencies, and conflicts in Contract Documents unless Contractor knew and failed to notify Owner of such item. - Article 2.4.c |  | Submittal Alternates & Substitutions: Specification Section 012500 - C Substitution Procedures Contract Document Deviations - Article 2.13.c | Yes | Yes |  | $2,500 fee per estimate proposal. Initial agreement contained three estimates: Concept, Schematic, and DD. |  | Yes | Contractor shall solicit, and use all reasonable efforts to obtain, not less than three (3) competitive proposals or bids from qualified and experienced firms reasonably approved by Owner for such Work - Article 8.1.c.iv |  | Yes | Yes | Yes |  | None |  | Yes | No | Not identified | Yes | ERP#1 Appendix G | 2024 |  | The term “Cost of the Work” means costs that are both (a) properly incurred by Contractor in the proper performance of the Work, as the scope of which may be adjusted pursuant to this Agreement, (b) expressly described in this Section 1 of this Exhibit E and (c) no higher than those standard in the Philadelphia, Pennsylvania area per the rates set forth in the GMP Amendment. - Exhibit E |  | Contractor and Owner acknowledge that the GMP (and each iteration of the Schedule of Values) shall contain a line item for “Contingency.” Upon completion of a line item on the Schedule of Values, such Contingency shall be increased by amounts not expended on such line item. Any Contingency remaining after Substantial Completion shall be retained by Owner. - Article 5.14.a | The Contingency may be used (and/or allocated to any other item on the Schedule of Values) only with Owner’s prior written approval. - Article 5.14.b | Reimbursable | With each payment application, Payment Contractor shall submit (i) such evidence as may be customary (including printouts showing payrolls and petty cash accounts, and receipted invoices), and such evidence as may be reasonably required by Owner, to demonstrate costs incurred or estimated to be incurred on account of the Work during such month and the percentage of completion (as calculated in accordance with Section 5.3(b)) of each category of Work reasonably estimated to the end of the month of the submission of such Application for Payment - Article 5.3.a | Yes | Not identified | 10% Overhead, 5% Profit - Article 6.6.d | 5% - Article 6.6.e | 5% - Article 6.5 | 2.5% | 0.1% | Not identified | 1% | 1.0%, if required. |  | "Severe Weather Conditions” means weather conditions that are materially worse than those that reasonably would be anticipated for the Site at the applicable time based on historic meteorological records. - Article 1.66 | 5 days - Article 4.6.G | None - interior renovation. |  | Article 2.6.F & Article 4.2 |  | Not identified |  | Article 4.6 Delays | 5 days - Article 4.6.G |  | Acceleration. Owner may, at any time, request that Contractor provide a plan for accelerating the Work. Within seven (7) days of receipt of a request therefor, Contractor shall submit to Owner the following, and any additional materials that Owner may reasonably require to evaluate the necessity or desirability of accelerating the Work beyond the current Schedule: (a) Accelerated Schedule; and (b) Revised GMP detailing anticipated costs to Owner related to such acceleration, along with a summary demonstrating such costs. Such plan shall be deemed a Change Order proposal prepared by Contractor. - Article 4.9 | "Business Day” or “Business Days” means Days other than (i) weekend Days, or (ii) national or local holidays in which federal government agencies in the County are closed for business. " - Article 1.7 | 1.73, 5.10 | “Substantial Completion” means the stage in the progress of the Work when (a) the Work or designated portion thereof (i) has been completed in accordance herewith, except for Punchlist Items shown on a punchlist that has been prepared by Contractor and approved in writing by Owner, and (ii) is sufficiently complete in accordance with the Contract Documents so that it may be used by Owner or its Tenant(s) for its intended purpose, and (b) Owner has received (i) a certificate of occupancy or temporary certificate of occupancy for the Work, or such portion thereof, and (ii) the Certificate of Substantial Completion from Designer and (c) the cost to complete all remaining items will not exceed [$TBD]; provided, however, with respect to any portion of the Work that is less than all of the Work, that Substantial Completion shall not require the delivery of the item(s) listed in Subsection (b)(i) of this definition. - Article 1.73 | 1.34 & 5.12 | “Final Completion” means the point at which the Work has been completed in accordance with the terms and conditions of the Contract Documents, including the Punchlist Items. - Article 1.34 | No | None | Progress (5.3.a) & Final (5.12) | 10% - Article 5.5.b | 5.5.c | Early Retainage Release. If a Subcontractor has completed its portion of the Work (including all Punchlist Items) pursuant to any given Subcontract, Contractor may request Owner to disburse such Subcontractor’s retainage, after delivering to Owner any necessary consent to such disbursement from such Subcontractor’s surety, in a form reasonably satisfactory to Owner. If Owner is satisfied that such Subcontractor’s Work has been completed in accordance with the Contract Documents and, unless prohibited by Applicable Law, Owner has received a conditional waiver and release on final payment from such Subcontractor (conditioned only upon the payment of an amount equal to such Subcontractor’s retainage) and in the applicable form attached as Exhibit L hereto (with modifications to comply with Applicable Law if requested by Owner), as well as a conditional waiver and release on final payment from all of such Subcontractor’s Subcontractors and completed in a manner reasonably acceptable to Owner, then Owner shall disburse such Subcontractor’s retainage. Disbursing any Subcontractor’s retainage will not accelerate the beginning or end of the Correction Period. - Article 5.5.c | No | No |  | Payment for On-Site and Off-Site Stored Materials. Unless otherwise agreed in writing, Owner shall make payment only on account of materials and equipment purchased by Contractor for installation and incorporation into the Work when such materials have been installed or when they are needed to maintain the sequence of the Work and have been delivered to and safely stored and protected at the Site or at an off-Site location approved in advance and in writing by Owner. Payment for materials and equipment stored on or off the Site shall be conditioned upon compliance by Contractor with procedures reasonably satisfactory to Owner to establish Owner’s title to such materials and equipment or otherwise protect Owner’s interest therein and to provide Owner with a perfected security interest in such materials or equipment to the extent Owner’s title in such materials or equipment is deemed to create a security interest or is otherwise insufficient to secure Owner’s absolute right and title to such materials and equipment, and shall include applicable insurance, storage and transportation to the Site for such materials and equipment stored off the Site. Title to such materials stored off-Site shall pass to Owner upon payment therefor; provided, however, that Contractor shall bear the risk of loss of such materials at all times while such materials are stored off-Site and during transportation to the Site, and Contractor shall be responsible for the proper care, storage, preservation, insurance and protection of all such materials. Materials stored off-Site shall be appropriately tagged and segregated in order to further protect Owner’s interest therein prior to delivery thereof to the Site. Contractor hereby absolutely and unconditionally guarantees to Owner delivery of all materials stored off-Site as aforesaid, free and clear of all liens and encumbrances, and Contractor shall save, indemnify, defend (at Owner’s option and with counsel reasonably acceptable to Owner) and hold Owner harmless from and against all Claims arising or resulting, directly or indirectly, from such storage of materials off-Site or from the failure of any such Subcontractor, materialman or supplier to deliver such materials to Owner as and when called for by Owner or Contractor. - Article 5.6 | Contractor shall deliver to Owner, at an address (which may be an e-mail address) specified by Owner, a written invoice (the “Application for Payment”) on or before the fifth (5th) Day of each month describing in reasonable detail all Work (and covering the Cost of the Work and Fee applicable to the Work) performed by Contractor during the previous month. Provided the Application for Payment and all other documentation required under the Contract Documents to be delivered concurrently are timely delivered to Owner, Owner shall make payment of amounts due to Contractor not later than the final Day of the month. " | 5.9 | Failure of Payment; Interest. If (a) Owner does not pay Contractor within ten (10) Days after the date established herein the amount set forth in the Application for Payment or (b)(i) Owner does not notify Contractor (which notification may be by email without the requirement of other methods of delivery of notice) within such ten (10) day period that Owner believes in good faith that a portion of such amount is not due in accordance with the provisions hereof and (ii) Owner does not pay such lesser amount as Owner claims in good faith is due in accordance with the provisions hereof, then Contractor may, upon ten (10) additional Days’ written notice to Owner, stop the Work for which Owner does not dispute that payment is owed to Contractor until payment of such undisputed amount owing has been received. The Schedule and GMP shall be equitably adjusted on account of such stoppage, including compensation for shutdown, delay and start-up. In addition, all amounts due and unpaid shall bear interest from the date payment is due until paid at the prime rate in effect from time to time as stated in Money Rates section of the Wall Street Journal. - Article 5.9 | 11.2 | 12.6 | No notice for convenience - Article 12.6.a | 5 days - Article 12.1 | [5 empty] | Warranty. Contractor warrants to Owner that any and all materials, equipment and furnishings incorporated into the Work shall be of good quality and new unless otherwise required or permitted by this Agreement, that the Work shall be free from defects and that the Work shall conform with the requirements of the Contract Documents, including Section 2.2 of this Agreement. Work not conforming to these requirements, including substitutions not properly approved and authorized, shall be considered defective. The foregoing warranty excludes (a) damage or defect occurring after Substantial Completion and caused by abuse, modifications not executed by Contractor, improper or insufficient maintenance, or improper operation and (b) normal wear and tear under normal usage occurring after Substantial Completion. Contractor hereby assigns to Owner any and all manufacturers’ and suppliers’ warranties relating to materials, machinery or equipment used in the Work, and shall perform the Work in such manner as to preserve such warranties. Contractor shall also maintain a comprehensive list and file of all warranties given by Subcontractors and other entities in connection with the Work, and shall provide to Owner upon request, but in no event later than the date of Final Completion. Notwithstanding any other provision of this Agreement, including Sections 14.3 and 14.4, Owner may assign all warranty and correction obligations of Contractor under this Agreement to other entities. - Article 2.7 |  | Documents and Samples at the Site. From and after commencement of the Work, Contractor shall maintain at the Site one record copy of the Contract Documents, and any and all amendments thereto, in good order and marked to record changes and selections made. In addition, Contractor shall maintain at the Site approved Shop Drawings, Product Data, Samples and similar required submittals (“Submittals”). These shall be provided to Owner within a reasonable time after Final Completion. - Article 2.13.a | 5.12 | Conditions Precedent to Final Payment. Neither final payment nor any final release of Retainage shall become due until (i) Final Completion has occurred, (ii) Owner has had thirty (30) Days to audit Contractor’s books and records in accordance with Section 14.13, (iii) Contractor has completed and submitted to Owner a close-out checklist in a form reasonably acceptable to Owner and cooperated with Owner to effect the closing out of the Work, (iv) the requirements of any Financing Entity regarding final completion have been satisfied (provided, however, that to the extent Contractor was not informed in writing prior the execution of this Agreement of a Financing Entity’s requirement, Contractor shall only be required to comply with such requirement to the extent such compliance is within the reasonable control of Contractor and is at no additional cost to Contractor unless Owner agrees to increase the GMP to cover such cost),, and (v) Contractor submits to Owner: - Article 5.12.b |  | Article 2.3.b & Excusable Delays | 10 days per 2.3.a, 5 days notice for Excusable Delays | Monthly Report - Article 2.6.f | Yes |  | Yes | Yes | Union | Yes | Exhibit A Scope of Work and Project Description Exhibit B Construction Allowance Items [To be added in GMP Amendment] Exhibit C Site Description Exhibit D List of Contract Documents [To be added in GMP Amendment] Exhibit E Cost of the Work Exhibit F GMP (Including Schedule) [To be added in GMP Amendment] Exhibit G Designation of Authorized Representatives Exhibit H Index of Key Personnel Exhibit I Contractor’s Insurance Requirements Exhibit J Form of Subcontract Exhibit K Scheduling Requirements [To be added in GMP Amendment] Exhibit L Forms of Lien Waivers Exhibit M LEED Requirements – N/A Exhibit N License Area ERP#1 ERP#1 Exhibit D Contract Documents ERP#1 Exhibit F Early Release GMP and Schedule ERP#1 Exhibit K Scheduling Requirements | No |  | Not identified | If the Builder's Risk insurance requires deductibles, the Owner shall pay costs not covered because of such deductibles, unless the Loss arises from the acts or omissions of Contractor or Subcontractor(s), in which case the culpable party or parties shall pay the deductible subject to a maximum deductible equal to the greater of: (1) the available limits of insurance or (2) ($150,000) - Article 1.6
13 | 18 | 2025-01-29 | Custom Contract | GMP | No | any costs incurred by the owner to achieve final completion | No | No | NA |  | 1 | Owner | NA | 100000 | D | Yes | No | Yes | No |  | NA |  | Task Order, Master Service Agreement, and all other contract docs in the task order or master agreement |  | Contractor responsible for doc review and reporting errors to design team immediately. reporting errors doesn't release contractor for responsibility of cost associated with errors but contractor is not responsible for design document code compliance in any way. |  | Must be documented via change order per 3.4.2 of master service agreement | Yes | No |  | $5,000 lump sum |  | No | NA |  | No | No | Yes |  | No shared savings |  | No | No | 100% of buyout savings returns to owner if not used during project. | No | I-7 | 2024 |  | Task Order Exhibit I - wages of workers, contractor's supervisory and admin personnel per exhibit J, taxes, insurance, subcontractor cost, transportation and storage cost, cost of materials, rental equipment, temp facilities, debris removal, contractor expenses, permit fees, testing fees, deposits lost, cost incurred due to emergencies |  | Requires owner approval | Must obtain owner approval before utilizing | Capped | Back up required for GR's | Yes | IMC labor plus IMC staff expenses | 10 | 5 subcontractor 5 tiered subcontractor (aggregate 10%) | 3 | 1 | 0.1 | NA | 1 | NA |  | MSA 4.3.7.2 (1) extreme or unusual compared to prior 10 year weather data (2) must have actually caused subcontractor to not work (3) claim must be substantiated by weather data (4) only applicable if delay will delay substantial completion (5) claim must be submitted within 5 cal days (6) must be submitted to owner by the end of the calendar month following the month with adverse weather conditions. | 5 | 0 |  | identify critical path and deadlines for submittals on the critical path |  | required starting on project commencement including subs names, number of workers, area working in. contractor to submit weekly to client (on monday for prior week) |  | definition of unavoidable delay is provided, avoidable delay is contractor's responsibility, owner can notice failure of meeting critical path schedule. Contractor must respond with cure within 7 days of receiving notice of failure. | 10 |  | contractor to accelerate at contractors cost. Contractor can use contingency or unused monies in GMP, if applicable. if not, cost is responsibility of contractor. | Cal | 9.8 | TCO, owner can occupy without major interference of uncompleted work, remaining work is certified to be completed within 30 days by contractor. | 9.10 | 1. Contract performed 2. work completed 3. final app certified by owner/arch 4. contract docs completed | No | NA | 9.6 (progress) and 9.10 (final) | 10 | 9.6 (progress) and 9.10 (final) | 10% until SC | No | No |  | requires owner prior approval | 45 | 9.7 | 30 days after written notice of late payment | 4.6 | 14 | 0 | 10 | [5 empty] | 1 year after substantial completed unless noted otherwise in contract documents. |  | required for submission prior to SC. 2 copies provided to owner | 9.10 | arch to certify. final sub waivers. insurance verification during period required in contract documents |  | Arch to certify. if in agreement time and cost is adjusted. If not, contractor to file claim | 5 | monthly notification of lien claimants | Yes |  | Yes | Yes | Non-Union | Yes | A - drawings and specs B - allowances and alternates C - project schedule D - insurance provisions E - schedule of certain indemnitees F - schedule of values G - compensation for construction change directives H - subcontractor default insurance I - cost of work J - contractor's approved staffing plan K - key personnel L - BIM requirements (NA) M - safety requirements and contractors manual X - CHOP credential requirements | No |  | NA | Owner
14 | 21 | 2025-04-30 | A102 - GMP Cost Plus Fee | N/A | No | na | Yes | Yes | 5k per day between target substantial completion date and the date that substantial completion is achieved. takes into account (30) day grace period. LDs assessed pursuant to this agreement shall be capped a Contractor's fee. |  | 2.5 | Owner | na | na | Owner | Yes | No | Yes | No |  | na |  | "ARTICLE 1 THE CONTRACT DOCUMENTS The Contract Documents consist of this Agreement, Conditions of the Contract (General, Supplementary and other Conditions), Drawings, Specifications, Addenda issued prior to execution of this Agreement, other documents listed in this Agreement and Modifications issued after execution of this Agreement, all of which form the Contract, and are as fully a part of the Contract as if attached to this Agreement or repeated herein. The Contract represents the entire and integrated agreement between the parties hereto and supersedes prior negotiations, representations or agreements, either written or oral. As of the date of this Agreement, the Contract Documents consist of those documents referenced in Section 16 below." |  | 3.2.2 |  | If the Contractor desires to substitute a product or method in lieu of what has been specified or shown in the Contract Documents. The Contractor may propose to do so in a written request delivered to the Architect and the Owner setting forth the following: (see 3.4.2) | No | No |  | Exhibit 5.2.4 #36 Preconstruction Services costs not to exceed 90k are assumed to be funded from within the GMP amount. |  | Yes | 3 |  | Yes | Yes | Yes |  | 100% to the Owner |  | Yes | Yes | 5.3 As the "buyout" process is completed in accordance with Articles 7 and 10 herein and any other applicable provisions of the Contract Documents, the Schedule of Values shall be revised and the actual costs associated with the line items in the original Schedule of Values attached hereto shall be incorporated into such revised Schedule of Values. At the time when subcontracts have been awarded for the Work of all subcontracted Work in the initial Schedule of Values have been procured by the time set forth in Section 10.1, any net savings between the estimated costs as reflected in the original schedule of values and the actual Subcontractor and supplier award amounts resulting from the buyout process shall be transferred to the Contingency line item. | Yes | Exhibit 7.1.1 | 2025 |  | 7.1.1 The term Cost of the Work shall mean costs necessarily incurred by the Contractor in the proper performance of the Work. |  | 5.1.7.2 The Guaranteed Maximum Price shall include a Contingency in the amount of $377,541 as shown in the initial Schedule of Values attached hereto. Contingency shall be used by the Contractor to cover unanticipated expenses which are necessary to complete the Work and for which the Contractor is not entitled to a Change Order; provided, however, that notwithstanding anything to the contrary herein, in no event shall Contingency be used for the costs of correcting non-conforming or defective Work or costs arising from the gross negligence or willful misconduct of the Contractor or its Subcontractors... | 5.1.7.2 ... The Contractor shall notify he Owner of costs that the Contractor proposes to charge to the Contingency, together with an explanation of the reason such costs are to be incurred, prior to incurring such costs. Any use of Contingency totaling $25,000 or more shall be subject to the prior written consent of the Owner which shall not be unreasonably withheld. In no event shall Contractor be entitled to use more than one hundred twenty thousand ($120,000) of Contingency fund for General Conditions Cost items. | Capped | Add earned portion of the General Conditions Costs Amount (the parties agreeing that no retainage shall be applied to the General Conditions Amount) | Yes | 0 1 - See Exhibit 7.1.1 | 10% | The aggregate amount of markups for overhead and profit for Subcontractors, regardless of the number of tiers of Subcontractors, shall not exceed 15% of actual cost. | 2.75 | 2.5 | 0.10 | See 7.3.3A | 1 | na |  | See 8.3.3 | See 15.1.2 - Within 21 days of event | See 8.3.3 - NOAA ten-year avg. |  | See 4.3 |  | na |  | 8.3.1 | within 21 days |  | na | Calendar days unless otherwise specified. | 9.8.1 | See 9.8.1 | 9.10.1 | To the best of the Architect's and the Owner's knowledge, information and belief, and on the basis of the Architect's and Owner's on-site visits And inspections, the Work has been completed in accordance with the terms and condictions of the Contract Documents and that the entire balance found to be due to the Contractor and noted in the final Certificate is due and payable. | Yes | Model units | 21.1 | 10%; Upon 50% completion of the Work, retainage shall be reduced to 5% | 12.1.8.2 | See 12.1.8 | Yes | Yes |  | See 9.3.2 | 30 days | 9.7. | See 9.7. | 15.3 | Article 14 | See 14.3 - At any time | See 14.2 - 3 days | [5 empty] | See 3.5.1 |  | See 3.11.1 - Maintain a record set of plans at the site with all deviations from Drawings and Specifications. | 9.10. | See 9.10.2 |  | See 10.3 | See 10.3.2 - Upon written notice. | Schedule, RFI Log, Submittal Log, Change Order Log, Project Narrative | Yes |  |  | Yes |  |  | Exhibit 3.1 Accepted Value Engineering Items (3.1); Exhibit 3.2 Contractor's Project Team (3.2); Exhibit 4.3-1 Project Schedule (4.3); Exhibit 4.3-2 Model Units (4.3); Exhibit 5.1.5 Unit Prices (5.1.5); Exhibit 5.2.1 Schedule of Values (5.2.1); Exhibit 5.2.2.1 Alternates (5.2.1); Exhibit 5.2.3 Allowances (5.2.3); Exhibit 5.2.4 (Qualifications/Assumptions (5.2.1, 5.2.4); Exhibit 7.1.1 General Condtions Costs (7.1.1); Exhibit 7.2.1 Schedule of Construction Worker Wages and Schedule of Contractor's Personnel included in the Cost of the Work (7.2.1, 7.2.2); Exhibit 10.5 Required Subcontract Provisions (10.5); Exhibit 15.7.5 Project Requirements (15.7.5); Exhibit 16.1.5 List of Drawings and Specifications (16.1.5); Exhibit 3.18.1 List of Indemnitees/Additonal Insureds; Exhibit 8.3.3 Example of Abnormal Weather Conditions; Exhibit 9.10.2.13 Training Protocol; Exhibit 11.1.1 Insurance Requirements; Schedule 1 CCIP manual |  |  | See 3.18.1 | Owner
23 | 26 | 2025-10-14 | A102 - GMP Cost Plus Fee | Cost of work plus a fee with guaranteed maximum price | No | N/A | Yes | Yes | Liquidated damages for delay paid to the owner, the sum of $500, for each calendar day after the date scheduled for substantial completion of the work until the contractor achieves substantial completion. |  | N/A | Owner | N/A | N/A | 11.3 | No | No | Yes | No |  | N/A |  | Drawing specification addenda issued prior to this agreement. |  | Contractor has visited site, generally familiar with local conditions under which the work is to be performed and correlated personal observations with requirements of the contract documents. |  | Except in the case of minor changes in the Work approved by the Architect in accordance with Section 3.12.8 or ordered by the Architect in accordance with Section 7.4, the Contractor may make substitutions only with the consent of the Owner, after evaluation by the Architect and in accordance with a Change Order or Construction Change Directive. | No | No |  | N/A |  | Yes | N/A |  | Yes | Yes | Yes |  | By submitting a Guaranteed Maximum Price proposal, the Construction Manager agrees that all buy out savings, discounts earned, unused allowances and other savings shall be returned to the Owner without sharing with the Construction Manager, unless the Owner agrees otherwise in writing. Savings shall be identified no later than in the final Application for Payment. |  | Yes | No | By submitting a Guaranteed Maximum Price proposal, the Construction Manager agrees that all buy out savings, discounts earned, unused allowances and other savings shall be returned to the Owner without sharing with the Construction Manager, unless the Owner agrees otherwise in writing. Savings shall be identified no later than in the final Application for Payment. | No | A.4 | 2025 |  | Cost of labor, cost of materials, cost of machinery/equipment, cost of bonds, insurance, taxes and permit fees, cost of supervision and field office personnel directly attributable to the cost. |  | The Construction Manager shall include a contingency for the Construction Manager’s exclusive use to cover those costs that are included in the Guaranteed Maximum Price but not otherwise allocated to another line item or included in a Change Order. | When the Construction Manager allocates costs from a contingency to another line item in the schedule of values, the Construction Manager shall submit supporting documentation to the Architect. | Capped | Full back up required. | Yes | UD Standard. | 10% | Aggregate 10% | 3% | N/A | N/A | N/A | 1% | N/A |  | If the Contractor is delayed at any time in the commencement or progress of the Work by adverse weather conditions documented in accordance with Section 15.1.6.2, or other causes beyond the Contractor’s control and the Architect determines, justify delay, then the Contract Time shall be extended for such reasonable time as the Architect may determine. | 21 days | 0 |  |  |  | The updated Project schedule shall include, in addition to activities which may be required by the Owner, the following: submission of the Guaranteed Maximum Price proposal; components of the Work; times of commencement and completion required of each Subcontractor; ordering and delivery of products, including those that must be ordered well in advance of construction; the occupancy requirements of the Owner; and the proposed date of Substantial and Final Completion. Updates shall be provided with each estimate of the Cost of the Work required by Section 3.1.6 below and whenever changes in the proposed Work or other conditions may materially alter the latest schedule. |  | The Construction Manager shall keep, and make available to the Owner and Architect, a daily log containing a record for each day of weather, portions of the Work in progress, number of workers on site, identification of equipment on site, problems that might affect progress of the work, accidents, injuries, and other information required by the Owner. | 21 days |  | The Construction Manager, in consultation with the Architect, shall provide recommendations with regard to accelerated or fast-track scheduling, procurement, and sequencing for phased construction. The Construction Manager shall take into consideration cost reductions, cost information, constructability, provisions for temporary facilities, and procurement and construction scheduling issues. | The term "day" as used in the Contract Documents shall mean calendar day unless otherwise specifically defined. | 2.3 | Subject to adjustments of contract time as provided in the contract documents, the construction manager shall achieve substantial completion of the entire work by agreed upon date in executed documents. If contractor fails, liquidated damages, if any, shall be assessed. | 9.10 | Upon receipt of the Contractor’s notice that the Work is ready for final inspection and acceptance and upon receipt of a final Application for Payment, the Architect will promptly make such inspection. When the Architect finds the Work acceptable under the Contract Documents and the Contract fully performed, the Architect will promptly issue a final Certificate for Payment stating that to the best of the Architect’s knowledge, information and belief, and on the basis of the Architect’s on-site visits and inspections, the Work has been completed in accordance with the Contract Documents and that the entire balance found to be due the Contractor and noted in the final Certificate is due and payable. | No | N/A | 11.1 and 11.2, respectively | 10% | 11.1.8 | There shall be no reduction of retainage until final payment. Upon Substantial Completion, the retainage may, with the Owner’s prior written approval, be reduced to five per cent (5%) with respect to particular Subcontractors. | Yes | Yes |  | If approved in advance by the Owner, payment may similarly be made for materials and equipment suitably stored off the site at a location agreed upon in writing. Payment for materials and equipment stored on or off the site shall be conditioned upon compliance by the Contractor with procedures satisfactory to the Owner to establish the Owner’s title to such materials and equipment or otherwise protect the Owner’s interest, and shall include the costs of applicable insurance, storage, and transportation to the site, for such materials and equipment stored off the site. | 30 days | 14.1.4 | If the Work is stopped for a period of 60 consecutive days through no act or fault of the Contractor, a Subcontractor, a Sub-subcontractor, or their agents or employees or any other persons or entities performing portions of the Work because the Owner has repeatedly failed to fulfill the Owner’s obligations under the Contract Documents with respect to matters important to the progress of the Work, the Contractor may, upon seven additional days’ notice to the Owner and the Architect, terminate the Contract and recover from the Owner as provided in Section 14.1.3. | 12.1 | 14.1 | 7 days | 7 days | [5 empty] | The Contractor warrants to the Owner and Architect that materials and equipment furnished under the Contract will be of good quality and new unless the Contract Documents require or permit otherwise. The Contractor further warrants that the Work will conform to the requirements of the Contract Documents and will be free from defects, except for those inherent in the quality of the Work the Contract Documents require or permit. Work, materials, or equipment not conforming to these requirements may be considered defective. The Contractor’s warranty excludes remedy for damage or defect caused by abuse, alterations to the Work not executed by the Contractor, improper or insufficient maintenance, improper operation, or normal wear and tear and normal usage. |  | The Contractor shall make available, at the Project site, the Contract Documents, including Change Orders, Construction Change Directives, and other Modifications, in good order and marked currently to indicate field changes and selections made during construction, and the approved Shop Drawings, Product Data, Samples, and similar required submittals. These shall be in electronic form or paper copy, available to the Architect and Owner, and delivered to the Architect for submittal to the Owner upon completion of the Work as a record of the Work as constructed. | 11.2 | Final payment, constituting the entire unpaid balance of the Contract Sum, shall be made by the Owner to the Construction Manager when the Construction Manager has fully performed the Contract, except for the Construction Manager’s responsibility to correct Work as provided in Article 12 of AIA Document A201–2017, and to satisfy other requirements, if any, which extend beyond final payment, the Construction Manager has submitted a final accounting for the Cost of the Work and a final Application for Payment, and a final Certificate for Payment has been issued by the Architect in accordance with Section 11.2.2.2. |  | Handling, removal, disposal, or capping of hazardous or contaminated materials is excluded. The Contractor is responsible for compliance with any requirements included in the Contract Documents regarding hazardous materials or substances. If the Contractor encounters a hazardous material or substance not addressed in the Contract Documents and if reasonable precautions will be inadequate to prevent foreseeable bodily injury or death to persons resulting from a material or substance, including but not limited to asbestos or polychlorinated biphenyl (PCB), encountered on the site by the Contractor, the Contractor shall, upon recognizing the condition, immediately stop Work in the affected area and notify the Owner and Architect of the condition. | 21 days | TAB Report, Commissioning Report | Yes |  | No | Yes | Prevailing Wage | No | 1 - General Provisions 2 - Owner 3 - Contractor 4 - Architect 5 - Subcontractor 6 - Construction by owner or by separate contractors 7 - Changes in the work 8 - Time 9 - Payments and Completion 10 - Protection of Persons and Property 11 - Insurance and Bonds 12 - Uncovering and Correction of Work 13 - Miscellaneous Provisions 14 - Termination or Suspension of the Contract 15 - Claims and Disputes | Yes |  | Optional insurance for cyber security to be purchased by owner. | Owner
22 | 22 | 2025-07-15 | A101 - Stipulated Sum | Lump Sum | No | § 15.1.7 Waiver of Claims for Consequential Damages The Contractor and Owner waive Claims against each other for consequential damages arising out of or relating to this Contract. This mutual waiver includes .1 damages incurred by the Owner for rental expenses, for losses of use, income, profit, financing, business and reputation, and for loss of management or employee productivity or of the services of such persons; and .2 damages incurred by the Contractor for principal office expenses including the compensation of personnel stationed there, for losses of financing, business and reputation, and for loss of profit, except anticipated profit arising directly from the Work. This mutual waiver is applicable, without limitation, to all consequential damages due to either party’s termination in accordance with Article 14. Nothing contained in this Section 15.1.7 shall be deemed to preclude assessment of liquidated damages, when applicable, in accordance with the requirements of the Contract Documents. | Yes | No | Section 6.1.6 deleted. |  | n/a | Owner | n/a | TBD (need to get a copy of the policy from Jaindl) | A2.3.1 The Owner shall provide the builders risk insurance policy to the Contractor evidencing coverage with the requirements in this Article A.2.3 at the following times: (1) prior to commencement of the Work; (2) upon renewal or replacement of each required policy of insurance; and (3) upon the Contractor’s written request. | Yes | No | Yes | Yes |  | excluded |  | ARTICLE 1 THE CONTRACT DOCUMENTS The Contract Documents consist of this Agreement, Conditions of the Contract (General, Supplementary, and other Conditions), Drawings, Specifications, Addenda issued prior to execution of this Agreement, other documents listed in this Agreement, and Modifications issued after execution of this Agreement, all of which form the Contract, and are as fully a part of the Contract as if attached to this Agreement or repeated herein. The Contract represents the entire and integrated agreement between the parties hereto and supersedes prior negotiations, representations, or agreements, either written or oral. An enumeration of the Contract Documents, other than a Modification, appears in Article 9. |  | 2.3.4 The Contractor shall review the surveys and reports provided by Owner using reasonable care and shall provide Owner with written notice of any anomalies discovered in the surveys and reports, if any. Except for those anomalies identified by Contractor, Contractor shall be entitled to rely upon the accuracy of the surveys and reports. THE INFORMATION IS AVAILABLE FOR REVIEW AND USE BY THE CONTRACTOR, BUT IS MADE AVAILABLE WITHOUT ANY WARRANTY OF ANY KIND, INCLUDING ACCURACY, ADEQUACY, FITNESS FOR A PARTICULAR PURPOSE, MERCHANTABILITY, OR PHYSICAL CONDITIONS. § 3.2.1 Execution of the Contract by the Contractor is a representation that the Contractor has reviewed the Contract Documents, has visited the site, become generally familiar with the nature and location of the Work, the conditions of the site as they exist based upon Contractor’s visual inspection of the site and its review of the surveys, reports and written information provided to Contractor by Owner, and, based upon Contractor’s visual inspection of the site and its review of the surveys, reports and written information provided to Contractor by Owner, the character of the operations to be carried out under the Contract Documents, including all existing site conditions, access to the site, physical characteristics of the site and immediate surrounding areas, all matters that could reasonably be expected to affect the Work, or its performance, and the time required for completion of the Work. The Contractor represents that it will abide by all applicable codes, ordinances, laws, regulations, and rules as they apply to the Work. Contractor shall not be entitled to claims for additional time or additional compensation because of the Contractor’s failure to familiarize itself with all local conditions reasonably expected to affect the Work or its performance, and the Contract Documents. § 3.2.2 Because the Contract Documents are complementary, the Contractor shall, before starting each portion of the Work, carefully study and compare the various Contract Documents relative to that portion of the Work, as well as the information furnished by the Owner pursuant to Section 2.3.4, shall take field measurements of any existing conditions related to that portion of the Work, and shall observe any conditions at the site affecting it. These obligations are for the purpose of facilitating coordination and construction by the Contractor and are not for the purpose of discovering errors, omissions, or inconsistencies in the Contract Documents; however, the Contractor shall promptly report to the Architect and Owner any errors, inconsistencies or omissions discovered by or made known to the Contractor as a request for information in such form as the Architect and/or Owner may reasonably require. It is recognized that the Contractor’s review is made in the Contractor’s capacity as a contractor and not as a licensed design professional, unless otherwise specifically provided in the Contract Documents. The accuracy of grades, elevations, dimensions, or locations of existing utilities is not guaranteed by the Architect or the Owner. The Contractor is responsible for verifying same. If the Contractor performs construction activity when the Contractor knows, or should know in the exercise of diligence as required by this subparagraph, that an activity involves an error, inconsistency, or omission in the accuracy of grades, elevations, dimensions, or locations of existing utilities, the Contractor shall assume appropriate responsibility for such performance and shall bear an appropriate amount of the costs attributable for correction. § 3.2.3 The Contractor is not required to ascertain that the Contract Documents are in accordance with applicable laws, statutes, ordinances, codes, rules and regulations, or lawful orders of public authorities, but the Contractor shall promptly report to the Owner and Architect any nonconformity discovered by or made known to the ContractorRFI |  | § 3.4.2 The Contractor may make substitutions only with the advance written consent of the Owner, after evaluation by the Architect and in accordance with a Change Order or Construction Change Directive. | No | No |  | n/a |  | No | n/a |  | Yes | No | Yes |  | n/a |  | No | No | n/a | No | Exhibit C | 2025 |  | n/a |  | n/a | n/a | Lump Sum | n/a | No | 01 | n/a | n/a | 5% | n/a | 0.1% | not stated in contract | 1% | 1% (but doesn't apply) |  | § 8.3.1 If the Contractor is materially delayed at any time in the commencement or progress of the Work by (1) an act or neglect of the Owner or Architect, of an employee of either, or of a Separate Contractor; (2) by changes ordered in the Work; (3) to the extent permitted by Section 8.3.1.1, by labor disputes, fire, unusual delay in deliveries, unavoidable casualties, adverse weather conditions documented in accordance with Section 15.1.6.2, or other causes beyond the Contractor’s reasonable control; (4) by delay authorized by the Owner; or (5) by other causes that the Contractor asserts, and the Architect reasonably determines, justify delay, then the Contract Time shall be extended for such reasonable time as the Owner and Contractor shall mutually determine with input from the Architect. § 15.1.6.2 If adverse weather conditions are the basis for a Claim for additional time, such Claim shall be made promptly following the date on which Contractor becomes aware that said weather conditions will delay the Contract Time, and shall be valid only to the extent documented by data substantiating that weather conditions were abnormal for the period of time, could not have been reasonably anticipated, and had a direct and adverse effect on the scheduled construction. | 5 days | Normal average |  | § 3.3.1 Subject to adjustments of the Contract Time as provided in the Contract Documents, the Contractor shall achieve Substantial Completion of the entire Work: Not later than Two Hundred Forty Seven (247) calendar days from the date of commencement of the Work. § 3.10.3 The Contractor shall perform the Work in general accordance with the most recent schedules submitted to the Owner and Architect. § 6.1.3 The Owner shall provide for coordination of the activities of the Owner’s own forces and of each Separate Contractor with the Work of the Contractor, who shall cooperate with them. The Contractor shall participate with any Separate Contractors and the Owner in reviewing their construction schedules. The Contractor shall make any revisions to its construction schedule deemed necessary after a joint review and mutual agreement. The construction schedules shall then constitute the schedules to be used by the Contractor, Separate Contractors, and the Owner until subsequently revised. |  | n/a |  | 13. Changes made, or delays caused in the field by utility companies or authorities having jurisdiction are excluded. § 8.2.1 Time limits stated in the Contract Documents are of the essence of the Contract. By executing the Agreement, the Contractor confirms that the Contract Time is a reasonable period for performing the Work. The Contractor shall notify Architect and Owner within 5 business days if the Contractor becomes aware of any material delay in performance of the Work and shall specify in writing to Owner the proposed revised performance dates as soon as practicable after notice of delay. § 8.3 Delays and Extensions of Time § 8.3.1 If the Contractor is materially delayed at any time in the commencement or progress of the Work by (1) an act or neglect of the Owner or Architect, of an employee of either, or of a Separate Contractor; (2) by changes ordered in the Work; (3) to the extent permitted by Section 8.3.1.1, by labor disputes, fire, unusual delay in deliveries, unavoidable casualties, adverse weather conditions documented in accordance with Section 15.1.6.2, or other causes beyond the Contractor’s reasonable control; (4) by delay authorized by the Owner; or (5) by other causes that the Contractor asserts, and the Architect reasonably determines, justify delay, then the Contract Time shall be extended for such reasonable time as the Owner and Contractor shall mutually determine with input from the Architect. § 8.3.1.1 The Contractor recognizes that delays or hindrances may occur. Except as set forth herein or Force Majeure Events as defined in Section 14.5.3 of the Agreement, no claims for increased costs, charges, expenses or damages of any kind, shall be made by the Contractor against the Owner for any delays, hindrances or sequencing of work from any cause whatsoever (excluding delays caused by Owner, its representatives, agents, Architect, or those acting at Owner’s direction) including but not limited to, strikes, walkouts, extended overhead, winter protection or work stoppages during the progress of any portion of the Work (“Non-Chargeable Delays”), notwithstanding whether such delays be avoidable or unavoidable. The Contractor's sole remedy for such Non-Chargeable Delays, shall be an extension of Contract Time or cost reimbursement, pursuant to and only in accordance with this Section 8.3. For each Non-Chargeable Delay of up to forty (40) days, and for an aggregate of ninety (90) Non-Chargeable Delays in total, Contractor shall have no claim for cost reimbursement. For Non-Chargeable Delays in excess of each instance and/or the aggregate provided in the preceding sentence, Contactor’s claim for cost reimbursement shall be capped at Twenty-Five Thousand Dollars ($25,000.00). All claims for extension of time or cost reimbursement for delays, acceleration, hindrances or sequencing of work shall be made, in writing, to the Owner no more than five (5) business days after the occurrence of the delay, acceleration or hindrance. A written request for an extension of time or cost reimbursement shall be a condition precedent to the Contractor’s right to claim an extension of time or cost reimbursement. Notwithstanding the foregoing, a delay or hindrance resulting from the Owner’s election or choice to suspend the Project for any reason shall not be considered a Non-Chargeable Delay and the Contractor’s sole remedy shall be an agreed upon adjustment in the Contract Time and the Contract Sum as outlined in Section 14.3.2; and a delay or hindrance resulting from a Force Majeure Event shall be governed by the provisions set forth in Sections 14.5.3 and 14.5.4 of the Agreement. | 5 |  | n/a | calendar day | 8.1.3 | § 4.2.9 The Architect will conduct inspections to determine the date or dates of Substantial Completion and the date of final completion; issue Certificates of Substantial Completion pursuant to Section 9.8; receive and forward to the Owner, for the Owner’s review and records, written warranties and related documents required by the Contract and assembled by the Contractor pursuant to Section 9.10; and issue a final Certificate for Payment pursuant to Section 9.10. § 9.8.1 Substantial Completion is the stage in the progress of the Work when the Work has passed final Township core and shell inspection with only minor punch list items remaining to be completed and can occur when a Temporary Certificate of Occupancy (“TCO”) has been issued. | 9.10 | § 9.10.1 Upon receipt by the Owner and Architect of the Contractor’s written notice that the Work is ready for final inspection and acceptance and upon receipt of a final Application for Payment, the Architect will promptly make such inspection. When the Architect and Owner find the Work acceptable under the Contract Documents and the Contract fully performed, the Architect will promptly issue a final Certificate for Payment stating that to the best of the Architect’s knowledge, information and belief, and on the basis of the Architect’s on-site visits and inspections, the Work has been completed in accordance with the Contract Documents and that the entire balance found to be due the Contractor and noted in the final Certificate is due and payable. The Architect’s final Certificate for Payment will constitute a further representation that conditions listed in Section 9.10.2 as precedent to the Contractor’s being entitled to final payment have been fulfilled. § 9.10.2 Neither final payment nor any remaining retained percentage shall become due until the Contractor submits to the Architect and Owner (1) an affidavit that payrolls, bills for materials and equipment, and other indebtedness connected with the Work for which the Owner or the Owner’s property might be responsible or encumbered (less amounts withheld by Owner) have been paid or otherwise satisfied, (2) a certificate evidencing that insurance required by the Contract Documents to remain in force after final payment is currently in effect and will not be canceled, materially altered or allowed to expire until at least 30 days’ (or fewer if 30 days not offered by Contractor’s insurer) prior written notice has been given to the Owner, (3) a written statement that the Contractor knows of no reason that the insurance will not be renewable to cover the period required by the Contract Documents, (4) consent of surety, if any, to final payment, (5) documentation of any special warranties, such as manufacturers’ warranties or specific Subcontractor warranties, (6) if required by the Owner, other data establishing payment or satisfaction of obligations, such as receipts and releases and waivers of liens, claims, security interests, or encumbrances arising out of the Contract, to the extent and in such form as may be designated by the Owner. If a Subcontractor refuses to furnish a release or waiver required by the Owner, the Contractor may furnish a bond satisfactory to the Owner to indemnify the Owner against such lien, claim, security interest, or encumbrance. If a lien, claim, security interest, or encumbrance remains unsatisfied after payments are made, the Contractor shall refund to the Owner all money that the Owner may be compelled to pay in discharging the lien, claim, security interest, or encumbrance, including all costs and reasonable attorneys’ fees, (7) record drawings and Operations & Maintenance Manuals (O&M’s) have been supplied to and approved by the Owner which approval shall not be unreasonably withheld or delayed, and (8) all areas have been cleaned to the Owner’s reasonable satisfaction. | No | n/a | 5 | 10 | 5.1.7.1 | 10% retainage held until 50% completion, at that time 5% retainage held until substantial completion as defined as passing of final Township core and shell inspection with only minor punch list items remaining to be completed | No | No |  | If approved in advance in writing by the Owner, payment may similarly be made for materials and equipment suitably stored off the site at a location agreed upon in writing. Payment for materials and equipment stored on or off the site shall be conditioned upon compliance by the Contractor with procedures satisfactory to the Owner to establish the Owner’s title to such materials and equipment or otherwise protect the Owner’s interest, and shall include the costs of applicable insurance, storage, and transportation to the site, for such materials and equipment stored off the site. | 30 | 9.7 | If the Architect does not issue a Certificate for Payment, through no fault of the Contractor, and without reasonable cause, within seven days after receipt of the Contractor’s Application for Payment, or if without reasonable cause the Owner does not pay the Contractor within seven days after the date established in the Contract Documents, the amount certified by the Architect, then the Contractor may, upon seven additional days’ written notice to the Owner and Architect, stop the Work until payment of the amount owing has been received. The Contract Time shall be extended appropriately and the Contract Sum shall be equitably increased by the amount of the Contractor’s reasonable costs of shutdown, delay and start-up, plus interest as provided for in the Contract Documents. | 6 | 7 | § 14.3.1 The Owner may, without cause or prior notice, order the Contractor in writing to suspend, delay or interrupt the Work in whole or in part for such period of time as the Owner may determine. | 7 (14.2.2) | [5 empty] | § 3.5.1 The Contractor warrants to the Owner and Architect that materials and equipment furnished under the Contract will be of good quality and new unless the Contract Documents require or permit otherwise. The Contractor further warrants that the Work will conform to the requirements of the Contract Documents and will be free from defects. Work, materials, or equipment not conforming to these requirements may be considered defective. The Contractor’s warranty excludes remedy for damage or defect caused by abuse, alterations to the Work not executed by the Contractor, improper or insufficient maintenance, improper operation, or normal wear and tear and normal usage. If required by the Owner, the Contractor shall furnish satisfactory evidence as to the kind and quality of materials and equipment. To the extent assignable, the Contractor shall assign to the Owner all warranties and guarantees of manufacturers, Subcontractors, and others related to the Work. § 12.2.2.2 The one-year period for correction of Work shall be extended with respect to portions of Work first performed after Substantial Completion by the period of time between Substantial Completion and the actual completion of that portion of the Work. § 12.2.2.3 Defective or non-conforming work corrected by the Contractor shall be warranted for an additional period of one year from the date of the Owner’s acceptance of the Contractor’s corrections. |  | 14. Contractor shall provide record drawing updates (as-builts) in accordance with the Contract Documents at project completion. Any change from original design intent will need approval from the Owner. | 5.2 | § 5.2.1 Final payment, constituting the entire unpaid balance of the Contract Sum, shall be made by the Owner to the Contractor when .1 the Contractor has fully performed the Contract except for the Contractor’s responsibility to correct Work as provided in Article 12 of AIA Document A201–2017, and to satisfy other requirements, if any, which arise or extend beyond final payment and the Work has passed all inspections required by applicable law; and .2 a final Certificate for Payment has been issued by the Architect and approved by the Owner; .3 the Contractor has delivered to the Owner conditional final waivers and lien releases in statutory form from the Contractor and all Subcontractors and suppliers; and .4 the Contractor has fully complied with Section 9.10 AIA A201-2017, and all other requirements of the Contract Documents for final payment. § 5.2.2 The Owner’s final payment to the Contractor shall be made no later than 30 days after the issuance of the Architect’s final Certificate for Payment, if approved by Owner, or as follows: |  | 11. Handling, removal, disposal, or capping of hazardous or contaminated materials is excluded. § 10.3.1 The Contractor is responsible for compliance with any requirements included in the Contract Documents regarding hazardous materials. The Contractor shall not cause or permit the discharge, emission or release of any hazardous substance and/or waste, pollutant, contaminant or other substance in violation of any applicable law. Contractor shall comply with all applicable environmental requirements and shall be responsible for compliance with all applicable hazardous waste laws, rules, and regulations, as well as provisions in the Contract Documents relating to hazardous waste. Hazardous materials, substances, and/or waste includes all substances which are or may be identified as such in 40 C.F.R. Part 261 or other applicable laws or regulations. If the Contractor encounters any hazardous material or substance not addressed in the Contract Documents and if reasonable precautions will be inadequate to prevent foreseeable bodily injury or death to persons resulting from a material or substance, including but not limited to asbestos or polychlorinated biphenyl (PCB), encountered on the site by the Contractor, the Contractor shall, upon recognizing the condition, immediately stop Work in the affected area and notify the Owner and Architect in writing of the condition. 29. Pricing is based on classified excavation and does not include costs and/or handling associated with rock, poor soils, existing building foundations, obstructions, sinkholes, or other unknown, concealed, or uncharted conditions. 39. Removal, replacement, or relocation of concealed or uncharted conditions is excluded. § 3.7.4 Concealed or Unknown Conditions If the Contractor encounters conditions at the site that are (1) subsurface or otherwise concealed physical conditions that differ materially from those indicated in the Contract Documents or (2) unknown physical conditions of an unusual nature that differ materially from those ordinarily found to exist and generally recognized as inherent in construction activities of the character provided for in the Contract Documents, the Contractor shall promptly provide notice to the Owner and the Architect before conditions are disturbed and in no event later than 10 days after first observance of the conditions. The Architect will promptly investigate such conditions and, if the Architect determines that they differ materially and cause an increase or decrease in the Contractor’s cost of, or time required for, performance of any part of the Work, will recommend that an equitable adjustment be made in the Contract Sum or Contract Time, or both. If the Architect determines that the conditions at the site are not materially different from those indicated in the Contract Documents and that no change in the terms of the Contract is justified, the Architect shall promptly notify the Owner and Contractor in writing, stating the reasons. If either party disputes the Architect’s determination or recommendation, that party may submit a Claim as provided in Article 15. Information shown on the Drawings as to the location of existing utilities has been prepared from the most reliable data available to the Architect. The Owner and the Architect do not guarantee this information, and it shall be the Contractor’s responsibility to verify the location, character and depth of existing utilities. If the information shown on the Drawings is inaccurate, the Contractor shall be entitled to an equitable adjustment to the Contract Sum. The Contractor shall help the utility companies, by reasonable means to verify said locations and the locations of recent additions to the systems not shown. | 10 | n/a | Yes |  | Yes | Yes | Non-Union | Yes | .1 AIA Document A101™–2017, Standard Form of Agreement Between Owner and Contractor .2 AIA Document A101™–2017, Exhibit A, Insurance and Bonds .3 AIA Document A201™–2017, General Conditions of the Contract for Construction .4 Exhibit B – Scope of Work, Documentation List, Qualifications and Schedule .5 Exhibit C – Reimbursable Cost of Work | Yes |  | n/a § A.2.5.1 Cyber Security Insurance for loss to the Owner due to data security and privacy breach, including costs of investigating a potential or actual breach of confidential or private information. | contract doesn't say
24 | 20 | 2025-06-03 | Custom Contract | Standalone Design and Build Construction Agreement - Lump Sump | No | Section 40 | No | Yes | Section 33. Following a 30-day grace period from the Substantial Completion Liquidated Damages are $10,000 per day, limited to a maximum of $905,000. |  | Attachment II - Section 4. Insurances: 1.25% | Owner | 100 | Not specified |  | Yes | No | Yes | Yes |  | 49.1 IMC shall within twenty (20) Business Days of receipt of the Agreement, provide an on demand Performance Bond, that shall be governed by the ICC Uniform Rules for Demand Guarantees URDG 758, whose value shall equate to 10% of the Agreement Price. 49.2 An Advance Payment Guarantee in a form contained in Attachment XVI is required for all advanced payments to be made by client at Agreement acceptance which exceed One Hundred Thousand US Dollars (USD $100,000) 49.3 Upon receipt of the Final Completion Certificate, IMC shall immediately provide an on-demand 5% Retention Bond of the final Agreement Price including all Changes of Work. The Retention Bond shall remain in place for (24) months. |  | Section 1. "Contract Documents" means and includes this Agreement, all Attachments hereto, the Designs including BIM models, Technical Documents, any addenda issued prior to the Effective Date of this Agreement, advance payment guarantee and performance bonds to be provided pursuant to this Agreement or other Contract Documents, additional Supplier design drawings and Design Development. Specifications, modifications and addenda issued after the Effective Date of this Agreement and approved in writing by Company, Changes to Work and field orders issued hereafter, any other amendments to this Agreement executed by Company, Company’s request for proposals and bid inquiry documents (to the extent not inconsistent with any other Contract Document) and all documents annexed hereto as part of or incorporated by reference in this Agreement or the other Contract Documents; "Technical Documents" means the Engineering Documents, technical specifications, datasheets and other documents listed in this Agreement, as well as any additional or revised Engineering Documents that may be issued by Company to Supplier in relation to the Work pursuant to Section 16; "Change to/of Work" means, a written order to Supplier executed by Company in accordance with Attachment XI. The Change to Work authorizes and directs an addition to, deletion from, or adjustment or revision to the requirements of the Agreement, or an adjustment to (a) the Agreement Price or other compensation payable to Supplier, or (b) the time for observance and performance of (i) the Contract Documents, (ii) the scheduled Completion Date; |  | 17.1 Supplier shall create and provide all Construction Documents described in or required by the Agreement, or as Company may reasonably request. Supplier shall review all Construction Documents prior to submission to Company, and Supplier represents by this review that: 17.1.1 Supplier has determined and verified all field measurements, field construction conditions and product requirements; and 17.1.2 Supplier has checked and coordinated each Construction Document with the requirements of the Work and the Agreement. 17.2 Supplier shall confirm its review of each Construction Document by the stamp (as applicable), date and signature of the responsible Personnel on the Construction Document. At the time of submission, Supplier shall notify Company in writing of any deviations in the Construction Documents from the requirements of the Work and the Agreement. 17.3 Upon Company's request, Supplier shall review and resubmit any submitted Construction Documents that Company rejects as containing Document Errors or otherwise being inconsistent with the Work or the Agreement. Company shall notify Supplier in writing of any revisions it requires to the Construction Documents that are to be resubmitted. |  | 15.1 Supplier shall acquire any Supplier Materials from manufacturers pre-approved by Company, and any request by Supplier to substitute other Materials must be approved by Company. Company shall be the sole judge of the acceptability of any alternative Materials proposed by Supplier and whether such alternative Materials conform to the specifications stipulated in the Agreement, and Company's approval shall be obtained before any such substitution is made. | No | No |  |  |  | No |  |  | No | Yes | No |  | This project is Lump Sump |  | No | [6 empty] | Section 1: "Agreement Price" means the total aggregate price to be paid by Company to Supplier for performing the Work, as calculated and determined in accordance with the Agreement and as may be adjusted by the applicable provisions of the Contract Documents, which shall constitute the full and entire amount payable by Company for the Work inclusive of any Changes to Work as may be applicable. The Agreement Price and method of compensating same are included in Attachment II of this Agreement. |  | N/A |  | Lump Sum | N/A | No | Section 1. Page 6 General Conditions include but are not limited to the following: Site Surveying/layout, site engineering equipment and supplies, drawing reproduction, shop drawing reproduction, , temporary chemical toilets, temporary water consumption, temporary heat, temporary cooling, conexes and project trailers, temporary electric consumption, temporary fire protection, temporary telephone service, snow removal as required, dust control as required, supplier's site office, architect site offices, miscellaneous site storage sheds and trailers, site supplier staff telephones, site architect’s telephone, site office equipment, site vehicles, site building intercom system, site watchman services, site offices cleaning, rubbish chute, site rubbish removal, project progress photographs, project signage, project petty cash, site office fire extinguishers, project postage, , site temporary fencing, site temporary gates, site temporary enclosure, traffic control, site drug and alcohol testing program, safety program, consumables, and Small Tools. The list of General Conditions referenced above should be reviewed against the Attachment I - Scope of Work (Merck Wilmington Biotech Lab & Administration Facility Scope Responsibility Matrix) and Attachment II – Compensation with regards the Company provided General Conditions with all remaining General Conditions the responsibility of Supplier. | Attachment II, Section 4: 10% |  | Attachment II, Section 4: 2.25% | Attachment II, Section 4: 1.25% | Attachment II, Section 4: 0% | Attachment II, Section 4: 6.5% | Attachment II, Section 4: 0% or included with CCIP | Attachment II, Section 4: 0% |  | Section 45: Neither Party shall be liable for a failure or delay in performing any of its obligations under this Agreement if, but only to the extent that, such failure or delay is due to causes beyond the reasonable control of the affected Party, including (1) acts of God; (2) fire, explosion, or unusually severe weather; (3) war, invasion, riot, or other civil unrest; (4) laws, orders, restrictions, actions, embargoes, or blockages imposed by any Governmental Authority; (5) national or regional emergency; and (6) injunctions, strikes, lockouts, labor trouble, or other industrial disturbances; provided that the Party affected shall promptly notify the other of the Force Majeure condition and shall exert reasonable efforts to eliminate, cure, or overcome any such causes and to resume performance of its obligations as soon as possible. Any failure or delay in performing any obligation under this Agreement as a result of failure or performance abnormality in software, hardware, or firmware shall not be, or be deemed to be, the result of Force Majeure | ASAP |  |  | 20.3 Supplier shall deliver to Company a revised Work Schedule every month or as otherwise requested by Company Representative, contrasting the initial Work Schedule and the actual progress of the Work. 20.4 Company reserves the right to modify any portion of the Work Schedule. Supplier shall promptly modify the Work Schedule as necessary to reflect said Company modifications. Company makes no representation that Supplier will be able to commence, prosecute, or complete the Work in accordance with any schedule. 20.5 The projected sequencing of the Work shown in the Work Schedule may be modified by Supplier, at no cost to Company, if such modifications do not adversely affect the work of Other Suppliers, or the achievement of the Scheduled Completion Date or any Milestone Date, provided however that Supplier shall inform Company of such modifications and obtain Company's prior written approval, which shall not be unreasonably withheld. |  | 20.6 Supplier shall be responsible for maintaining the progress of all parts of the Work in accordance with the Work Schedule. Such responsibility of Supplier shall not be diminished or relieved in any way as a result of any failure caused by labor strikes or shortages or by loss of or damage to the Work or Facilities. The cost of taking all necessary steps to progress the Work or to expedite the rate of progress, including subcontracting, additional shifts, overtime and supplying additional manpower, materials, resources and equipment as may be required, shall be the responsibility of and for the account of Supplier. |  | 21.1 If, at any time during the progress of the Work, Supplier is responsible for a delay in the Work, fails to meet any Milestone Dates or fails to complete any portion of the Work within the time limits set forth in the Work Schedule, or if Company, acting reasonably, believes that any of Supplier's methods for executing the Work are inadequate or that the Supplier Group is not proceeding with the Work with sufficient diligence or sufficient Personnel to meet Work Schedule requirements and ensure completion of the Work in accordance with the terms of the Agreement, then Company may instruct and direct Supplier to improve its means and methods, increase and employ such additional Personnel or perform such additional, accelerated or overtime work or take such other steps as are required to ensure the timely completion of the Work in accordance with the Agreement, including obtaining and implementing a recovery schedule, all at Supplier's sole cost, risk and expense. | 20.1 ASAP - Supplier shall notify Company, promptly in writing, as soon as Supplier becomes aware of any potential material deviations from the Agreement Price or Work Schedule (including without limitation any delays in the progress of the Work), and the details thereof. |  | 21.2 If Company determines that it wishes to accelerate the Milestone Dates or Scheduled Completion Date to an earlier date and such acceleration is not due to any act, omission or fault of Supplier and is capable of being achieved by effecting revisions to the Work Schedule or by reallocating the available Supplier resources as agreed by Supplier, then Company may at any time request Supplier to alter the sequence of the Work and/or work overtime and/or holidays and rest days and/or deploy available additional resources, including manpower and equipment. Supplier shall take no steps to alter the sequence of the Work and/or work such overtime or additional days and/or deploy and utilize such additional resources until Company issues a Change of Work directing or approving such a change. | Section 1: "Business Day" means any day other than a Saturday, Sunday or a statutory holiday in the country in which the Project is being constructed. If Business Days is not specifically stated then any other reference to days shall mean calendar days. "Work" means the provision by Supplier of all services and other work to be performed pursuant to the Agreement including but not limited to, the procurement, supply of any required Supplier Materials and Supplier Supplies by Supplier, and the provision of all necessary engineering services, Construction Documents, Design Development, detailed design, technical personnel, labour, management, supervision, Subcontracts, administration, software, expertise and equipment for the construction, testing and handover of the Facilities by Supplier Group, as well as anything that is ancillary or necessary by implication to fulfill the Agreement or Company's requirements; | Section #32 and attachment VII | Section 32.1 32.1.1 All Work has been completed and the Facilities have been properly constructed and fit for the purpose for which they were constructed by Supplier in accordance with the requirements of the Contract Documents and to the satisfaction of Company with the exception of a handover Punchlist which will be issued by Company in conjunction with the Substantial Completion Certificate. 32.1.2 Supplier has completed all testing and installation verification activities completed by the Supplier to the satisfaction of Company. 32.1.3 All critical handover documentation completed by the Supplier to the satisfaction of Company and the required number of three (3) copies issued. All other handover documentation is to be completed by the Supplier within one (1) month of Substantial Completion. 32.1.4 All construction and start-up documentation, and warranties provided by Suppliers and Subcontractors as required by this Agreement in a form reasonably acceptable to Company. | Section #32 and attachment VIII | "Final Completion" means final completion of the Work in accordance with the requirements of this Agreement and the Contract Documents, including that all items of unfinished Work have been completed and, where applicable, that a certificate of occupancy and all necessary municipal permits required for Company’s intended use of the Project have been obtained, and that the Work has been accepted by Company as evidenced by a signed Final Completion Certificate; | No |  | Section 23 | 23.12 Company shall withhold ten percent (10%) retainage or Lien holdback | 23.12 | 23.12 Upon Final Completion and subject to receiving security as required by Section 49.3 (5% Retention Bond) of this Agreement, the retainage shall be released. | Yes | Yes |  | 19.2 Materials stored (whether on Company Work Site or Supplier Work Site) but not yet incorporated into the Facilities shall not be deemed qualified for payment without Company’s prior written approval. Supplier may request said Company approval in writing provided that: (1) said storage provides a material financial benefit to the cost of the subject Project, or (2) is for special “long-lead” Materials; and provided further that, with respect to Materials stored in a Company Work Site or Supplier Work Site, said Materials are physically segregated from other goods stored in said sites and marked as the property of Company with Company entity clearly identified. Said request shall include, without limitation, a reasonably detailed description of the subject Materials, including the quantities and value thereof. 19.3 Supplier shall provide to Company, at the time of any such approval, Invoices in accordance with Section 23. Payment for any such Company-approved stored Materials shall exclude any retainage. Company reserves the right to inspect all such Materials prior to any such payment and the right to make all such subsequent inspection of said Materials as Company deems desirable. | 90 |  | 23.8 If Company withholds payment (in whole or in part) of any Invoice, Company shall so notify Supplier in writing. Except as otherwise provided by Law, Supplier shall, within thirty (30) days of receipt of such Notice, notify Company Representative in writing that Supplier disputes such withheld payment. Said Supplier Notice shall include a justification, including a detailed justification including the required back-up as requested by Company, for reimbursement of the payment withheld. Supplier’s failure to notify Company within said thirty (30) days will result in a waiver of Supplier’s rights to the withheld payment. | 23.8 and 62 | 56, 56.2 | 5 | 0 | [5 empty] | Section 1: Starting the date of final completion certificate: Structural Warranty - Supplier shall provide a ten (10) year Warranty Period on its workmanship with respect to any structural Work. Non-Structural Warranty - Supplier shall provide a twenty-four (24) month Warranty Period with respect to any Work, Materials, equipment or components that forms part of the Work or are installed in the Facilities. Section 34.6 Express Warranties. During the Warranty Period, Supplier warrants that (i) the Facilities will conform strictly with the Contract Documents and perform in accordance with the performance requirements set forth in the Agreement; (ii) the Facilities and their components have been designed and manufactured so as to conform with the Contract Documents; (iii) the Facilities will be merchantable (as such term is defined by Law), of high quality material and workmanship, free from defects in design, workmanship and Materials, and will be fit and sufficient for the purpose intended; and (iv) the Facilities will conform to the Contract Documents and/or other Technical Documents and Engineering Documents provided by Company to Supplier prior to the effective date of the Agreement. Supplier further represents, warrants and covenants that all Materials, items furnished, and all workmanship shall be of high quality. Supplier shall replace or reperform, as deemed necessary by Company, any of the Materials, items furnished or Work that are found lacking or defective, in the reasonable opinion of Company, without additional cost to Company. 34.20 Collateral Warranty. Supplier shall within 10 (ten) working days of Company’s request, procure that each Subcontractor and each member of Supplier Design Team shall each execute and deliver a Collateral Warranty in favor of Company. 38.4 Supplier further warrants against Deficiency any and all work and goods it supplies in respect of any remedial work performed by it pursuant to Section 38.1 for a period ending the later of twenty-four (24) months from completion of such remedial work and the end of the original Warranty Period. |  | 17.4 Supplier shall, unless otherwise directed by Company: 17.4.1 prepare, collect and maintain at the Project Site, on a current basis over the course of the Work, sufficient and updated Redline Drawings, with any necessary cross-referencesto relevant specifications, standards and codes; 17.4.2 during the performance of the Work, provide Company with access to the Redline Drawings; and 17.4.3 record the exact locations of each of the differences, sizes and details of the Work as executed, with cross-references to relevant specifications and other requirements, on the Redline Drawings. 17.5 All Technical Documents, BIM models, Construction Documents and any other specifications, operating instructions, manuals and other pertinent papers prepared by or provided to Supplier in performance of the Work or necessary for Company to operate, maintain, repair, modify or replace the Work or Facilities or any part thereof shall be the property of Company and shall be considered to be Confidential Information, and shall not be used by Supplier on other work and shall, on request, be returned or provided to Company upon the earlier of the termination of the Agreement or Final Completion. | Section 23 and attachment XVII | 23.9 A Final Release of Liens shall be included with Supplier’s Final Invoice and with the Final Invoice submitted by each Subcontractor, prior to the release of Final Payment to Supplier by Company. |  | Section 52 52.1 Supplier shall at all times take all necessary precautions to prevent the discharge of any Hazardous Material onto the site or into the environment during performance of the Work. To the extent that Company has actual knowledge thereof, Company shall inform Supplier of any conditions on or within the Project Site that pose hazards to the health or safety of persons or that may affect Supplier’s performance of the Work under this Agreement. | ASAP - 52.4 If, in the course of performing the Work, Supplier encounters environmental conditions of which it has not been made aware by Company, including Pre-Existing Conditions, Supplier shall promptly notify Company of their existence and location, and shall cease all operations in the affected area until such time as Company and Supplier have had an opportunity to discuss such environmental conditions | 20.3 - Monthly schedule 54.4 - At Clinet's request to be performed by IMC and IMC's subcontractors: SOC 1 Type 2Audit report, performed by a client's acceptable firm, preferably KPMG, PwC, among others) Attachment XII - Quarterly diversity reports | No |  | Yes | Yes | Non-Union | Yes | Attachment I Scope of Work Attachment II Compensation Attachment III Work Schedule Attachment IV Health & Safety Standards Attachment V Not Used Attachment VI Not Used Attachment VII Substantial Completion Certificate Attachment VIII Final Completion Certificate Attachment IX Data Privacy and Security Requirements Atttachment X Drug & Alcohol Program Attachment XI Change to Work Form Attachment XII Supplier Diversity Attachment XIII Transportation and Security Matters Attachment XIV Export Compliance Attachment XV Performance Bond Template Attachment XVI Advanced Payment Guarantee Template Attachment XVII Statutory Declaration and Release & Certificate of Final Payment Attachment XVIII Not Used Attachment XIX Collateral Warranty Template Attachment XX Not Used | Yes |  | Section 41.1: Insurance requirement Comprehensive cyber/network/privacy liability $3,000,000 | Section 41.4 Client may request IMC to procure a buy down policy insuring the Builders Risk insurance policy deductible amounts specific to this Project. In that case a Chage Order will be provided to IMC
16 | 25 | 2025-10-15 | A101 - Stipulated Sum | Stipulated Sum | No | N/A | Yes | Yes | Liquidated damages for delay paid to the owner, the sum of $500, for each calendar day after the date scheduled for substantial completion of the work until the contractor achieves substantial completion. |  | N/A | Owner | N/A | N/A | 11.3 | No | No | No | No |  | N/A |  | Drawing specification addenda issued prior to this agreement. |  | Contractor has visited site, generally familiar with local conditions under which the work is to be performed and correlated personal observations with requirements of the contract documents. |  | Except in the case of minor changes in the Work approved by the Architect in accordance with Section 3.12.8 or ordered by the Architect in accordance with Section 7.4, the Contractor may make substitutions only with the consent of the Owner, after evaluation by the Architect and in accordance with a Change Order or Construction Change Directive. | No | No |  | N/A |  | No | N/A |  | No | No | No |  | N/A |  | No | No | N/A | No | A.4 | LS 2025 |  | Cost of labor, cost of materials, cost of machinery/equipment, cost of bonds, insurance, taxes and permit fees, cost of supervision and field office personnel directly attributable to the cost. |  | N/A | N/A | Lump Sum | N/A | No | N/A | 10% | Aggregate 10% | 3% | N/A | N/A | N/A | 1% | N/A |  | lf the Contractor is delayed at any time in the commencement or progress of the Work by adverse weather conditions documented in accordance with Section 15.1.6.2, or other causes beyond the Contractor's control or by other causes that the Contractor asserts, and the Architect determines, justify delay, then the Contract Time shall be extended for such reasonable time as the Architect may determine. | 21 days | 0 |  | The schedule shall contain detail appropriate for the Project, including (I) the date of commencement of the Work, interim schedule milestone dates, and the date of Substantial Completion; (2) an apportionment of the Work by construction activity; and (3) the time required for completion of each portion of the Work. The schedule shall provide for the orderly progression of the Work to completion and shall not exceed time limits current under the Contract Documents. The schedule shall be revised at appropriate intervals as required by the conditions of the Work and Project. |  | N/A |  | If the Contractor is delayed at any time in the commencement or progress of the Work by {l) an act or neglect of the Owner or Architect, of an employee of either, or of a Separate Contractor; (2) by changes ordered in the Work; (3) by labor disputes fire, unusual delay in deliveries, unavoidable casualties, adverse weather conditions documented in accordance with Section 15.1.6.2, or other causes beyond the Contractor's control; (4) by delay authorized by the Owner pending mediation and binding dispute resolution; or (5) by other causes that the Contractor asserts, and the Architect determines, justify delay, then the Contract Time shall be extended for such reasonable time as the Architect may determine. | 21 days |  | The Contractor shall achieve completion by those dates and times (Per the schedule) and shall perform all out-of-sequence work, come-back work, stand-by work, overtime, expediting and acceleration that may be required to complete the Work by those dates and times, all without charge to the Owner. | The term "day" as used in the Contract Documents shall mean calendar day unless otherwise specifically defined. | 3.3 | Subject to adjustments of contract time as provided in the contract documents, the contractor shall achieve substantial completion of the entire work by agreed upon date in executed documents. If contractors fails, liquidated damages, if any, shall be assessed. | 9.10 | Upon receipt of the Contractor's notice that the Work is ready for final inspection and acceptance and upon receipt of a final Application for Payment the Architect will promptly make such inspection. When the Architect finds the Work acceptable under the Contract Documents and the Contract fully performed, the Architect will promptly issue a final Certificate for Payment stating that to the best of the Architect's knowledge, information and belief, and on the basis of the Architect's on-site visits and inspections, the Work has been completed in accordance with the Contract Documents and that the entire balance found to be due the Contractor and noted in the final Certificate is due and payable. | No | N/A | 5.1 and 5.2, respectively | 10% | 5.1.7 | There shall be no reduction in retainage until final payment. | No | No |  | The amount of each progress payment shall include that portion of the Contract Sum properly allocable to materials and equipment delivered and suitably stored at the site for subsequent incorporation in the completed construction, or, if approved in advance by the Owner, suitably stored off the site at a location agreed upon in writing. | 30 days | 14.1.4 | If the Work is stopped for a period of 60 consecutive days through no act or fault of the Contractor, a Subcontractor, a Sub-subcontractor, or their agents or employees or any other persons or entities performing portions of the Work because the Owner has repeatedly failed to fulfill the Owner's obligations under the Contract Documents with respect to matters important to the progress of the Work, the Contractor may, upon seven additional days' notice to the Owner and the Architect, terminate the Contract and recover from the Owner as provided in 14.1.3. | 6.2 | 14.1.1 | 7 days | 7 days | [5 empty] | Work, materials, or equipment not confirming to the standard requirements, including unapproved substitutions, may be considered defective. The Contractor’s warranty does not cover damage or defect caused by abuse that is not the Contractor’s responsibility, alterations to the Work not executed by the Contractor, improper or insufficient maintenance, improper operation, or normal wear and tear and normal usage. If required by the Owner or Architect, the Contractor shall furnish satisfactory evidence as to the kind and quality of materials and equipment. |  | The Contractor shall furnish to the Owner two hard copies in three-ring binders and one electronic version on a CD in PDF format (Adobe compatible) of each item identified on the Construction Contract Close Out Checklist, on the form attached to the Agreement (including any Supplement thereto). If the Contractor does not furnish these items, and the Owner must otherwise obtain such information and data, the costs reasonably incurred by the Owner in doing so will be deducted from payments then or thereafter due to Contractor. | 5.2 | Final payment, constituting the entire unpaid balance of the contract sum, shall be made by the owner to the contractor when the contractor has fully performed the contract except the contractor's responsibility to correct work, to satisfy other existing outstanding requirements, and a final certificate for payment has been issued by the architect. |  | The Contractor is responsible for compliance with any requirements included in the Contract Documents regarding hazardous materials or substances. If the Contractor encounters a hazardous material or substance not addressed in the Contract Documents and if reasonable precautions will be inadequate to prevent foreseeable bodily injury or death to persons resulting from a material or substance, including but not limited to asbestos or polychlorinated biphenyl (PCB), encountered on the site by the Contractor, the Contractor shall, upon recognizing the condition, immediately stop Work in the affected area and notify the Owner and Architect of the condition. | 21 days | TAB Report, Fire Alarm Report, Commissioning Report | Yes |  | No | Yes | Prevailing Wage | No | 1 - General Provisions 2 - Owner 3 - Contractor 4 - Architect 5 - Subcontractor 6 - Construction by owner or by separate contractors 7 - Changes in the work 8 - Time 9 - Payments and Completion 10 - Protection of Persons and Property 11 - Insurance and Bonds 12 - Uncovering and Correction of Work 13 - Miscellaneous Provisions 14 - Termination or Suspension of the Contract 15 - Claims and Disputes | No |  | Optional insurance for cyber security to be purchased by owner. | Owner
25 | 27 | 2025-11-07 | Custom Contract | Standalone Design Build Lump Sum Agreement | No | Section 40 | No | Yes | Section 33. Following a 30-day grace period from the Substantial Completion Liquidated Damages are $10,000 per day, limited to a maximum of $415,000. |  | 2% | Owner | Not specified | Not specified | Not Provided | Yes | No | Yes | No |  | Payment and Performance bond requirement removed by Merck, but we will need a retention bond at final completion. 49.3 Upon receipt of the Final Completion Certificate, IMC shall immediately provide an on-demand 5% Retention Bond of the final Agreement Price including all Changes of Work. The Retention Bond shall remain in place for (24) months. |  | Section 1. ""Contract Documents"" means and includes this Agreement, all Attachments hereto, the Designs including BIM models, Technical Documents, any addenda issued prior to the Effective Date of this Agreement, advance payment guarantee and performance bonds to be provided pursuant to this Agreement or other Contract Documents, additional Supplier design drawings and Design Development. Specifications, modifications and addenda issued after the Effective Date of this Agreement and approved in writing by Company, Changes to Work and field orders issued hereafter, any other amendments to this Agreement executed by Company, Company’s request for proposals and bid inquiry documents (to the extent not inconsistent with any other Contract Document) and all documents annexed hereto as part of or incorporated by reference in this Agreement or the other Contract Documents; "Technical Documents" means the Engineering Documents, technical specifications, datasheets and other documents listed in this Agreement, as well as any additional or revised Engineering Documents that may be issued by Company to Supplier in relation to the Work pursuant to Section 16; "Change to/of Work" means, a written order to Supplier executed by Company in accordance with Attachment XI. The Change to Work authorizes and directs an addition to, deletion from, or adjustment or revision to the requirements of the Agreement, or an adjustment to (a) the Agreement Price or other compensation payable to Supplier, or (b) the time for observance and performance of (i) the Contract Documents, (ii) the scheduled Completion Date |  | 17.1 Supplier shall create and provide all Construction Documents described in or required by the Agreement, or as Company may reasonably request. Supplier shall review all Construction Documents prior to submission to Company, and Supplier represents by this review that: 17.1.1 Supplier has determined and verified all field measurements, field construction conditions and product requirements; and 17.1.2 Supplier has checked and coordinated each Construction Document with the requirements of the Work and the Agreement. 17.2 Supplier shall confirm its review of each Construction Document by the stamp (as applicable), date and signature of the responsible Personnel on the Construction Document. At the time of submission, Supplier shall notify Company in writing of any deviations in the Construction Documents from the requirements of the Work and the Agreement. 17.3 Upon Company's request, Supplier shall review and resubmit any submitted Construction Documents that Company rejects as containing Document Errors or otherwise being inconsistent with the Work or the Agreement. Company shall notify Supplier in writing of any revisions it requires to the Construction Documents that are to be resubmitted. |  | 15.1 Supplier shall acquire any Supplier Materials from manufacturers pre-approved by Company, and any request by Supplier to substitute other Materials must be approved by Company. Company shall be the sole judge of the acceptability of any alternative Materials proposed by Supplier and whether such alternative Materials conform to the specifications stipulated in the Agreement, and Company's approval shall be obtained before any such substitution is made. | No | No |  | N/A |  | No | N/A |  | No | Yes | No |  | N/A - Lump Sum |  | No | No | N/A - Lump Sum | No | N/A - Lump Sum | N/A - Lump Sum |  | "Section 1: ""Agreement Price"" means the total aggregate price to be paid by Company to Supplier for performing the Work, as calculated and determined in accordance with the Agreement and as may be adjusted by the applicable provisions of the Contract Documents, which shall constitute the full and entire amount payable by Company for the Work inclusive of any Changes to Work as may be applicable. The Agreement Price and method of compensating same are included in Attachment II of this Agreement." |  | N/A - Lump Sum | N/A - Lump Sum | Lump Sum | N/A - Lump Sum | No | "Section 1. Page 6 General Conditions include but are not limited to the following: Site Surveying/layout, site engineering equipment and supplies, drawing reproduction, shop drawing reproduction, , temporary chemical toilets, temporary water consumption, temporary heat, temporary cooling, conexes and project trailers, temporary electric consumption, temporary fire protection, temporary telephone service, snow removal as required, dust control as required, supplier's site office, architect site offices, miscellaneous site storage sheds and trailers, site supplier staff telephones, site architect’s telephone, site office equipment, site vehicles, site building intercom system, site watchman services, site offices cleaning, rubbish chute, site rubbish removal, project progress photographs, project signage, project petty cash, site office fire extinguishers, project postage, , site temporary fencing, site temporary gates, site temporary enclosure, traffic control, site drug and alcohol testing program, safety program, consumables, and Small Tools. The list of General Conditions referenced above should be reviewed against the Attachment I - Scope of Work (Merck Wilmington Biotech Lab & Administration Facility Scope Responsibility Matrix) and Attachment II – Compensation with regards the Company provided General Conditions with all remaining General Conditions the responsibility of Supplier. " | Not specified | Not specified | Attachment II, Section 4. 10% Flat Markup. Supervision and Project Management costs are evaluated on case by case basis. | See above. | See above. | See above. |  | See above. |  | Section 45: Neither Party shall be liable for a failure or delay in performing any of its obligations under this Agreement if, but only to the extent that, such failure or delay is due to causes beyond the reasonable control of the affected Party, including (1) acts of God; (2) fire, explosion, or unusually severe weather; (3) war, invasion, riot, or other civil unrest; (4) laws, orders, restrictions, actions, embargoes, or blockages imposed by any Governmental Authority; (5) national or regional emergency; and (6) injunctions, strikes, lockouts, labor trouble, or other industrial disturbances; provided that the Party affected shall promptly notify the other of the Force Majeure condition and shall exert reasonable efforts to eliminate, cure, or overcome any such causes and to resume performance of its obligations as soon as possible. Any failure or delay in performing any obligation under this Agreement as a result of failure or performance abnormality in software, hardware, or firmware shall not be, or be deemed to be, the result of Force Majeure | Not specified. 20.1 - Supplier shall notify Company, promptly in writing, as soon as Supplier becomes aware of any potential material deviations from the Agreement Price or Work Schedule (including without limitation any delays in the progress of the Work), and the details thereof. | 0 |  | 20.3 Supplier shall deliver to Company a revised Work Schedule every month or as otherwise requested by Company Representative, contrasting the initial Work Schedule and the actual progress of the Work. 20.4 Company reserves the right to modify any portion of the Work Schedule. Supplier shall promptly modify the Work Schedule as necessary to reflect said Company modifications. Company makes no representation that Supplier will be able to commence, prosecute, or complete the Work in accordance with any schedule. 20.5 The projected sequencing of the Work shown in the Work Schedule may be modified by Supplier, at no cost to Company, if such modifications do not adversely affect the work of Other Suppliers, or the achievement of the Scheduled Completion Date or any Milestone Date, provided however that Supplier shall inform Company of such modifications and obtain Company's prior written approval, which shall not be unreasonably withheld. |  | 20.6 Supplier shall be responsible for maintaining the progress of all parts of the Work in accordance with the Work Schedule. Such responsibility of Supplier shall not be diminished or relieved in any way as a result of any failure caused by labor strikes or shortages or by loss of or damage to the Work or Facilities. The cost of taking all necessary steps to progress the Work or to expedite the rate of progress, including subcontracting, additional shifts, overtime and supplying additional manpower, materials, resources and equipment as may be required, shall be the responsibility of and for the account of Supplier. |  | 21.1 If, at any time during the progress of the Work, Supplier is responsible for a delay in the Work, fails to meet any Milestone Dates or fails to complete any portion of the Work within the time limits set forth in the Work Schedule, or if Company, acting reasonably, believes that any of Supplier's methods for executing the Work are inadequate or that the Supplier Group is not proceeding with the Work with sufficient diligence or sufficient Personnel to meet Work Schedule requirements and ensure completion of the Work in accordance with the terms of the Agreement, then Company may instruct and direct Supplier to improve its means and methods, increase and employ such additional Personnel or perform such additional, accelerated or overtime work or take such other steps as are required to ensure the timely completion of the Work in accordance with the Agreement, including obtaining and implementing a recovery schedule, all at Supplier's sole cost, risk and expense. | Not specified. 20.1 - Supplier shall notify Company, promptly in writing, as soon as Supplier becomes aware of any potential material deviations from the Agreement Price or Work Schedule (including without limitation any delays in the progress of the Work), and the details thereof. |  | 21.2 If Company determines that it wishes to accelerate the Milestone Dates or Scheduled Completion Date to an earlier date and such acceleration is not due to any act, omission or fault of Supplier and is capable of being achieved by effecting revisions to the Work Schedule or by reallocating the available Supplier resources as agreed by Supplier, then Company may at any time request Supplier to alter the sequence of the Work and/or work overtime and/or holidays and rest days and/or deploy available additional resources, including manpower and equipment. Supplier shall take no steps to alter the sequence of the Work and/or work such overtime or additional days and/or deploy and utilize such additional resources until Company issues a Change of Work directing or approving such a change. | Section 1: "Business Day" means any day other than a Saturday, Sunday or a statutory holiday in the country in which the Project is being constructed. If Business Days is not specifically stated then any other reference to days shall mean calendar days. | 32 / Attachment VII | 32.1.1 All Work has been completed and the Facilities have been properly constructed and fit for the purpose for which they were constructed by Supplier in accordance with the requirements of the Contract Documents and to the satisfaction of Company with the exception of a handover Punchlist which will be issued by Company in conjunction with the Substantial Completion Certificate. 32.1.2 Supplier has completed all testing and installation verification activities completed by the Supplier to the satisfaction of Company. 32.1.3 All critical handover documentation completed by the Supplier to the satisfaction of Company and the required number of three (3) copies issued. All other handover documentation is to be completed by the Supplier within one (1) month of Substantial Completion. 32.1.4 All construction and start-up documentation, and warranties provided by Suppliers and Subcontractors as required by this Agreement in a form reasonably acceptable to Company. | 32 / Attachment VIII | "Final Completion" means final completion of the Work in accordance with the requirements of this Agreement and the Contract Documents, including that all items of unfinished Work have been completed and, where applicable, that a certificate of occupancy and all necessary municipal permits required for Company’s intended use of the Project have been obtained, and that the Work has been accepted by Company as evidenced by a signed Final Completion Certificate; | Yes | Milestones Dates Date Commencement Date 7-Nov-2025 Phase 2 Award to Supplier 30-Mar-2026 Site Mobilization 18-Jan-2027 Company Completion of Dry Shell 29-Jan-2027 Substantial Completion Date 30-Nov-2027 Scheduled Completion Date 5-Jan-2028 | 23 | 10% | 23.12 | 23.12 Upon Final Completion and subject to receiving security as required by Section 49.3 (5% Retention Bond) of this Agreement, the retainage shall be released. | Yes | Yes |  | 19.2 Materials stored (whether on Company Work Site or Supplier Work Site) but not yet incorporated into the Facilities shall not be deemed qualified for payment without Company’s prior written approval. Supplier may request said Company approval in writing provided that: (1) said storage provides a material financial benefit to the cost of the subject Project, or (2) is for special “long-lead” Materials; and provided further that, with respect to Materials stored in a Company Work Site or Supplier Work Site, said Materials are physically segregated from other goods stored in said sites and marked as the property of Company with Company entity clearly identified. Said request shall include, without limitation, a reasonably detailed description of the subject Materials, including the quantities and value thereof. 19.3 Supplier shall provide to Company, at the time of any such approval, Invoices in accordance with Section 23. Payment for any such Company-approved stored Materials shall exclude any retainage. Company reserves the right to inspect all such Materials prior to any such payment and the right to make all such subsequent inspection of said Materials as Company deems desirable. | 90 | Not specified | Not specified | 23.8 and 62 | 23.8 and 62 | 5 | 0 | [5 empty] | "Section 1: Starting the date of final completion certificate: Structural Warranty - Supplier shall provide a ten (10) year Warranty Period on its workmanship with respect to any structural Work. Non-Structural Warranty - Supplier shall provide a twenty-four (24) month Warranty Period with respect to any Work, Materials, equipment or components that forms part of the Work or are installed in the Facilities. Section 34.6 Express Warranties. During the Warranty Period, Supplier warrants that (i) the Facilities will conform strictly with the Contract Documents and perform in accordance with the performance requirements set forth in the Agreement; (ii) the Facilities and their components have been designed and manufactured so as to conform with the Contract Documents; (iii) the Facilities will be merchantable (as such term is defined by Law), of high quality material and workmanship, free from defects in design, workmanship and Materials, and will be fit and sufficient for the purpose intended; and (iv) the Facilities will conform to the Contract Documents and/or other Technical Documents and Engineering Documents provided by Company to Supplier prior to the effective date of the Agreement. Supplier further represents, warrants and covenants that all Materials, items furnished, and all workmanship shall be of high quality. Supplier shall replace or reperform, as deemed necessary by Company, any of the Materials, items furnished or Work that are found lacking or defective, in the reasonable opinion of Company, without additional cost to Company. 34.20 Collateral Warranty. Supplier shall within 10 (ten) working days of Company’s request, procure that each Subcontractor and each member of Supplier Design Team shall each execute and deliver a Collateral Warranty in favor of Company. 38.4 Supplier further warrants against Deficiency any and all work and goods it supplies in respect of any remedial work performed by it pursuant to Section 38.1 for a period ending the later of twenty-four (24) months from completion of such remedial work and the end of the original Warranty Period. " |  | "17.4 Supplier shall, unless otherwise directed by Company: 17.4.1 prepare, collect and maintain at the Project Site, on a current basis over the course of the Work, sufficient and updated Redline Drawings, with any necessary cross-references to relevant specifications, standards and codes; 17.4.2 during the performance of the Work, provide Company with access to the Redline Drawings; and 17.4.3 record the exact locations of each of the differences, sizes and details of the Work as executed, with cross-references to relevant specifications and other requirements, on the Redline Drawings. 17.5 All Technical Documents, BIM models, Construction Documents and any other specifications, operating instructions, manuals and other pertinent papers prepared by or provided to Supplier in performance of the Work or necessary for Company to operate, maintain, repair, modify or replace the Work or Facilities or any part thereof shall be the property of Company and shall be considered to be Confidential Information, and shall not be used by Supplier on other work and shall, on request, be returned or provided to Company upon the earlier of the termination of the Agreement or Final Completion. " | Section 23 and attachment XVII | 23.9 A Final Release of Liens shall be included with Supplier’s Final Invoice and with the Final Invoice submitted by each Subcontractor, prior to the release of Final Payment to Supplier by Company. |  | "Section 52 52.1 Supplier shall at all times take all necessary precautions to prevent the discharge of any Hazardous Material onto the site or into the environment during performance of the Work. To the extent that Company has actual knowledge thereof, Company shall inform Supplier of any conditions on or within the Project Site that pose hazards to the health or safety of persons or that may affect Supplier’s performance of the Work under this Agreement. " | ASAP - 52.4 If, in the course of performing the Work, Supplier encounters environmental conditions of which it has not been made aware by Company, including Pre-Existing Conditions, Supplier shall promptly notify Company of their existence and location, and shall cease all operations in the affected area until such time as Company and Supplier have had an opportunity to discuss such environmental conditions | 20.3 - Monthly schedule 54.4 - At Client's request to be performed by IMC and IMC's subcontractors: SOC 1 Type 2Audit report, performed by a client's acceptable firm, preferably KPMG, PwC, among others) Attachment XII - Quarterly diversity reports" | No |  | Yes | Yes | Non-Union | Yes | Attachment I Scope of Work Attachment II Compensation Attachment III Work Schedule Attachment IV Health & Safety Standards Attachment V Not Used Attachment VI Not Used Attachment VII Substantial Completion Certificate Attachment VIII Final Completion Certificate Attachment IX Data Privacy and Security Requirements Atttachment X Drug & Alcohol Program Attachment XI Change to Work Form Attachment XII Supplier Diversity Attachment XIII Transportation and Security Matters Attachment XIV Export Compliance Attachment XV Performance Bond Template Attachment XVI Advanced Payment Guarantee Template Attachment XVII Statutory Declaration and Release & Certificate of Final Payment Attachment XVIII Not Used Attachment XIX Collateral Warranty Template Attachment XX Not Used | Yes |  | "Section 41.1: Insurance requirement Comprehensive cyber/network/privacy liability $3,000,000 " | Section 41.3 The deductible associated with the Builders Risk insurance policy shall be the sole responsibility of the Company, and not the Supplier or its Subcontractors.
| 1 | 2023-04-25 | A195 - Integrated Project Delivery | [24 empty] | Yes | Yes | zdh | ADFN | dgb | No | zng | sfgn | Yes | Yes | Yes | DFB | DFB | DFB | No | No | DFB | No | DFB | DFB | DFB | DFB | DFB | DFB | DFB | Capped | DFB | No | DFB | DFB | DFB | ADF | DFB | DR | DFB | DSF | SF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | No | ESF | WEF | WEF | WEF | WEF | Yes | Yes | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | WEF | Yes | WEF | Yes | Yes | Union | No | WEF | No | WEF | WEF
| 2 | 2023-04-10 | A201 - Design Bid Build Standard |  | No | this is a test this is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a testthis is a test

## Sheet1
ID | Start time | Completion time | Email | Name | What is the Execution Date of the Contract Agreement? | What is the Bid Number for this Bid / Project? (Typically BYY.###) Example = B23.123 | What is the Project Number for this Project? (Typically YY.###) Example = 23.123 | What is the IMC Fee % for this Project? | What is the AIA Form of Contract Agreement? | What is the Contract Type for this Project? (Custom Text Answer) | Are there Consequential Damages on the Project? | What are the are the Consequential Damages Terms & Conditions? | Is there a mutual waiver of Consequential Damages in the Contract? | Are there Liquidated Damages on the Project? | What are the are the Liquidated Damages Terms & Conditions? | What is the Article # for Consequential & Liquidated Damages? | What is the CCIP Rate % for this Project? | Is IMC or the Owner carrying the Builder's Risk Policy for this project? | What is the Builders Risk %? | What is the Builders Risk Deductible? ($) | What is the Builders Risk Waiver of Subrogation Appendix / Exhibit (Letter or Number) if the Owner Carries the Policy | Is Professional Liability Insurance Required for this project? | Is Railroad Insurance Required for this project? | Is Pollution Liability Insurance Required for this project? | Is a Payment & Performance Bond Required for this project? | What is the Payment & Performance Bond Article #? | What are the Payment & Performance Bond Article Terms & Conditions? | What is the Contract Documents Definition & Incorporation Article #? | What are the Contract Documents Definition & Incorporation Definitions, Terms, & Conditions? | What is the IMC Design Document Review obligations Article #? | What are the Terms & Conditions / IMC's obligations for Design Document Review? | What is the Submittal Alternates, Substitutions, & Contract Document Deviations Article #? | What are the Submittal Alternates, Substitutions, & Contract Document Deviations Terms & Conditions? | Do we have a Precon Agreement? | Is Precon Reimbursable beyond the Agreement? | What is the Precon Reimbursable Contract Article #? | What are the Precon Reimbursable Terms & Conditions? | What is the Subcontractor Bid Requirements Article #? | Are the Subcontractor Bids / Bid Tabs Required to be Provided to Owner? | What is the Subcontractor Required Number of Bids per package? | What are the Subcontractor Bids / Bid Tabs Provided to Owner Terms & Conditions? | Does a Subcontractor Award have to be Approved by Owner? | Can Owner Mandate Specific Subcontractors be used? | Is IMC Entitled a PCCO for Owner Selected / Mandated Subcontractors? | What is the GMP Shared Savings Article #? | What are the GMP Shared Savings Terms & Conditions? | What is the GMP Buyout Savings Article #? | Do GMP Buyout Savings need to be Reported to Owner? | Must the GMP Buyout Savings be Shown on Monthly Schedule of Values? | What are the GMP Buyout Savings Definition & Terms & Conditions? | Must Use of Buyout Savings for Trade Costs be Approved by Owner? | What is the General Conditions Rate Sheet Appendix / Exhibit (A,B,C,D, Etc.)? | What is the General Conditions Rate Sheet Year? | What is the Cost of the Work Article #? | What is the definition for the Cost of the Work? | What is the Contingency Usage Article #? | What are the Contingency Usage Terms and Conditions? | What are the Contingency Usage Owner Notification Requirements? | What is the General Conditions Type? | What are the General Conditions Billing Backup Requirements? | Are there General Conditions / Requirements Owner Audit Provisions? | What is the definition of General Conditions for this project? (01 v 50 Code Split) | What is the Change Markup - Subcontractor %? | What is the Change Markup - Tiered Subcontractor %? | What is the Change Markup - IMC Fee %? | What is the Change Markup - CCIP %? | What is the Change Markup - Warranty %? | What is the Change Markup - General Conditions %? | What is the Change Markup - CM Insurance %? | What is the Change Markup - P & P Bond %? | What is the Adverse Weather Days Article #? | What are the Adverse Weather Days Terms & Conditions? | Within how many days must we notify the owner of adverse weather day impacts? | How many Adverse Weather Days Included in Contract Agreement? | What is the Schedule Requirements Article #? | What are the Schedule Requirements Terms & Conditions? | What is the Daily Log & Manpower Article #? | What are the Daily Log & Manpower Terms and Conditions? | What is the Schedule Delay / Time Issues Article #? | What are the Schedule Delay / Time Issues Terms & Conditions? | How much Schedule Delay / Time Issues Notice to Owner Requirements (Within What # of Days)? | What is the Schedule Acceleration Directed by Owner Article #? | What are the Schedule Acceleration Directed by Owner Terms & Conditions? | What are the Schedule Definitions of Days (Work / Calendar / Holidays / Etc.)? | What is the Substantial Completion Article #? | What are the Substantial Completion Terms & Conditions? | What is the Final Completion Definition Article #? | What is the Final Completion Definition? | Are there Project Interim Milestones? | Project Interim Milestones List | What is the Payment Terms (Progress & Final) Article #? | What are the Payment Terms Retainage %? | What is the Payment Terms for Retainage Reduction Article #? | What are the Payment Terms & Conditions for Retainage Reduction? | Are there Payment Terms for Retainage on General Conditions? | Are there Payment Terms for Retainage on Fee? | What is the Payment Terms for Offsite Stored Material Article #? | What are the Terms and Conditions for Payment of Offsite Stored Material? | How many days within Approved Application for Owner Payment? | What is the Article # for IMC's Stop Work Ability for late Owner payment? | What are the Terms & Conditions for IMC's Stop Work Ability for late Owner payment? | What is the Dispute Resolution Article #? | What is the CM Suspension / Termination Article #? | How many days notice must the Owner give IMC for CM Termination for Convenience? | How many days notice must the Owner give IMC for CM Termination for Cause? | What is the Direct Negotiation Duration (# of Days)? | What is the Mediation Duration (# of Days)? | What is the Mediator Selection Duration (# of Days)? | How many days after Mediator Selection is the Mediation Session? | What is the Warranty Terms & Conditions Article #? | What are the Warranty Terms & Conditions? | What is the As-Built / Record Documents Requirements Article #? | What are the As-Built / Record Documents Requirements? | What is the Final Payment Article #? | What are the Final Payment Terms & Conditions? | What is the Concealed / Unknown / Hazardous Conditions Article #? | What are the Concealed / Unknown / Hazardous Conditions Terms & Conditions? | How much Concealed / Unknown / Hazardous Conditions Notice to Owner Requirements (Within What # of Days)? | List the Owner / Project Required Reports | Is Owner Allowed to Occupy Building Prior to Substantial Completion Article? | If the Owner is Allowed to Occupy Building Prior to Substantial Completion, what is the Article #? | Hazardous Materials - IMC is Only Responsible Content Created by Us or our Subcontractors | Hazardous Materials - IMC is Entitled to Stop Work, and Recover Cost for Delay for Encountered Hazardous Material | What is the Labor? | Is IMC Responsible to Recover Delay (Cost & Schedule) for labor related work stoppage; strike etc.? | List all Contract Agreement Exhibit / Appendix (Letter / Number /Name) | Are there any Contract Agreement / Specifications Containing BIM Requirements? | What is the Cyber Indemnification / Hacking Article #? | What are the Cyber Indemnification / Hacking Article Terms & Conditions? | Who is Responsible to pay the Builders Risk Deductible? (May Vary Depending on Amount)

## Sheet2
ID | 1
Start time | 2023-04-25 15:13
Completion time | 2023-04-25 15:17
Email | dmaser@imcconstruction.com
Name | David Maser
What is the Execution Date of the Contract Agreement? | 2023-04-25
What is the Bid Number for this Bid / Project? (Typically BYY.###) Example = B23.123 | aery
What is the Project Number for this Project? (Typically YY.###) Example = 23.123 | 99.998
What is the IMC Fee % for this Project?
What is the AIA Form of Contract Agreement? | A195 - Integrated Project Delivery
What is the Contract Type for this Project? (Custom Text Answer)
Are there Consequential Damages on the Project?
What are the are the Consequential Damages Terms & Conditions?
Is there a mutual waiver of Consequential Damages in the Contract?
Are there Liquidated Damages on the Project?
What are the are the Liquidated Damages Terms & Conditions?
What is the Article # for Consequential & Liquidated Damages?
What is the CCIP Rate % for this Project?
Is IMC or the Owner carrying the Builder's Risk Policy for this project?
What is the Builders Risk %?
What is the Builders Risk Deductible? ($)
What is the Builders Risk Waiver of Subrogation Appendix / Exhibit (Letter or Number) if the Owner Carries the Policy
Is Professional Liability Insurance Required for this project?
Is Railroad Insurance Required for this project?
Is Pollution Liability Insurance Required for this project?
Is a Payment & Performance Bond Required for this project?
What is the Payment & Performance Bond Article #?
What are the Payment & Performance Bond Article Terms & Conditions?
What is the Contract Documents Definition & Incorporation Article #?
What are the Contract Documents Definition & Incorporation Definitions, Terms, & Conditions?
What is the IMC Design Document Review obligations Article #?
What are the Terms & Conditions / IMC's obligations for Design Document Review?
What is the Submittal Alternates, Substitutions, & Contract Document Deviations Article #?
What are the Submittal Alternates, Substitutions, & Contract Document Deviations Terms & Conditions?
Do we have a Precon Agreement? | Yes
Is Precon Reimbursable beyond the Agreement? | Yes
What is the Precon Reimbursable Contract Article #? | zdh
What are the Precon Reimbursable Terms & Conditions? | ADFN
What is the Subcontractor Bid Requirements Article #? | dgb
Are the Subcontractor Bids / Bid Tabs Required to be Provided to Owner? | No
What is the Subcontractor Required Number of Bids per package? | zng
What are the Subcontractor Bids / Bid Tabs Provided to Owner Terms & Conditions? | sfgn
Does a Subcontractor Award have to be Approved by Owner? | Yes
Can Owner Mandate Specific Subcontractors be used? | Yes
Is IMC Entitled a PCCO for Owner Selected / Mandated Subcontractors? | Yes
What is the GMP Shared Savings Article #? | DFB
What are the GMP Shared Savings Terms & Conditions? | DFB
What is the GMP Buyout Savings Article #? | DFB
Do GMP Buyout Savings need to be Reported to Owner? | No
Must the GMP Buyout Savings be Shown on Monthly Schedule of Values? | No
What are the GMP Buyout Savings Definition & Terms & Conditions? | DFB
Must Use of Buyout Savings for Trade Costs be Approved by Owner? | No
What is the General Conditions Rate Sheet Appendix / Exhibit (A,B,C,D, Etc.)? | DFB
What is the General Conditions Rate Sheet Year? | DFB
What is the Cost of the Work Article #? | DFB
What is the definition for the Cost of the Work? | DFB
What is the Contingency Usage Article #? | DFB
What are the Contingency Usage Terms and Conditions? | DFB
What are the Contingency Usage Owner Notification Requirements? | DFB
What is the General Conditions Type? | Capped
What are the General Conditions Billing Backup Requirements? | DFB
Are there General Conditions / Requirements Owner Audit Provisions? | No
What is the definition of General Conditions for this project? (01 v 50 Code Split) | DFB
What is the Change Markup - Subcontractor %? | DFB
What is the Change Markup - Tiered Subcontractor %? | DFB
What is the Change Markup - IMC Fee %? | ADF
What is the Change Markup - CCIP %? | DFB
What is the Change Markup - Warranty %? | DR
What is the Change Markup - General Conditions %? | DFB
What is the Change Markup - CM Insurance %? | DSF
What is the Change Markup - P & P Bond %? | SF
What is the Adverse Weather Days Article #? | WEF
What are the Adverse Weather Days Terms & Conditions? | WEF
Within how many days must we notify the owner of adverse weather day impacts? | WEF
How many Adverse Weather Days Included in Contract Agreement? | WEF
What is the Schedule Requirements Article #? | WEF
What are the Schedule Requirements Terms & Conditions? | WEF
What is the Daily Log & Manpower Article #? | WEF
What are the Daily Log & Manpower Terms and Conditions? | WEF
What is the Schedule Delay / Time Issues Article #? | WEF
What are the Schedule Delay / Time Issues Terms & Conditions? | WEF
How much Schedule Delay / Time Issues Notice to Owner Requirements (Within What # of Days)? | WEF
What is the Schedule Acceleration Directed by Owner Article #? | WEF
What are the Schedule Acceleration Directed by Owner Terms & Conditions? | WEF
What are the Schedule Definitions of Days (Work / Calendar / Holidays / Etc.)? | WEF
What is the Substantial Completion Article #? | WEF
What are the Substantial Completion Terms & Conditions? | WEF
What is the Final Completion Definition Article #? | WEF
What is the Final Completion Definition? | WEF
Are there Project Interim Milestones? | No
Project Interim Milestones List | ESF
What is the Payment Terms (Progress & Final) Article #? | WEF
What are the Payment Terms Retainage %? | WEF
What is the Payment Terms for Retainage Reduction Article #? | WEF
What are the Payment Terms & Conditions for Retainage Reduction? | WEF
Are there Payment Terms for Retainage on General Conditions? | Yes
Are there Payment Terms for Retainage on Fee? | Yes
What is the Payment Terms for Offsite Stored Material Article #? | WEF
What are the Terms and Conditions for Payment of Offsite Stored Material? | WEF
How many days within Approved Application for Owner Payment? | WEF
What is the Article # for IMC's Stop Work Ability for late Owner payment? | WEF
What are the Terms & Conditions for IMC's Stop Work Ability for late Owner payment? | WEF
What is the Dispute Resolution Article #? | WEF
What is the CM Suspension / Termination Article #? | WEF
How many days notice must the Owner give IMC for CM Termination for Convenience? | WEF
How many days notice must the Owner give IMC for CM Termination for Cause? | WEF
What is the Direct Negotiation Duration (# of Days)? | WEF
What is the Mediation Duration (# of Days)? | WEF
What is the Mediator Selection Duration (# of Days)? | WEF
How many days after Mediator Selection is the Mediation Session? | WEF
What is the Warranty Terms & Conditions Article #? | WEF
What are the Warranty Terms & Conditions? | WEF
What is the As-Built / Record Documents Requirements Article #? | WEF
What are the As-Built / Record Documents Requirements? | WEF
What is the Final Payment Article #? | WEF
What are the Final Payment Terms & Conditions? | WEF
What is the Concealed / Unknown / Hazardous Conditions Article #? | WEF
What are the Concealed / Unknown / Hazardous Conditions Terms & Conditions? | WEF
How much Concealed / Unknown / Hazardous Conditions Notice to Owner Requirements (Within What # of Days)? | WEF
List the Owner / Project Required Reports | WEF
Is Owner Allowed to Occupy Building Prior to Substantial Completion Article? | Yes
If the Owner is Allowed to Occupy Building Prior to Substantial Completion, what is the Article #? | WEF
Hazardous Materials - IMC is Only Responsible Content Created by Us or our Subcontractors | Yes
Hazardous Materials - IMC is Entitled to Stop Work, and Recover Cost for Delay for Encountered Hazardous Material | Yes
What is the Labor? | Union
Is IMC Responsible to Recover Delay (Cost & Schedule) for labor related work stoppage; strike etc.? | No
List all Contract Agreement Exhibit / Appendix (Letter / Number /Name) | WEF
Are there any Contract Agreement / Specifications Containing BIM Requirements? | No
What is the Cyber Indemnification / Hacking Article #? | WEF
What are the Cyber Indemnification / Hacking Article Terms & Conditions? | WEF
Who is Responsible to pay the Builders Risk Deductible? (May Vary Depending on Amount)

## _56F9DC9755BA473782653E2940F9 (hidden)
P0YbIax95UuNtfh0kfaJ6QenDOCl-mFJov_kZV9wTP1UMVBETVBIQjNOUjlFVEUxQjE4MFVUSzBFSCQlQCN0PWcu
Form1
{bba344bd-0d21-46cb-9be1-bf9c2d276fef}
17